MTM Open Quality Items as of 9/6/06

VVSA-1

- Address Data package comments.

  - Provided corrected RT report 1MC115320 (???)

My notes from the 5/25/06 visit where I spent significant time with Doug looking at documentation of weld repairs shows: “1MC115320 shows the wrong film orientation – MTM will fix”.

13Sep2006: The document has been updated (new file name MC119826.tif).   Is part of the updated data package.

18Sep2006:  Updated data package uploaded to PPPL ftp site.

  - Locate/add documentation of 100% RT of Port 12A & 12B welds. - - - Done and is part of updated data package.

The package we have or one that is forthcoming?

13Sep2006:  Yes (forthcoming)

18Sep2006:  Updated data package uploaded to PPPL ftp site.

  - Clarify what the files in the VVSA-1 Final Quality Documentation are. (???)

The files uploaded to our ftp site included a folder named VVSA-1 Final Quality Documentation.  It appears to contain various iterations of documentation in tif & pdf formats. Some are related to heat treatment. What are they documenting? Are they all needed or is one the complete version?

13Sep2006:  Sorry, I still don’t understand the comment.  I checked the ftp directories and cannot locate…….(???)

18Sep2006:  No change.

  - Provide the completed travelers (Done)

Where?  Note that the Processing Histories provided are the updated processing plans, not signed off records of activity completion.

13Sep2006:  Our electronic transactions (signoffs) are stored within the MTM Quality System Database.  MTM only planned to provide the process outline / process history already submitted as discussed in previous contract negotiations.

18Sep2006:  Mike Manuel and Mike Viola discussing.

  - Special process personnel qualifications required by the SOW (5.4) Provided  (Done)

Done

  - Provide an updated graphic of the processing (Visual Manufacturing).  (working)

13Sep2006:  This is still work in progress.

18Sep2006:  No change.

  - Replace black and white segmentation chart with a color version, if practical. Copy Provided-one will also go into Data Book (Done, will be included in next data package upload)

  - The following VVSA-1 NC’s are not in the Data Book:

17288

17342

18526

18888

19667

19754

19108

19149

19289

  - Changes made: Again the implication is that we have a new data book forthcoming. Is this correct?  13Sep2006:  Yes. 18Sep2006:  Updated data package uploaded to PPPL ftp site.

    - 17288 in lot 9 data book

    - 17342 in lot 1 data book

    - 18526 in lot 7 data book

    - 18888 Superseded by 19776

We cannot have an NCR left hanging.  Please provide updated copy of this and 19754 with annotation that it was superseded by 19776  13Sep2006:  Done

    - 19667 in lot 1 data book

    - 19754 superseded by 19776

    - 19108 in lot 1 data book

    - 19149 in lot 9 data book

    - 19289 in lot 1 data book

  - NC19739 is in Data Book (w/o PPPL signatures), but I can’t find any record of it. Was this submitted to and approved by PPPL?

  - NCR19739 was created during the discussion and understanding development of the 0.637” dimension.  I’ll have to research this one further….More to follow….

13Sep2006:  Still work in progress.

15Sep2006:  NCR 19391,392, and 393 cover the same information and are included (with disposition) in the data package.  19739 is obsolete and has been removed from the data package.

  - NC19464a is listed in the TOC, but is not in Data Book & not in our records.

  - NCR19464 has been updated to include disposition (19464A not required)

An updated data book that PPPL doesn’t yet have?

13Sep2006:  Yes

18Sep2006:  Updated data package uploaded to PPPL ftp site.

  - NC19612a is in Data Book, but not listed in TOC.

  - NCR19612a in data book TOC.

An updated data book that PPPL doesn’t yet have?

13Sep2006:  Yes

18Sep2006:  Updated data package uploaded to PPPL ftp site.

VVSA-2

- PPPL to review final data package

VVSA-3

- Need NC for boss misalignments  (NCR20384 includes boss locations)

Yes and this NC is in processing at NCSX now.

13Sep2006:  Received today and added to data book.

18Sep2006:  Updated data package uploaded to PPPL ftp site.

- Need corrective action documented for NC 20282, grind flange seal weld prep to ensure 0.62” min.  (NCR updated to include confirmation of corrective action)

Yet to be submitted?

13Sep2006:  Sent today.

- Need PPPL disposition for:

  - NC 20353 - profile of the spacer - DONE

  - NC 20354 - flatness of the VV Flange Seal on half b - DONE

  - NC 20384 – final shell dimensional - in processing at NCSX now

13Sep2006:  Received today and added to data book.

18Sep2006:  Updated data package uploaded to PPPL ftp site.

- Need Lot 3 & 6 Data Books.  (Lot 6 uploaded, Lot 3 awaiting disposition of NCR 20384)

13Sep2006:  MTM QA dept. compiling data book today / tomorrow (was waiting on NCR 20384 disposition)

18Sep2006:  Updated data package uploaded to PPPL ftp site.

- Need Lot 3, 6, 9 Process History  (Done)

Same question as 1d, above.

13Sep2006:  (See above)

18Sep2006:  No change.