## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Description:
This WBS element consists of the manufacturing design, procurement, and fabrication of the TF conductor and assembly of the TF winding packs including interface elements for connections to power and cooling supply at the coils.
Schedule:
See Attached
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Responsible Line Manager
_______________________________________________________
Project Manager
_______________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [15 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
In Table II Estimate

## Table II - M&S
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Materials and Subcontracts (M&S)
Description: | $ |  |  |  |  | HOURS
| 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
Procrurement & Fabrication
Contract Costs Remaining |  | 502092 | [13 empty] | Per contaract | 7 | 502092 | 0
0
Title III /Engrg | 5000 | [10 empty] | 240 |  |  | 480 | Based on 15% coverage for Kalish and 30% coverage for Meighan through 10/08. This is the level of coverage that has been required now that the operation is becoming more routine | 8 | 5000 | 720
In House Inspection | [10 empty] | 68 | 96 |  |  |  | Cover inspection for 18 coils, two engs - six days for the first coil, .5 day for one technician for subsequent coils | 8 | 0 | 164
Support of Assembly operations and metrology | [11 empty] | 84.4 |  |  |  | .25% coverage during 35days FP#1 assembly of TFs + 10% coverage for 18days of FP#2 TF assembly | 8 | 0 | 84.4
Additional Materials as Required | 4000 | [14 empty] | Actual purchases ($4K for glass insulation) => expected one more time | 8 | 4000 | 0
TOTAL | 9000 | 502092 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 420.4 | 0 | 0 | 480 |  |  | 511092 | 968.4
[17 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[11 empty] | 1 - National Standards | [5 empty] | 1 | 0 | 0 | 0% | 0%
[11 empty] | 2 - Engineering Judgement/Experience | [5 empty] | 2 | 0 | 0 | 0% | 0%
[11 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) | [5 empty] | 3 | 0 | 0 | 0% | 0%
[11 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) | [5 empty] | 4 | 0 | 0 | 0% | 0%
[11 empty] | 5 - Prototype Data/Test Results | [5 empty] | 5 | 0 | 0 | 0% | 0%
[11 empty] | 6 - Catelogue Price/Vendor Quote | [5 empty] | 6 | 0 | 0 | 0% | 0%
[11 empty] | 7 - Placed Contracts | [5 empty] | 7 | 502092 | 0 | 98.24% | 0%
[11 empty] | 8 - Actual experience for NCSX Work | [5 empty] | 8 | 9000 | 968.4 | 1.761% | 100%
[11 empty] | 9 - Other | [5 empty] | 9 | 0 | 0 | 0% | 0%
[16 empty] | TOTALS |  | 511092 | 968.4 | 100% | 100%

## Table III - FabAssy & Instl
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
In-house Fabrication and Assembly and Installation
Description: Incl in M&S Table II

## Table IV - Conting & Risk
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Cionsiderations
| Design Maturity | X |  |  |  | Coils in fabrication - design is complete
-10%/+15%
| Design Complexity |  | X |  |  | While conventional cross-section with solid Cu, some potential difficulty in maintain precise geometry and tolerances
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil |  |  |  | VU | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0
1361 | Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair (Also impacts Jobs 1352 & 7503) |  |  |  | VU | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . | Insulation fault in lead area is considered the most likely failure scenario. Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellarator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2
1361 | Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core (Also impacts Jobs 1352 & 7503) |  |  |  | NC | 1st of each kind will be tested at cryogenic temperature at elevated (50% higher than routine field tests) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher than routine field tests) voltage for faults to ground . | High impact-low probability event not covered by contingency
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)