## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Description:
Job 1408 consists of all the procured components for the modular coil windings, and includes the cable conductor, kapton and glass insulation, epoxy, coil clamps, cooling lines, lead blocks, fillers, etc. Job 1451 consists of all the labor required to wind conductor, vacuum bag, vacuum impregnate with epoxy, connect cooling lines, and inspect the modular coils. This WBS element consists of all punch list items need to finalize the fabrication of each modular coil.
Schedule:
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Responsible Line Manager
_______________________________________________________
Project Manager
_______________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [16 empty] | Basis of Estimate
|  | FY07$K |  |  |  |  | HOURS
Task ID | Comments | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
No Design Work Associated with This Job

## Table II - M&S
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Materials and Supplies
All M&S included in Table III

## Table III Fab & Assy
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Fabrication and Assembly
Conditions and Basis for Estimate
1) All estimates are based on work performed from Dec 1, 2007 through the end of modular coil fabrication program
2) Labor estimates are based on actual in-field times as well as consultation with metrology personnel and technicians
[10 empty] | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
|  | EAEM | EAEM | EMSM | EMEM
TASK DESCRIPTION |  | Chrz. | Raft. | Meighan | Languish
| 9450-1***-1451 | hr/month | hr/month | hr/month | hr/month
Engineering and Oversight |  | 70% | 40% | 70% | 40%
LOE FY08 (October thru December) |  | 120 | 70 | 120 | 70
Engineering and Oversight |  | 50% | 40% | 70% | 40%
LOE FY08 (January thru August) |  | 90 | 70 | 120 | 70 |  |  |  |  | Based on MCWF actuals to date | 8 | 0 | 350
[10 empty] | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
Casting Preparation |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours]
RESA Building Activities
Unload & unbox winding form | 9450-1***-1459 | 0.5 | 0 | 0 | 0 | 12 | 0 | 0 | COMPLETE
Inspect casting [surfaces, magnetic permeability] | 9450-1***-1451 | 0.5 | 1 | 8 | 4 | 0 | 0 | 0 | COMPLETE
Winding form modifications | 9450-1***-1459 | 3 | 0 | 0 | 0 | 48 | 0 | 0 | COMPLETE
Station 1a/4 Activities
Position & mount WF to support ring | 9450-1***-1451 | 2 | 3 | 9 | 54 | 32 | 0 | 0 | COMPLETE
Install coil in station 4 turning fixture | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 1 | 40 | A6 | Based on MCWF actuals to date | 8 | 0 | 40
Install weights and balance casting and ring assembly | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 1 | 16 | A6 | Based on MCWF actuals to date | 8 | 0 | 16
Weld monuments, stud adapters & lead nuts | 9450-1***-1451 | 2.5 | 1 | 8 | 20 | 16 | 1 | 36 | A6 | Based on MCWF actuals to date | 8 | 0 | 36
Measure casting wings using metrology equipment | 9450-1***-1451 | 2 | 2 | 8 | 32 | 0 | 1 | 32 | A6 | Based on MCWF actuals to date | 8 | 0 | 32
Install studs for winding clamps | 9450-1***-1451 | 2 | 3 | 8 | 48 | 0 | 1 | 48 | A6 | Based on MCWF actuals to date | 8 | 0 | 48
Electrical test poloidal break | 9450-1***-1451 | 0.5 | 1 | 8 | 4 | 0 | 1 | 4 | A6 | Based on MCWF actuals to date | 8 | 0 | 4
Clean casting [Inspect and clean all holes] | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 1 | 16 | A6 | Based on MCWF actuals to date | 8 | 0 | 16
Install Kapton edging and mold release winding surface | 9450-1***-1451 | 2 | 2 | 8 | 32 | 0 | 1 | 32 | A6 | Based on MCWF actuals to date | 8 | 0 | 32
Fitup Lead blocks and terminals [Remove lead blocks] | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 1 | 16 | A6 | Based on MCWF actuals to date | 8 | 0 | 16
Cladding final clean & Kapton [Parallel activity] | 9450-1***-1451 | 7 | 1 | 8 | 56 | 0 | 1 | 56 | A6 | Based on MCWF actuals to date | 8 | 0 | 56
Install inner cladding plates and cooling Tubes | 9450-1***-1451 | 5 | 3 | 8 | 120 | 0 | 1 | 120 | A6 | Based on MCWF actuals to date | 8 | 0 | 120
[8 empty] | 416 | TOTALS hours |  |  |  | 416
Coil Winding Station 2, 3, and 4 |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] |  | Revised
Prep for Winding
Prepare coil for transfer | 9450-1***-1451 | 0.5 | 2 | 9 | 9 | 0 | 1 | 9 | Coils A6 | Based on MCWF actuals to date | 8 | 0 | 9
Install winding form in turning fixture | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 1 | 40 | Coils A6 | Based on MCWF actuals to date | 8 | 0 | 40
Install upper Tee for coil clamps | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 1 | 36 | Coils A6 | Based on MCWF actuals to date | 8 | 0 | 36
Install/set winding clamps side bars A & B | 9450-1***-1451 | 4 | 3 | 9 | 108 | 0 | 1 | 108 | Coils A6 | Based on MCWF actuals to date | 8 | 0 | 108
Prep groundwrap insulation [Parallel activity] | 9450-1***-1451 | 6 | 1 | 9 | 54 | 0 | 1 | 54 | Coils A6 | Based on MCWF actuals to date | 8 | 0 | 54
Re-install G-11 lead blocks- sides A & B | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 2 | 36 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 36
Position inner GW insulation onto winding form (sides A & B) | 9450-1***-1451 | 7 | 2 | 9 | 126 | 0 | 2 | 252 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 252
Position lacing strips sides A & B | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 2 | 72 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 72
Wind Side "A"
Braze & secure 1st. coil lead set [inc. brazing] | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 2 | 72 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 72
Position leads & Wind side A | 9450-1***-1451 | 13 | 2.5 | 9 | 292.5 | 0 | 2 | 585 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 585
Reposition coil from side A to side B | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 2 | 80 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 80
Wind Side "B"
Braze & secure 1st. coil lead set [inc. brazing] | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 2 | 72 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 72
Position leads & Wind side B | 9450-1***-1451 | 13 | 2.5 | 9 | 292.5 | 0 | 2 | 585 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 585
Final coil winding activities
Measure, reposition & re-measure coil bundle [sides A & B] | 9450-1***-1451 | 8 | 3 | 8 | 192 | 0 | 2 | 384 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 384
Secure Lacing | 9450-1***-1451 | 2.5 | 2 | 8 | 40 | 0 | 3 | 120 | Coils B5, A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 120
Complete groundwrap installation | 9450-1***-1451 | 7 | 2 | 8 | 112 | 0 | 4 | 448 | Coils B5, A6 and B6, C6 | Based on MCWF actuals to date | 8 | 0 | 448
Unanticipated Delays/Rework Activities
Tasks TBD | 9450-1***-1451 | 3 | 3 | 8 | 72 | 0 | 8 | 576 |  | Based on MCWF actuals to date |  | 0 | 576
[8 empty] | 3529 | TOTALS hours |  |  |  | 3529
Final Coil prep & Mold Application [Stations 2, 3 & 4] |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining | Revised
Final Coil Prep
Clean chill plates [Parallel activity] | 9450-1***-1451 | 4 | 1 | 8 | 32 | 0 | 2 | 64 | Coils A6 and B6 | Based on MCWF actuals to date | 8 | 0 | 64
Install chill plates & Tubing | 9450-1***-1451 | 13 | 2.5 | 8 | 260 | 0 | 4 | 1040 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 1040
Cut, braze, silverplate and position 2nd. coil lead set [side A] | 9450-1***-1451 | 3 | 2 | 8 | 48 | 0 | 4 | 192 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 192
Cut, braze, silverplate and position 2nd. Coil lead set [side B] | 9450-1***-1451 | 3 | 2 | 8 | 48 | 0 | 4 | 192 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 192
Soft solder and clean all lead joints | 9450-1***-1451 | 2 | 1 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Install outer co-wound Diagnostic loops | 9450-1***-1451 | 2 | 2 | 8 | 32 | 0 | 4 | 128 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 128
Measure position of co-wound diagnostic loops | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Perform pre-VPI elect. & pressure tests
Pressure test cryo lines | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Perform preliminary [pre-vpi] electrical tests | 9450-1***-1451 | 0.5 | 2 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Install bag mold around modular coil
Prep sprue sub-assemblies [Parallel activity] | 9450-1***-1451 | 1 | 1 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Prep lead sprue sub-assemblies [Parallel activity] | 9450-1***-1451 | 0.5 | 1 | 8 | 4 | 0 | 4 | 16 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 16
Install G-11 final clamp pads & sprue bases | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Finalize and secure G-11 lead box | 9450-1***-1451 | 1 | 1 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Install glass roving and sheet over chill plates | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Install silicone bag & sprues | 9450-1***-1451 | 5 | 2 | 8 | 80 | 0 | 4 | 320 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 320
Vacuum pumpdown/ RTV overcoat & leak repair | 9450-1***-1451 | 2 | 3 | 8 | 48 | 0 | 4 | 192 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 192
Install epoxy shell | 9450-1***-1451 | 3 | 3 | 8 | 72 | 0 | 4 | 288 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 288
[8 empty] | 2848 | Totals Hours |  |  |  | 2848
VPI Activities (Station 5) |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Final VPI Prep
Prepare MC for transfer | 9450-1***-1451 | 0.5 | 2 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Transfer modular coil to Autoclave | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 4 | 160 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 160
Prepare MC for VPI [Connect fill lines & TC; leak check] | 9450-1***-1451 | 3 | 3 | 8 | 72 | 0 | 4 | 288 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 288
Vacuum pumpdown & preheat mold and autoclave | 9450-1***-1451 | 2 | 3 | 10 | 60 | 0 | 4 | 240 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 240
VPI modular coil
Epoxy mix and fill coil | 9450-1***-1451 | 1 | 4 | 12 | 48 | 0 | 4 | 192 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 192
Temperature rampup and Cure | 9450-1***-1451 | 3 | 2 | 12 | 72 | 0 | 4 | 288 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 288
Temperature rampup and Post cure | 9450-1***-1451 | 2 | 2 | 12 | 48 | 0 | 4 | 192 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 192
Temperature rampdown | 9450-1***-1451 | 1 | 1 | 10 | 10 | 0 | 4 | 40 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 40
Cleanup & ready autoclave for coil removal | 9450-1***-1451 | 3 | 3 | 8 | 72 | 0 | 4 | 288 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 288
Rebuild manifolds and prep autoclave for next VPI | 9450-1***-1451 | 6 | 3 | 8 | 144 | 0 | 4 | 576 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 576
[8 empty] | 2296 | Totals Hours |  |  |  | 2296
Post VPI Activities (Station 1) |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Prepare coil for transfer | 9450-1***-1451 | 0.5 | 2 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Transfer modular coil from Autoclave to Station #1 | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 4 | 160 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 160
Remove studs, structural shell & sprues | 9450-1***-1451 | 9 | 2 | 8 | 144 | 0 | 4 | 576 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 576
Install final coil clamps | 9450-1***-1451 | 3.5 | 2 | 8 | 56 | 0 | 4 | 224 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 224
Perform (room temperature) electrical & Pressure Tests | 9450-1***-1451 | 1 | 2 | 8 | 16 | 0 | 4 | 64 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 64
Remove coil from ring assembly | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 4 | 160 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 160
[8 empty] | 1216 | TOTALS hours |  |  |  | 1216
Punch List Items |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Mount diagnostic boxes | 9450-1***-1459 | 0.5 | 2 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Route and secure diagnostic wires to box | 9450-1***-1459 | 0.5 | 2 | 8 | 8 | 0 | 4 | 32 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 32
Install final clamps [coils previously finished] | 9450-1***-1459 | 3 | 2 | 8 | 48 | 0 | 0 | 0 | COMPLETE
Finalize cooling tubes | 9450-1***-1459 | 1 | 2 | 8 | 16 | 0 | 6 | 96 | B4, B5, B6, C6, A5, A6 | Based on MCWF actuals to date | 8 | 0 | 96
Install Rogowski coils | 9450-1***-1459 | 2 | 2 | 8 | 32 | 0 | 2 | 64 | Coils A3 and A4 | Based on MCWF actuals to date | 8 | 0 | 64
Test thermocouples & strain gages | 9450-1***-1459 | 0 | 0 | 0 | 10 | 0 | 6 | 60 | Only strain gages remain | Based on MCWF actuals to date | 8 | 0 | 60
Install thermocouples | 9450-1***-1459 | 0 | 1 | 0 | 32 | 0 | 11 | 352 | 11 remaining coils | Based on MCWF actuals to date | 8 | 0 | 352
Test additional thermocouples | 9450-1***-1459 |  |  |  | 10 |  | 18 | 180 |  | Based on MCWF actuals to date | 8 | 0 | 180 | NEW
Install additional [170] thermocouples per design change | 9450-1***-1459 |  | 1 |  | 24 | 0 | 18 | 432 | 18 coils | Based on MCWF actuals to date | 8 | 0 | 432 | NEW
Extend length of existing TC's [216] | 9450-1***-1459 |  | 1 |  | 24 |  | 18 | 432 | 18 coils | Based on MCWF actuals to date |  | 0 | 432 | NEW
Install strain gages | 9450-1***-1459 |  |  |  | 24 | 0 | 6 | 144 | Last FPA only | Based on MCWF actuals to date | 8 | 0 | 144
Measure final coil clamp surfaces | 9450-1***-1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DELETE
Install Thermal Insulation over coil | 9450-1***-1459 | 3 | 2 | 8 | 48 | 0 | 11 | 528 | A3, A4, A6, B2, B3, B5, B6, C3 thru C6 | Based on MCWF actuals to date | 8 | 0 | 528
Replace co-wound loop on C4 | 9450-1***-1459 | 1 | 2 | 8 | 16 | 0 | 0 | 0 | COMPLETE
Install additional flange holes [12 per type "C" winding form] | 9450-1***-1459 | 0 | 0 | 0 | 0 | 192 | 3.5 | 672 | C3, C4, C5, C6 | Based on MCWF actuals to date | 8 | 0 | 672
Measure as built coils as required | 9450-1***-1459 | 2 | 2 | 8 | 32 | 0 | 11 | 352 |  | Based on MCWF actuals to date | 8 | 0 | 352
Ground Poloidal Break Hardware | 9450-1***-1459 | 0 | 0 | 0 | 0 | 2 | 6 | 12 | B4, B5, B6, C4, C6, A4 | Based on MCWF actuals to date | 8 | 0 | 12
Ground lead jumper studs | 9450-1***-1459 | 0.2 | 1 | 8 | 1.6 | 0 | 4 | 6.4 | B5, B6, C6, A6 | Based on MCWF actuals to date | 8 | 0 | 6.4
Grind flange pockets for hardware | 9450-1***-1459 | 0 | 0 | 0 | 0 | 24.4 | 6 | 146.4 | Includes crane activities assoc. with task | Based on MCWF actuals to date | 8 | 0 | 146.4
Grind winding form wings/clearances | 9450-1***-1459 | 0 | 0 | 0 | 0 | 24 | 8 | 192 | A2, A5, B4, B5, B6, C4, C6, C6 | Based on MCWF actuals to date | 8 | 0 | 192
New Scope
Coil to Coil fitup modifications [grinding/chill plates] | 9450-1***-1459 |  |  |  | 24 | 24 | 12 | 576 | Each B to C requires mod | Based on MCWF actuals to date | 8 | 0 | 576
[6 empty] | 300 |  | 300 | Unknown work that may result from fitup trials | Based on MCWF actuals to date | 8 | 0 | 300
Additional hours for crane activities associated with punch list- RESA Work | [5 empty] | 48 | 10 | 480 |  | Based on MCWF actuals to date | 8 | 0 | 480
[8 empty] | 5088.8 | TOTALS hours |  |  |  | 5088.8
|  |  | Coil Tech | Coil Tech | Tech Shop | No. of | TOTAL | M&S
MATERIAL & SUPPLIES | Job Number |  | [hours per | [hours per | Support | coils | Tech | w/o G&A | COILS
|  |  | shift] | coil] | [hours] | remaining | Hours
Coil Supplies
1) Insulation | 9450-1***-1408 |  |  | 0 | 0 | 2 |  | 2000 |  | Based placed contracts/vendor quotes | 6 | 2000 | 0
2) Epoxy- CTD-101 [$4500.00 per coil @ assume 5 injections] | 9450-1***-1408 |  |  | 0 | 0 | 4 |  | 22500 | Coils A6; B5, B6 and C6 | Based placed contracts/vendor quotes | 6 | 22500 | 0
3) Miscellaneous and safety supplies [@ $7000/month] | 9450-1***-1408 |  |  | 0 | 0 | 4 |  | 42000 | approx. 6 months | Based placed contracts/vendor quotes | 6 | 42000 | 0
4) Strain gages | 9450-1***-1408 | [6 empty] | 30000 |  | Based placed contracts/vendor quotes | 6 | 30000 | 0
5) Additional thermocouples for modular coils per revised requirements- assembly drawings | 9450-1***-1408 | [6 empty] | 35000 |  | Based placed vendor quotes & engr judgement |  | 35000
6) Cutting hardware for flange bolts | 9450-1***-1459 | [6 empty] | 1500 |  | Based placed contracts/vendor quotes | 6 | 1500 | 0
VPI Supplies
1) Epoxy/glass for mold shell [Hysol] | 9450-1***-1408 |  |  | 0 | 0 | 4 |  | 5500 |  | Based placed contracts/vendor quotes | 6 | 5500 | 0
2) VPI clean manifold contract [$1100.00 per VPI] | 9450-1***-1408 |  |  | 0 | 0 | 4 |  | 5000 |  | Based placed contracts/vendor quotes | 6 | 5000 | 0
Tech Shop Support-
Miscellaneous activities- TBD | 9450-1***-1408 |  |  | 0 | 80 | 4 | 320 |  | Coils A4-A6; B3-B6 and C6 | Based on MCWF actuals to date | 8 | 0 | 320
Miscelleneous Tech shop support for MC mods during FPA | 9450-1***-1459 | [5 empty] | 320 |  |  | Engineering Judgement/Experience | 8 | 0 | 320 | NEW
[8 empty] | 143500 | TOTALS |  |  | 143500 | 640
[11 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[9 empty] | 1 - National Standards |  | 1 | 0 | 0 | 0% | 0%
[9 empty] | 2 - Engineering Judgement/Experience |  | 2 | 0 | 0 | 0% | 0%
[9 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | 0 | 0% | 0%
[9 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 0 | 0 | 0% | 0%
[9 empty] | 5 - Prototype Data/Test Results |  | 5 | 0 | 0 | 0% | 0%
[9 empty] | 6 - Catelogue Price/Vendor Quote |  | 6 | 143500 | 0 | 100% | 0%
[9 empty] | 7 - Placed Contracts |  | 7 | 0 | 0 | 0% | 0%
[9 empty] | 8 - Actual Costs/Schedule for NCSX Work |  | 8 | 0 | 16383.8 | 0% | 100%
[9 empty] | 9 - Other |  | 9 | 0 | 0 | 0% | 0%
[10 empty] | Totals |  | 143500 | 16383.8 | 100% | 100%

## Table IV - Conting & Risk
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
Job 1408 |  |  |  |  | -5%/+10%
| Design Maturity | X |  |  |  | Mostly off-the-shelf items
| Design Complexity |  |  | X |  | Mostly off-the-shelf items
Job 1451 |  |  |  |  | -10%/+15%
| Design Maturity | X |  |  |  | Known and proven procedures and processes
| Design Complexity |  | X |  |  | Have built & Test 14 coils and have proven processes even with tight metrology and tolerances.
Job 1459 |  |  |  |  | -10%/+15%
| Design Maturity |  | X |  |  | Still uncertainty on number of field changes (e.g., number of holes, etc.)
| Design Complexity |  |  | X |  | Standard field work.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1408 - NONE
1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound (Please see Assumptions) |  |  |  | U | Continue to use same rigorous process used for first 12 coils during which there were no fabrication mihaps requiring re-winding a coil | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 400 | 450 | 0 | 2 | RR#6 | 16 of 18 coils successfully wound.Remaining 2 coils in winding process.
1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station |  |  |  | U | Critical spare components are availble from winding station #2 that is no longer being used | ~$5K for repair costs | 5 | 10 | 0 | 0 | RR#7 | Future risk, has not occurred yet - N/A
1451 | Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly |  |  |  | NC | C1 tested at full current at cryogenic temperature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. In addition, routine field tests will be performed on each assembly station to ensure that the electrical | High impact-low probability event not covered by contingency |  |  |  |  | RR#17 | 16 of 18 coils successfully wound.Remaining 2 coils in winding process.
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur. | [6 empty] | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Assumptions Cost: Would need ~$4.5K of Expoxy + ~$3K of insulation + $1.5K of shell + ~$5K of other misc components/materials + cost of new lead blocks of ~$15K => round off to ~$35K. Labor ~$380K assuming ~4.5 months to rework and redo coil. Schedule: To redo the coil: Need 138 shifts x 3 men/shift x 8 hours/shift => 3 months + To rework of ~65 shifts x 3 men/shift x 8 hours/shift => 1.5 months. Need an additional ~3 months to order lead blocks if needed. Anticipate ~3 months to re-order and obtain new lead blocks. If Type B coil is the one to fail, could add 1-2 months to critcal path at an added "standing army" cost of ~$260K/months or ~$520K.

## Table V - Basis of Estimate
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski