## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702)
Job Title: Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Description:
This WBS element consists of the design and fabrication of the base support structure. The base support structure consists of the base column assemblies, interconnecting beams and column base hardware.
Schedule:
See Attached
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Responsible Line Manager
________________________________________________________
Project Manager
________________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Description:
Title I and II Engineering for Base Support Structures and Title III Support of Fabrication Effort.
|  | $ |  |  |  |  | HOURS
Task ID |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EADD | EMSM | EMSB | EMTB | EAD* | EASB | EEEM | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
TITLE I DESIGN COMPLETED
TITLE II DESIGN
| Base Support layout & design | [7 empty] | 420 | [6 empty] | Prior experience on similar work - See Note below | 4 | 0 | 420
| Design engrg. & analysis | [11 empty] | 360 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 360
| PDR prep | [7 empty] | 12 |  |  |  | 12 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 24
| Disposition PDR chits | [11 empty] | 16 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 16
| FDR prep | [7 empty] | 16 |  |  |  | 16 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 32
| Prepare SOW/RFQ | [11 empty] | 12 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 12
| Disposition FDR chits | [7 empty] | 32 |  |  |  | 24 |  |  | Prior experience on similar work - See Note below | 4 | 0 | 56
| Subtotal Title II Design | [7 empty] | 480 |  |  |  | 440 | [5 empty] | 920
TITLE III DESIGN
Vendor Oversight, Inspection | [12 empty] | 20 |  |  | Engineering judgement based on prior experience - See Note below. | 2 | 0 | 20
Disposition of deviation requests and non-conformances | [12 empty] | 16 |  |  | Engineering judgement based on prior experience - See Note below. | 2 | 0 | 16
Coordination of Procurement Actions | [12 empty] | 8 |  |  | Engineering judgement based on prior experience - See Note below. | 2 | 0 | 8
Subtotal Title III Design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 |  |  |  | 44
NOTE: Estimates are based on verbal and written budgetary quotes from vendors, in-house shop estimates, current catalogue prices where available, and previous experience which includes designing similar magnets, neutral beams, diagnostics, structures, and supports for the following machines - PLT, PDX, S1, MRX, CNT, and TFTR.
[17 empty] | Category | Amount (Hrs) | % of ETC
CATEGORIZATION CODES:
[13 empty] | 1 - National Standards |  |  |  | 1 |  | 0%
[13 empty] | 2 - Engineering Judgement/Experience |  |  |  | 2 | 44 | 4.564%
[13 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  |  |  | 3 |  | 0%
[13 empty] | 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  |  |  | 4 | 920 | 95.44%
[13 empty] | 5 - Prototype Data/Test Results |  |  |  | 5 |  | 0%
[13 empty] | 6 - Catelogue Price/Vendor Quote |  |  |  | 6 |  | 0%
[13 empty] | 7 - Placed Contracts |  |  |  | 7 |  | 0%
[13 empty] | 8 - Actual experience for NCSX Work |  |  |  | 8 |  | 0%
[13 empty] | 9 - Other |  |  |  | 9 |  | 0%
[16 empty] | Totals |  | 964 | 100%

## Table II - M&S
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Materials and Subcontracts (M&S) |  |  |  |  | Basis of Estimate
Description: | [5 empty] | Category | Amount ($) | Amount (Hrs)
The base support structure is the main gravity load carrying structure (~250,000lbs) for the entire machine. It must provide the gravity load path from the machine and distribute these loads to the test cel floor. It must also be capable of withstanding horizontal seismic accelerations of 0.171g and vertical accelerations of 0.108g.
Purchased parts: | (ft.) | lbs./ft. | $/lb. (or per pkg.) | cost
4 - W12 x 50 x 24' - 316L stainless steel (LW) | 96 | 50 | 9.2 | 44160 | Verbal quote StainlessStructurals - recent (-confirmed 1/08) - $/lb | 6 | 44160
4 - W8 x 35 x 24' - 316L stainless steel (LW) | 96 | 35 | 9.2 | 30912 | Verbal quote StainlessStructurals - recent (-confirmed 1/08) - $/lb | 6 | 30912
4 - W12 x 50 x 24' - 316L stainless steel (LW) | 96 | 50 | 9.2 | 44160 | Verbal quote StainlessStructurals - recent (-confirmed 1/08) - $/lb | 6 | 44160
5 - 4" x 4" x 3/8" thk. Angle sections - 316L | 120 | 9.2 | 9.2 | 10156.8 | Verbal quote StainlessStructurals - recent (-confirmed 1/08) - $/lb | 6 | 10156.8
3/4" - 316L plate 36" x 48" base hub plate | 4 | 95 | 7.5 | 2850 | Quote , metal suppliers online | 6 | 2850
3/4" - 316L plate 36" x 48" top & bottom base column bases | 4 | 95 | 7.5 | 2850 | Quote , metal suppliers online | 6 | 2850
Weld rod & roto-bores |  |  |  | 3000 | PPPL Shop estimate - adjusted by WBS Manager- filler rod 316L + Mn (Stellalloy) | 2 | 3000
12 - Inconel 718 hex bolts 1-8 x 2.5" @ $55 ea. |  |  |  | 660 | Quote B&G fabricators | 6 | 660
12 - Inconel 718 hex nuts 1-8 @ $38 ea. |  |  |  | 456 | Quote B&G fabricators | 6 | 456
24 - 316 SS flat washers 1.03" ID @$4.26 ea. |  |  |  | 102.24 | Catalog item McMaster-Carr (current online cat. 1/08) | 6 | 102.24
1 x 9" 316ss Hilti concrete anchors - 4 packs (Part#97799A730) |  | 231.8 | 24 | 5563.2 | Catalog item McMaster-Carr (current online cat. 1/08) | 6 | 5563.2
24 Heater elements with thermostat controllers Cat.#3654K22 |  | 95.25 | 24 | 2286 | Catalog item McMaster-Carr (current online cat. 1/08) | 6 | 2286
Total Materials |  |  |  | 147156.24 |  |  | 147156.24
EMTB
Labor - PPPL: | hrs.
Welding (4hrs @ 48 places) | 192 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager | 2 |  | 192
Welding (4hrs @ 24 places) | 96 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager | 2 |  | 96
Cut & Drill plates | 75 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager | 2 |  | 75
| 363 | [6 empty] | 363
[6 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
[5 empty] | 1 - National Standards | 1 | 0 | 0 | 0% | 0%
[5 empty] | 2 - Engineering Judgement/Experience | 2 | 3000 | 363 | 2.039% | 100%
[5 empty] | 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) | 3 | 0 | 0 | 0% | 0%
[5 empty] | 4 - Previous PPPL/ORNL Experience (e.g., TFTR, NSTX, PLT, etc.) | 4 | 0 | 0 | 0% | 0%
[5 empty] | 5 - Prototype Data/Test Results | 5 | 0 | 0 | 0% | 0%
[5 empty] | 6 - Catalog Price/Vendor Quote | 6 | 144156.24 | 0 | 97.96% | 0%
[5 empty] | 7 - Placed Contracts | 7 | 0 | 0 | 0% | 0%
[5 empty] | 8 - Actualexperience for NCSX Work | 8 | 0 | 0 | 0% | 0%
[5 empty] | 9 - Other | 9 | 0 | 0 | 0% | 0%
[5 empty] | TOTALS |  | 147156.24 | 363 | 100% | 100%

## Table III - FabAssy & Instl
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
In-house Fabrication and Assembly and Installation
Included in Table II

## Table IV - Conting & Risk
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Uncertainty of the Estimate
|  | High | Medium | Low | Comments/Other Considerations
Job 1702 |  |  |  |  | -10% - +15%
| Design Maturity |  | X |  |  | Design requirements still not finalized.
| Design Complexity |  |  | X |  | Standard parts and components
Job 1752 |  |  |  |  | -10% - +15%
| Design Maturity |  | X |  |  | Design requirements still not finalized.
| Design Complexity |  |  | X |  | Standard parts and components
Residual Risks
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1702 | NONE
1752 | NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
PPPL Engineering/Tech Shop Estimate | Metal Suppliers Internet Quote
B&G Quote