## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 21
WBS Title: Gas Fueling System
Job Number: 2101
Job Title: Fueling System
Job Manager: Bill Blanchard
Description:
The MIE project scope encompasses a remotely controlled and monitored fueling system consisting of three gas injection assemblies, three gas delivery systems , a pumpout system and associated gauging. Each gas injection assembly (GIA) will consist of a fill valve, interface valve and a piezoelectric pulse valve that will be operated by a valve driver controlled by the NCSX computer system. Each GIA will have a maximum fueling rate greater than 50 T-l/s.
Schedule:
See Attached
Approvals:
____________________________________________________
Job Manager
____________________________________________________
Responsible Line Manager
____________________________________________________
Project Manager
_____________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 21
WBS Title: Gas Fueling System
Job Number: 2101
Job Title: Fueling System
Job Manager: Bill Blanchard
Description:
The proposed fueling system will be remotely controlled and monitored and consist of three gas injection assemblies, three gas delivery systems , a pumpout system and associated gauging. Each gas injection assembly (GIA) will consists of a fill valve, interface valve and a piezoelectric pulse valve that will be operated by a valve driver controlled by the NCSX computer system. Each GIA will have a maximum fueling rate greater than 50 T-l/s.
|  | $ | Hours
Task ID |  | M&S | EMEM | EMSM | EMSB | EMTB | EASB | EEEM | EESM | EESB | EETB | Basis of Estimate | Category | Amount ($) | Amount (Hrs)
Title I and II Design | [11 empty] | See Note (1) below
Preliminary Design / Management / Admin
| Engr Work Planning & Design | Hours EMEM: 48 |  | 4 | 0 | 48
| Design Gas handling Hardware | Hours EMSB: 96 |  | 4 | 0 | 96
| Design PLC Controls | Hours EEEM: 112 |  | 4 | 0 | 112
| Drafting Support | Hours EASB: 24 |  | 4 | 0 | 24
Final Design / Management / Admin
| Engr Work Planning & Design | Hours EMEM: 88 |  | 4 | 0 | 88
| Design Gas handling Hardware | Hours EMSB: 48 |  | 4 | 0 | 48
| Design PLC Controls | Hours EEEM: 448 |  | 4 | 0 | 448
| Drafting Support (Electrical) | Hours EASB: 144 |  | 4 | 0 | 144
| Drafting Support (Mechanical) | Hours EASB: 68 |  | 4 | 0 | 68
Subtotal Title I & II Design |  |  | 136 | 0 | 144 | 0 | 236 | 560 |  | 0 | 0 | Subtotal |  | 0 | 1076
Title III | [11 empty] | See Notes (2) below
| Engr Work Planning & Design | Hours EMEM: 40 |  | 4 | 0 | 40
| Fabricate & Install Hardware | Hours EMSB: 120; Hours EMTB: 240 |  | 4 | 0 | 360
| Fabricate & Install Hardware (Electrical) | Hours EMTB: 288 |  | 4 | 0 | 288
| Install PLC Controls | Hours EEEM: 192 |  | 4 | 0 | 192
| Integrated System Testing | Hours EMEM: 40; Hours EEEM: 80 |  | 4 | 0 | 120
| Materials and Supplies | $ M&S: 38000 | See Note (3) below | 4 | 38000 | 0
Subtotal Title III |  | 38000 | 80 | 0 | 120 | 528 | 0 | 272 |  | 0 | 0 | Subtotal |  | 38000 | 1000
[12 empty] | Totals |  | 38000 | 2076
Note:
(1) Title I & II: The fueling system estimate is based on prior experience on similar systems (e.g., NSTX) and input from experienced engineers/personnel familiar with specific parts of this project. Includes overall design and oversight activities, some P&ID drawings, weld drawings, fabrication drawings, and two reviews (PDR & FDR).
(2) Title III: This effort includes procurement, fabrication/welding/assembly, installation, oversight, leak checking of the subsystems, procedures, refurbishment of legacy equipment as required and initial operation and testing. Estimate based up input from cognizant individuals with experience on previous similar system installation on other machines.
(3) M&S based upon prior experience on similar systems and uses standard off-the-shelf components.
[13 empty] | Category | Amount ($) | Amount (Hrs) | % of ETC ($) | % of ETC (Hrs)
CATEGORIZATION CODES:
|  | Hours EEEM: 1 - National Standards |  | 1 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 2 - Engineering Judgement/Experience |  | 2 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 3 - Estimates/Data from External Sources (e.g., W7X, ATF, etc.) |  | 3 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 4 - Previous PPPL/ORNL Experieince (e.g., TFTR, NSTX, PLT, etc.) |  | 4 | 38000 | 2076 | 100% | 100%
|  | Hours EEEM: 5 - Prototype Data/Test Results |  | 5 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 6 - Catelogue Price/Vendor Quote |  | 6 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 7 - Placed Contracts |  | 7 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 8 - Actual experience for NCSX Work |  | 8 | 0 | 0 | 0% | 0%
|  | Hours EEEM: 9 - Other |  | 9 | 0 | 0 | 0% | 0%
[12 empty] | Totals |  | 38000 | 2076 | 100% | 100%

## Table II - M&S
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | There have been no design reviews therefore the design is not fixed.
-15%/+25%
| Design Complexity |  |  | X |  | Anticipated to only require standard components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is responsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikely (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)