## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 823
WBS Title: Design Integration
Job Number: 8203
Job Title: Design Integration
Job Manager: Tom Brown
Description:
Responsibilities include: • Configuration development and integration support for all design and construction activities. Participating in design reviews. • Administering the CAD database of project models and drawings. Reviewing and promoting CAD models and drawings. Establishing Intralink procedures and privileges. • Providing support to the metrology and dimensional control efforts by analyzing metrology data in conjunction with CAD models of the parts and assemblies
Schedule: | See Attachment
Approvals:
________________________________________________________
Job Manager
________________________________________________________
Responsible Line Manager
________________________________________________________
Project Manager
_______________________________________________________
Engineering Department Head

## Table I - Dsn Labor
WBS Number: 823
WBS Title: Design Integration
Job Number: 8203
Job Title: Design Integration
Job Manager: Tom Brown
Design Intergration Functions for Each Station Includes:
Configuration Development - This effort is consistant with the necessary configuration development and integration support for all design and construction activities. The design support covers design activities to update drawings per shop generated mark-ups.
CAD Adminstration - This LOE is consistent with project experiences associated with the drawing review/Intralink administration process and appropriate through 1st Plasma.
Major Activities by Year:
FY2008 - Design Integration, including (1) Service routing within the cryostat & test cell (2) Facility updated & integration within the device core (3 Cryostat design review and integration update, and (4) General integration activities
FY2008 - Stations 2 & 3 & Balance of Plan (Assembly Oversight)
FY2009 - Stations 3 & 5 & Balance of Plant (Assembly Oversight)
FY2010 - Stations 5 & 6 & Balance of Plant (Assembly Oversight)
FY2011 - Station 6 & Balance of Plant (Aswembly Oversight)
FY2012 - Stations Balance of Plant & Integrated CAD Models (Assembly Oversight)
|  | Name | Labor | Activity | FY2008 (FTEs) | FY2009 (FTEs) | FY2010 (FTEs) | FY2011 (FTEs) | FY2012 (FTEs) | TOTALS (FTEs)
|  | Brown | EAEM | Design Integ. | 0.1854 |  |  |  |  | 0.1854
|  | Jones | EADM | Design Integ. | 0.04635 |  |  |  |  | 0.04635
|  | Upcavage | EADM | Design Integ. | 0.32445 |  |  |  |  | 0.32445
|  | Subtotal Job 8203 - Design Integration |  |  | 0.5562 | 0 | 0 | 0 | 0 | 0.5562
|  | Brown | EAEM | Assy Oversight | 0.2 | 0.7 | 0.7 | 0.7 | 0.5 | 2.8
|  | Smith | EAEM | Assy Oversight | 0 | 0.4 | 0.4 | 0.4 | 0 | 1.2
|  | Avarsala | EAEM | Assy Oversight | 0 | 0.4 | 0.4 | 0 | 0 | 0.8
|  | Jones | EADM | Assy Oversight | 0.1 | 0.1 | 0 | 0 | 0 | 0.2
|  | Morris | EADM | Assy Oversight | 0 | 0.8 | 0.8 | 0.6 | 0.5 | 2.7
|  | Upcavage | EADM | Assy Oversight | 0.3 | 0 | 0 | 0 | 0 | 0.3
|  | Subtotal Job 8203 - Assembly Oversight |  |  | 0.6 | 2.4 | 2.3 | 1.7 | 1 | 8
|  | TOTAL JOB 8203 |  |  | 1.1562 | 2.4 | 2.3 | 1.7 | 1 | 8.5562
CD-4

## Table II - M&S
WBS Number: 823
WBS Title: Design Integration
Job Number: 8203
Job Title: Design Integration
Job Manager: Tom Brown
Description: | None
Why do all of these formulas refer back to B87 => seems like it should progress with coil

## Table III Fab & Assy
WBS Number: 823
WBS Title: Design Integration
Job Number: 8203
Job Title: Design Integration
Job Manager: Tom Brown
Fabrication and Assembly | None

## Table IV - Conting & Risk
WBS Number: 823
WBS Title: Design Integration
Job Number: 8203
Job Title: Design Integration
Job Manager: Tom Brown
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X
-15%/+25%
| Design Complexity |  | X
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
8203 | Loss or prolonged unavailability of certain key personnel (Brown) from the project could substantially impact the schedule. |  |  |  | VU | Mark Smith and Srinivas Avasarala has been budgeted along with two designers to provide support to Tom Brown in Design Integration during peak demands and pick up the slack for Brown if he became unavailable. | Estimated impact is <0.5 months on the critical path. No impact on FPA cost because impacted personnel would be assigned to other activities. | 0 | 0 | 0 | 0.5 | RR#19b | Risk retired on RR - Delete???
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as loaded costs
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
+