## Fab Project
WBS 161 LN2 Distribution System Inside Cryostat | [10 empty] | 17 |  | Duration of activity per fiscal year (weeks)
Labor
| Activity Title |  | Manhours | FY2003 $$ | Labor Type | Start Date Month/Yr | End Date Month/Yr | Comments |  |  |  | duration (weeks) | 2002-10-01 | 2003-10-01 | 2004-10-01 | 2005-10-01 | 2006-10-01 | 2007-10-01 | 2008-10-01
Preliminary Design (Title I)
|  | ( 33% of design schedule) | 0 |  | EAEM | 2005-12-05 | 2006-01-16 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | 33.3333 | 33.33% | of design is preliminary design
|  |  | 0 |  | EADM | 2005-12-05 | 2006-01-16 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 272 |  | ORNL Eng | 2005-12-05 | 2006-01-16 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2005-12-05 | 2006-01-16 | Composite of ORNL Physics / scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2005-12-05 | 2006-01-16 | PPPL Physics/scientific |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Final Design (Title II)
|  | ( 67% of design schedule) | 0 |  | EAEM | 2006-01-16 | 2006-04-10 | PPPL Engineer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0 |  | 66.6667 | 66.67% | of design schedule is final design
|  |  | 0 |  | EADM | 2006-01-16 | 2006-04-10 | PPPL Designer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 544 |  | ORNL Eng | 2006-01-16 | 2006-04-10 | Composite of ORNL Engineer / Designer |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 0 |  | ORNL Phys. | 2006-01-16 | 2006-04-10 | Composite of ORNL Physicist |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
|  |  | 0 |  | PPPL Phys. | 2006-01-16 | 2006-04-10 | PPPL Physics/scientific |  |  |  | 12 | 0 | 0 | 0 | 12 | 0 | 0
Lab R&D labor
|  |  | #REF! |  | EAEM | 2005-12-05 | 2006-01-16 | PPPL Engineer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | #REF! |  | EADM | 2005-12-05 | 2006-01-16 | PPPL Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | #REF! |  | ORNL Eng | 2005-12-05 | 2006-01-16 | Composite of ORNL Engineer / Designer |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | #REF! |  | EASM | 2005-12-05 | 2006-01-16 | PPPL monthly support |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
|  |  | #REF! |  | EMTB | 2005-12-05 | 2006-01-16 | PPPL Technician |  |  |  | 6 | 0 | 0 | 0 | 6 | 0 | 0
Lab Fab/Assembly/Installation (Title III)
|  |  | 87.6 |  | EAEM | 2006-04-10 | 2007-01-01 | PPPL Engineer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 0 |  | EADM | 2006-04-10 | 2007-01-01 | PPPL Designer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 88.4 |  | ORNL Eng | 2006-04-10 | 2007-01-01 | Composite of ORNL Engineer / Designer |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 123 |  | EASM | 2006-04-10 | 2007-01-01 | PPPL monthly support |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
|  |  | 492 |  | EMTB | 2006-04-10 | 2007-01-01 | PPPL Technician |  |  |  | 38 | 0 | 0 | 0 | 24.8571 | 13.1429 | 0
Labor
Manhours per fiscal year by labor category
Level of Effort |  |  |  | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
| PPPL Engineer |  | EAEM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 153 | per hour
| PPPL Designer |  | EADM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 100 | per hour
| Composite of ORNL Engineer / Designer |  | ORNL Eng | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 130 | per hour
| PPPL monthly support |  | EASM | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 100 | per hour
| PPPL Technician |  | EMTB | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 73 | per hour
| Composite of ORNL Physics / scientific |  | ORNL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 160 | per hour
| PPPL Physics/scientific |  | PPPL Phy | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 141 | per hour
[12 empty] | #REF! | #REF! | PPPL
[12 empty] | #REF! | #REF! | ORNL
M&S Costs
| Activity Title |  |  |  |  | Comment
Procured Hardware/Material
|  | tubing, manifolds, headers |  | 58612.3718
|  | Profit |  | 0 |  | included in hardware estimate
|  | total, procured hdwe/matl. |  | 58612.3718 |  | w/o G&A
| Purchased Design Services |  |  | 0 |  | no purchased services anticipated
| Procured Installation/Assembly Costs |  |  | 0 |  | All installation and assembly costs are included in WBS 7
Other Costs
| Activity Title |  |  | FY2003 $$ |  | Comment
| Travel |  |  | 0 |  | no trips are anticipated for this WBS
Summary Costs
| Activity Title |  | Manhours | FY2003 $$ |  | Comment
Labor
| PPPL Effort |  | #REF! | #REF! |  | Assumed rates: |  | EASM | 100 $/hr
| ORNL effort |  | #REF! | #REF! |  | EAEM | 153 $/hr | EMTB | 73 $/hr
|  | subtotal, labor | #REF! | #REF! |  | EADM | 100 $/hr | PPPL Phys | 141 $/hr
[6 empty] | ORNL Eng | 130 $/hr | ORNL Phys | 160 $/hr
M&S, Other
| Manufacturing Development (R&D) |  |  | 0
| Procured Hardware/Material |  |  | 58612.3718
| Purchased Design Services |  |  | 0
| Procured Installation/Assembly Costs |  |  | 0
| Travel |  |  | 0
|  | subtotal, M&S |  | 58612.3718
| G&A |  |  | 14653.0929 |  | 25% | on all purchased materials, subcontracts, travel
| Subtotal without contingency |  |  | #REF!
| Contingency |  |  | #REF! |  | 28% | Overall on this WBS
| Total cost |  |  | #REF!

## Engr
WBS 161 LN2 Distribution System Inside Cryostat
Engineering, Title I, II and III
Description:
This effort covers all Title I, II, and III engineering for the LN2 distribution system inside the cryostat, which includes all the necessary manifolding and connections to interface with the ex-cryostat LN2 supply system. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7. |  |  |  |  | Labor category
[5 empty] | total fraction | EMEM |  | EADM |  | ORNL Eng |  | ORNL Physics |  | PPPL Physics
| multiplier | unit | no. | hours |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Title I, II design
Pro-E models (avg) | 4 | hrs/model | 40 | 160 | 1 | 0 | 0 | 0 | 0 | 1 | 160 | 0 | 0 | 0 | 0
assy dwgs | 8 | hrs/dwg | 11 | 88 | 1 | 0 | 0 | 0 | 0 | 1 | 88 | 0 | 0 | 0 | 0
Detail drawings | 4 | hrs/dwg | 6 | 24 | 1 | 0 | 0 | 0 | 0 | 1 | 24 | 0 | 0 | 0 | 0
installation dwg | 8 | hrs/dwg | 11 | 88 | 1 | 0 | 0 | 0 | 0 | 1 | 88 | 0 | 0 | 0 | 0
cooling schematic | 20 | hrs/dwg | 1 | 20 | 1 | 0 | 0 | 0 | 0 | 1 | 20 | 0 | 0 | 0 | 0
electrical schematic | 0 | hrs/dwg | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
I&C schematic | 20 | hrs/dwg | 1 | 20 | 1 | 0 | 0 | 0 | 0 | 1 | 20 | 0 | 0 | 0 | 0
stress analysis | 40 | hrs/calc | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
thermal analysis | 40 | hrs/calc | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 1 | 40 | 0 | 0 | 0 | 0
special analysis (electromagnetics) | 160 | hrs/calc | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
fab specifications | 160 | hrs/spec | 2 | 320 | 1 | 0.75 | 0 | 0 | 0 | 0.25 | 80 | 0 | 0 | 0 | 0
preliminary and final design reviews | 80 | hrs/rev | 2 | 160 | 1 | 0 | 0 | 0 | 0 | 1 | 160 | 0 | 0 | 0 | 0
meetings/reporting/presentations | 10% | % of tot | 960 | 96 | 1 | 0 | 0 | 0 | 0 | 1 | 96 | 0 | 0 | 0 | 0
subtotal |  |  |  | 1056 |  |  | 0 |  | 0 |  | 816 |  | 0 |  | 0 | 155466.36
16588.812
[5 empty] | total fraction | EMEM |  | EASM |  | EADM |  | ORNL Eng |  |  |  | 172055.172
Title III | [5 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
vendor oversight, inspection | 0 | hrs/wk | 12 | 0 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
Disposition of deviation requests and non-conformances | 1 | hrs/wk | 38 | 38 | 1 | 0.2 | 7.6 | 0 | 0 | 0 | 0 | 0.8 | 30.4
As-built drawings | 2 | hrs/dwg | 29 | 58 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 58
Procurement coordination | [6 empty] | 80
subtotal |  |  |  | 96 |  |  | 87.6 |  | 0 |  | 0 |  | 88.4
Schedule assumptions | start | duration (weeks) | end
Title I Design | 2005-12-05 | 6 | 2006-01-16
Title II Design | 2006-01-16 | 12 | 2006-04-10
Procurement | 2006-04-10 | 12 | 2006-07-03
In-house fab / sub-assy | 2006-07-03 | 0 | 2006-07-03
Installation / final assembly | 2006-07-03 | 26 | 2007-01-01
Notes and worksheets
LN2 distribution system
| total | vessel torus, | port extensions | NBI duct | manifolds | headers
Pro-E models | 33 | 10 | 13 | 2 | 6 | 2 | models for each type of tube, manifold, and header
assy dwgs | 5 | 1 | 1 | 1 | 1 | 1
Detail drawings | 6 | 0 | 0 | 0 | 4 | 2 | drawings of each manifold and header
installation dwg | 4 | 1 | 1 | 1 | 1 |  | on drawing per type of part
cooling schematic | 0
electrical schematic | 0
I&C schematic | 0
stress analysis | 1
thermal analysis | 1 | 1 |  |  |  |  | one analysis for all cooling lines
special analysis | 0
procurement specifications | 1 | [5 empty] | one procurement spec for the tubing, piping and fittings
preliminary and final design reviews | 1 | [5 empty] | one review for all the plumbing
meetings/reporting/presentations | 15%
flow control system
total
Pro-E models | 6 |  | elements added to piping system
assy dwgs | 6
Detail drawings | 0
installation dwg | 6
cooling schematic | 1 |  | block flow diagram
electrical schematic | 1 |  | actuator electrical schematic, if applicable
I&C schematic | 0
stress analysis | 0
thermal analysis | 0
special analysis | 0
procurement specifications | 1 |  | one procurement specification for all flow control elements
preliminary and final design reviews | 0 |  | reviews covered under WBS 191
meetings/reporting/presentations | 10%
Local I&C
Pro-E models | 1
assy dwgs | 0
Detail drawings | 0
installation dwg | 1
cooling schematic | 0
electrical schematic | 0
I&C schematic | 1
stress analysis | 0
thermal analysis | 0
special analysis | 0
procurement specifications | 0
preliminary and final design reviews | 1
meetings/reporting/presentations | 10%
1. LN2 distribution system instrumentation consists of a single thermocouple placed on each return header inside cryostat
2. There will be a single supply and return header for each field period which supplies the TF coils and the upper and lower PF coils
3. Reviews and procurement specs for T/C are covered as part of WBS 171
Formulas:
multiplier = [no.]-[unit]*7
no. = [multiplier, row below]

## M&S
WBS 161 LN2 Distribution System Inside Cryostat
Materials and Subcontracts (M&S)
Description:
This effort covers procurement of materials for the LN2 distribution system by fixed price subcontract.
Assumptions:
outside engr rate = | 120 | $ per hour
outside fab rate = | 60 | $ per hour
outside inspection/technician rate = | 80 | $ per hour
Purchased parts:
coolant line pigtails from coils to manifolds | 18480 | see notes below
Insulating Jumper hoses | 4320
Manifolds for cooling lines | 6612.3718
valves | 6000 | see notes below
other hardware | 23200
Thermocouples | 0 | included in job 1408 for the modular coil fabrication
subtotal, purchased parts | 58612.3718
Worksheet:
coolant line pigtails from coils to manifolds
Average length of pigtail | 3 | ft
| Total | TF | Modular | PF1 | PF2 | PF3 | PF4 | PF5 | PF6
No. of coils | 48 | 18 | 18 | 2 | 2 | 2 | 2 | 2 | 2
circuits per coil at header |  | 1 | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
total circuits | 168 | 18 | 144 | 1 | 1 | 1 | 1 | 1 | 1
Total number of pigtails | 336 | supply and return per circuit
Cost per pigtail, with fittings | 55
Total cost of pigtails | 18480
Number of MC coil insulating break jumper hoses and end fittings | 144
cost per jumper | 30
total cost of jumpers | 4320
total cost of all lines
Manifolds for cooling lines
Assume 1 pair of 1.5 inch manifolds for each field period, one above and one below the midplane inside the PF5 coil
Each manifold will have 1/3 of the required cooling connections plus 25% spare
The manifolds will connect via vertical pipes to the supply system below the cryostat
avg toroidal perimeter of field period | 15.8041 | ft
avg vertical height of connection lines | 9 | ft
no of header pairs | 3
cost of tubing | 15 | per foot, 316 SSt
cost per field period | 2232.3718
total number of coolant connections, all headers | 840
cost per connection | 5
cost of nipples for all manifolds | 4200
welding consumables | 200 | total
no. connections for supply piping | 6 | 2 connections per manifold
cost per connection | 30
cost for supply piping connections | 180
total matl cost for manifolds | 6612.3718
Flow control hardware
no. of circuits | 24
Valves | 250 | ea
no.of valves | 24 | one for each pf and tf coil circuit at manifold
Total cost for valves | 6000
flow control orifice at manifold | 50 | ea
no of orifice units | 144 | one for each MC coil circuit
Total cost for orifice | 7200
Other misc items | 10000
total hardware | 23200
Thermocouples
Number | 0 | ea
Thermocouple cost each, with connector | 68 | $ each
total for thermocouples | 0

## Fab_assy
WBS 161 LN2 Distribution System Inside Cryostat
In-house Fabrication and Assembly
Description:
This effort covers all the assembly time to put the cooling line tracing on the exterior of the vessel and ports, and to build the coolant manifolds | [5 empty] | Labor category
[6 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
| multiplier | unit | no. | hours |  |  | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
Fab operations summary
| 615 | hrs/lot | 1 | 615 |  | 1 | 0 | 0 | 0.2 | 123 | 0.8 | 492 | 0 | 0
| 0 | hrs/line | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hrs / coil | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
subtotal | 615 |  |  | 615 |  |  |  | 0 |  | 123 |  | 492 |  | 0
[6 empty] | total fraction | EAEM |  | EASM, EMSM |  | EMTB |  | EADM
Assembly operations summary | [6 empty] | fract. | hrs | fract. | hrs | fract. | hrs | fract. | hrs
| 0 | hr/lot | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/lot | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hr/coil | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | hours | 1 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
subtotal | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0
Worksheets
coolant line pigtails from coils to manifolds
Average length of pigtail | 3 | ft
| Total | TF | Modular | PF1 | PF2 | PF3 | PF4 | PF5 | PF6
No. of coils | 38 | 18 | 18 | 2 | 2 | 2 | 2 | 2 | 2
circuits per coil at header |  | 1 | 8 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
total circuits | 168 | 18 | 144 | 1 | 1 | 1 | 1 | 1 | 1
Total number of pigtails | 336 | supply and return per circuit
Manifolds for cooling lines
Assume 1 pair of 1.5 inch manifolds for each field period, one above and one below the midplane inside the PF5 coil
Each manifold will have 1/3 of the required cooling connections plus 25% spare
The manifolds will connect via vertical pipes to the supply system below the cryostat
avg toroidal perimeter of field period | 15.8041 | ft
avg vertical height of connection lines | 9 | ft
no of header pairs | 3
cost of tubing | 15 | per foot, 316 SSt
cost per field period | 2232.3718
total number of coolant connections, all headers | 840
hours to weld each connection | 0.5 | hr per connection
shifts to form manifold tube | 0.5 | per manifold pair
crew size for forming | 2
hours to cut vertical pipes | 2 | hrs per pipe
hours to weld vertical pipes to header | 2 | hrs per pipe
total shifts for manifolds | 61.5
tech hours for manifolds | 492 | hours
technical oversight, inspection | 123 | hrs
total hours for manifolds | 615 | hrs

## Installation
WBS 161 LN2 Distribution System Inside Cryostat
Installation
This element is not part of the WBS 1 scope of work
will be included in the machine assembly
notes: | get name of federal QA outfit from Rod Templon's email