## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 134
WBS Title: Conventional Coils I&C
Job Number: 1355
Job Title: Conventional Coils I&C
Job Manager: Mike Kalish
Description:
This WBS element provides the manufacturing design and fabrication of the local I&C components required by the WBS elements under Conventional Coils (WBS 13). Local I&C requirements will be determined in the design of these WBS elements, and may include strain gages, RTDs, and voltage taps.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $72,143
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 134
WBS Title: Conventional Coils I&C
Job Number: 1355
Job Title: Conventional Coils I&C
Job Manager: Mike Kalish
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [15 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
In Table II

## Table II - M&S
WBS Number: 134
WBS Title: Conventional Coils I&C
Job Number: 1355
Job Title: Conventional Coils I&C
Job Manager: Mike Kalish
Materials and Subcontracts (M&S)
Description: | FY07$K |  |  |  |  | HOURS
| 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | Basis of Estimate
Procrurement & Fabrication
I&C Design and Installation
Procure Thermocouples TF | 4320 | [10 empty] | 2 |  |  |  | $40 per TE 6 per coil - based on Omega Catalogue
Procure Thermocouples PF4 | 480 | [10 empty] | 2 |  |  |  | $40 per TE 6 per coil - based on Omega Catalogue
Procure Thermocouples PF5 | 480 | [10 empty] | 2 |  |  |  | $40 per TE 6 per coil - based on Omega Catalogue
Procure Thermocouples PF6 | 480 | [10 empty] | 2 |  |  |  | $40 per TE 6 per coil - based on Omega Catalogue
Procure Thermocouples PF1a | 240 | [10 empty] | 2 |  |  |  | $40 per TE3 per coil - based on Omega Catalogue
Thermcocouple Wire | 4000 | [10 empty] | 2 |  |  |  | 500ft per TE - based on Omega Catalogue
Design and Review | [11 empty] | 60 |  |  |  | Design-based on previous experience on similar projects
Installation Procedures - Review and Approval | [11 empty] | 20 |  |  |  | Installation Procedures + Review and Approval - based on previous experience (e.g., NSTX)
Design Review | [11 empty] | 8 |  |  |  | Design Review - based on previous exprerience
I*+&C Title III Engineering
Support of Installation | [10 empty] | 396 | 40 |  |  |  | Two hours per TE - basis on previous experience (e.g., NSTX)
Subtotal Job 1355 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 140 | 0 | 0 | 0

## Table III - FabAssy & Instl
WBS Number: 134
WBS Title: Conventional Coils I&C
Job Number: 1355
Job Title: Conventional Coils I&C
Job Manager: Mike Kalish
In-house Fabrication and Assembly and Installation
Description: Incl in M&S Table II
Worksheets

## Table IV - Conting & Risk
WBS Number: 134
WBS Title: Conventional Coils I&C
Job Number: 1355
Job Title: Conventional Coils I&C
Job Manager: Mike Kalish
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Cionsiderations
| Design Maturity |  | X |  |  | Requirements in early development, but relatively simple design based on previous experience.
-10%/+15%
| Design Comlexity |  |  | X |  | Simple off-the-shelf thermocouples attached to coil
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
Risk |  |  |  |  | Likelihood of Occurring | Mitigation Strategies | Consequence if Occurs
[7 empty] | Cost | Schedule
NONE