## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Description:
This WBS element consists of the manufacturing design, procurement, and fabrication of the TF conductor and assembly of the TF winding packs including interface elements for connections to power and cooling supply at the coils.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $965,391
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [15 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
In Table II Estimate

## Table II - M&S
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Materials and Subcontracts (M&S)
Basis of Estimate
Description: | FY07$K |  |  |  |  | HOURS
| 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
Procrurement & Fabrication
Title III /Engrg | 5 | [10 empty] | 656 | [10 empty] | Based on 50% Oversight / coverage of fabrication of coils at Everson-Tesla until all coils are in house. This is the level of coverage that has been required up until this point
In House Inspection | [10 empty] | 68 | 48 | [10 empty] | Cover inspection for 18 coils, two engs - three days for the first coil, .5 day for one technician for subsequent coils
Support of Assembly operations and metrology | [11 empty] | 84.4 | [10 empty] | .25% coverage during 35days FP#1 assembly of TFs + 10% coverage for 18days of FP#2 TF assembly
Contract Costs Remaining |  | 965
Additional Materials as Required | 8 | [21 empty] | Actual purchases ($4K for glass insulation) => expect one more time
TOTAL | 13 | 965 | [8 empty] | 68 | 788.4

## Table III - FabAssy & Instl
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
In-house Fabrication and Assembly and Installation
Description: Incl in M&S Table II

## Table IV - Conting & Risk
WBS Number: 131
WBS Title: Toroidal Field coils
Job Number: 1361
Job Title: TF Coil Fabrication
Job Manager: Mike Kalish
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Cionsiderations
| Design Maturity | X |  |  |  | Coils in fabrication - design is complete
-10%/+15%
| Design Complexity |  | X |  |  | While conventional cross-section with solid Cu, some potential difficulty in maintain precise geometry and tolerances
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil |  |  |  | VU | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)