## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1416
Job Title: Type A/B Coil Final Design
Job Manager:David Williamson
Description:
Job 1416 consists of the effort to complete the final design for the Type A and Type B Modular Coils.
Schedule:
Cost: (loaded in as-spent dollars):
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Description:
Title I and II Engineering for design of the modular coil interfaces. Title III for these components is included in Job 1802.
FY07$K
Task ID | Description | Comments | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | EMEM | EMTB | EAEM | EASB | Basis of Estimate
Clamp Hardware Modifications | [7 empty] | 50 |  |  |  |  | Added 40 ORNL hours based on experience to date.
1416-204.1 | Modify Type-B clamps for stud attaqchments
Blanket Thermal Insulation | [7 empty] | 60 |  |  |  |  | Added 40 ORNL hours based on experience to date.
1416-304 | Revise assembly drawings | [6 empty] | 30 |  |  | 10 |  | Added 20 ORNL hours based on experience to date.
1416-305 | Review and approve insulation concept | [6 empty] | 40 |  |  | 8 |  | Added 40 ORNL hours based on experience to date.
1416-33198 | Report results
FY07 Rebaseline
ecp53rbx04 | [7 empty] | 8
Top Level Assembly Drawings
1416-501 | Complete models/drawings of coolant line routing | [6 empty] | 0 |  |  |  |  | Complete
1416-502 | Check layout of flux loop terminations and revise | [6 empty] | 0 |  |  |  |  | Complete
1416-503 | Complete models/drawings of power cable connections | [6 empty] | 120 |  |  |  |  | Work remaining - modify leads per analysis
1416-504 | Complete models/drawings of protective covers | [6 empty] | 120 |  |  |  |  | Work remaining - assume covers are different for reach coil
1416-505 | Drawing callouts for interface hdw (prelim model) | [6 empty] | 0 |  |  |  |  | Task deleted
1416-507 | Update, review, %& approve coil assembly spec | [6 empty] | 80
1416-508 | Complete drawing rev to leades, terminals asm (ECN) | [6 empty] | 80 |  |  |  |  | Work remaining - drawing in checking cycle
1416-506 | Check and promote top-level models/drawings | [6 empty] | 80 |  |  |  |  | Added 20 ORNL hours based on experience to date.
Analysis and coseout documentation
1416-601 | Prepare EM and structural analysis of loads |  | 60 |  |  |  |  | 80 |  |  | 192 |  | ORNL Contract w/ Myatt
1416-602 | Design memo for KF structueal analysis | [6 empty] | 96 |  |  |  |  | Added 16 ORNL hours based on experience to date.
1416-603 | Update, review and approve FEMEC | [6 empty] | 60
1416-604 | Finalize drdaft documents - materials, eddy currents, etc. | [6 empty] | 40
1416-605 | Prepare Type ABC coselout FDR | [6 empty] | 72 |  |  |  |  | Added 32 ORNL hours based on experience to date.
1416-606 | Resolve FDR comments | [6 empty] | 72 |  |  |  |  | Added 32 ORNL hours based on experience to date.
Type C Design Closeout
1403-47C | Perform cool-down/warmup analysis | [9 empty] | 40
TOTALS |  |  | 60 |  |  |  |  | 1088 | 0 | 0 | 250 | 0

## Table II - M&S
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Materials and Supplies |  | Resp Org. | Basis of Estimate
Included in Table I

## Table III Fab & Assy
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
NONE

## Table IV - Conting & Risk
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X
[5 empty] | -20% to +40% |  | Major issue is continuous iteration of design
| Design Complexity |  | X |  |  |  | Major uncertainty is C-C access for bolting at machine assembly
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)