## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 31
WBS Title: Magnetic Diagnostic Systems
Job Number: 3101
Job Title: Magnetic Diagnostic Systems
Job Manager: Brent Stratton
Description:
This effort covers the design, procurement of materials and parts, and fabrication and installation of the magnetic diagnostics for the NCSX machine. The magnetic sensors include diamagnetic loops, flux loops, saddle loops, Rogowski coils and B-coils that will provide signals to measure the magnetic flux change in the many geometries necessary to determine the magnetic field geometry using an equilibrium reconstruction code.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $293,460
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 31
WBS Title: Magnetic Diagnostic Systems
Job Number: 3101
Job Title: Magnetic Diagnostic Systems
Job Manager: Brent Stratton
Description:
Included in Table II

## Table II - M&S
WBS Number: 31
WBS Title: Magnetic Diagnostic Systems
Job Number: 3101
Job Title: Magnetic Diagnostic Systems
Job Manager: Brent Stratton
Materials and Subcontracts (M&S) | [8 empty] | Basis of Estimate
| Description | Material |  | Labor
|  | Type | Cost $
|  |  | (Note 1) | EMEM | EMSM | EMTB | EADM | EEEM
New Scope Cost for Exiting T/Cs and Heater Power Leads at Port 12
5 | Remaining Design |  |  | 136 |  |  |  |  | Design about 50% complete.
Distribution of wires to 2.75 ConFlat
System Diagram
| Research Amphenol Receptical | [7 empty] | Will modify Commercial Bud Box based upon review with tech
Impact of Cryostat
Evaluate magnetic permeability issue
Extend Heater Power Leads
5a | Support of Procurements under Job 1204 |  |  | 40 |  |  |  |  | Vendor contacts, reqn, etc. - Labik - support of efforts by Dudek.
5b | Engineering Support Field/Fab Activities (Title III) |  |  | 25
6 | Peer Review |  |  | 30 |  |  |  |  | Based on previous experience on similar jobs
Based on previous experience on similar jobs
7 | Design Drafting | [5 empty] | 30 |  | Based on previous experience on similar jobs
Issue new drawing
8 | Install and Connect T/C Feedthroughs | [7 empty] | Included in Job 1810
9 | Install Extra Length Wire and Connect ( Solder ) Power Feedthroughs | [7 empty] | Included in Job 1810
10 | Machine Twelve 2.75 CF Blanks |  |  |  | 36 |  |  |  | Based on previous experience on similar jobs
11 | Rubber Seal
12 | Machine 6 Commercial Aluminum Boxes |  |  |  | 36 |  |  |  | Based on previous experience on similar jobs
NOTE: M&S in Job 1204 |  | TOTAL | 28700 | 231 | 72 | 0 | 30 | 0
| Description | Material |  | Labor
|  | Type | Cost $ | EMEM | EMSM | EMTB | EADM | EEEM
Existing + Added Cost for Co Wound Loops for Modular Coils
| Design Protective Boxes | [7 empty] | Work Completed
| Drawings | [7 empty] | Work Completed
| Purchase SS Sheet | [7 empty] | Work Completed
| Purchase PTFE Tubing and Fiber Glass Sheath | [7 empty] | Work Completed
| Prototype | [7 empty] | Work Completed
| Formal Issue of Drawings Rev 0 | [7 empty] | Work Completed
| Form 18 Protective Boxes | [7 empty] | Work Completed
| Weld end plates | [7 empty] | Work Completed
| Drawing Change , add extra slots | [7 empty] | Work Completed
| Formal Issue of Drawings Rev 1 | [7 empty] | Work Completed
| Engineering Support Field/Fab Activities (Title III) | [7 empty] | Work Completed
| Fab MC co-wound loops | [7 empty] | Work Completed
|  | TOTAL | 0 | 0 | 0 | 0 | 0 | 0
| Description | Material |  | Labor
|  | Type | Cost $ | EMEM | EMSM | EMTB | EADM | EEEM
Existing + Added Cost for Co Wound Loops for 18 TF and 6 PF and 2 SolenoidCoils
| Design Protective Boxes |  |  | 110 |  |  |  |  | TF Complete
| Drawings |  |  | 60 |  |  |  |  | TF Complete.
| Purchase SS Sheet |  | 870 | 1 |  |  |  |  | Partial.
| Purchase Heat Shrink Tubing, 20 @ 100 ft |  | 2000 | 6 |  |  |  |  | 12 ordered in Dec 06 => 6 of 12 Received.
| Purchase additional CoAxial cable 3500 ft |  | 4550 | 2 |  |  |  |  | Placed order for 1900 ft
| Prototype |  |  |  | 12 |  |  |  | TF Complete.
| Formal Issue of Drawings Rev 0 | [5 empty] | 0 |  | Work Completed
| Form 26 Protective Boxes |  |  |  | 102 |  |  |  | 6 TF completed.
| Weld end plates |  |  |  |  | 18 |  |  | 6 TF completed.
| Engineering Support Field/Fab Activities (Title III) |  |  | 36
| Develop Convective Air Furnace |  | 0 |  | 0 |  |  |  | Work Completed
| Fab TF, PF & solenoid co-wound loops |  |  |  | 130 |  |  |  | 9 of 26 completed.
|  | TOTAL | 7420 | 215 | 244 | 18 | 0 | 0
| Description | Material |  | Labor
|  | Type | Cost $ | EMEM | EMSM | EMTB | EADM | EEEM
Existing + Added Cost for Flux Loop Junction Boxes and 20 Spacer Flux Loops and 6 Protective Boxes
| Purchase Material - 2.75 ConFlat Flanges |  | 900 | 2 |  |  |  |  | Based on previous experience
| Purchase Material - AL and SS Plate |  | 820 |  |  | 2 |  |  | Based on previous experience
| Purchase Material - 316 SS flat head screws |  | 400 |  |  | 2 |  |  | Based on previous experience
| Purchase Material - Circuit Boards RF Filtered w/TB |  | 3200 |  |  |  |  | 32 | Based on previous experience
| Install 24 JB ( 410 cables) Act # | [7 empty] | Included in Job 1810
| Terminate 24 JB ( 410 cables ) | [7 empty] | Included in Job 1810
| Anneal 2.75 Conflat Flanges |  |  |  | 12 |  |  |  | Based on previous experience
| Engineering Support Field/Fab Activities (Title III) |  |  | 120 |  |  |  |  | Based on previous experience
| Purchase 2000 ft 0.059 CoAx-Spacer |  | 3500 | 2 |  |  |  |  | Based on previous experience
| AutoCAD Drawings of Field Runs/Tag#/Port Assignments |  |  | 112 |  |  |  |  | Based on previous experience
| Water Jet Machine Cu Templates |  | 240 |  |  | 8 |  |  | Based on previous experience
| Install 20 Templates | [7 empty] | Included in Job 1810
| Install Spacer Flux Loops | [7 empty] | Included in Job 1810
| Twist leads | [7 empty] | Included in Job 1810
| Design Protect Box & Prepare Dwg |  |  | 22 |  |  |  |  | Based on previous experience
| Fab 6 Prot Boxes |  | 200 |  | 24 |  |  |  | Based on previous experience
| Install Prot Boxes | [7 empty] | Included in Job 1810
| Prepare Drawing of Spacer Loops | [5 empty] | 60 |  | Based on previous experience
NOTE: M&S in Job 1204 |  | TOTAL | 9260 | 258 | 36 | 12 | 60 | 32
| Description | Material |  | Labor
|  | Type | Cost $ | EMEM | EMSM | EMTB | EADM | EEEM
Existing + Added Cost forHigh Temperature Rogowski Coil
| CDR + Peer Reviews |  |  | 60
| Preliminary Design |  |  | 60
| Fabricate Prototype |  | 50 |  |  | 20
| Test Prototype |  | 50 |  | 24
| Prepare for and Conduct PDR |  |  | 20
| Final Design |  |  | 60
| Purchase Spec for Winding Mandrel |  |  | 40
| Trip to Vendor |  |  | 16 | 16
| Sub contract Winding 3 Mandrels |  | 15000
| Prepare for and Conduct FDR |  |  | 10
| Formal Issue of Drawings | [5 empty] | 4
| Purchase Material - ARI SS Coax Cable 0.032 inch |  | 2650 | 2
| Purchase Material - SS Flex and Bendable Smooth Tube |  | 300 | 2
| Purchase Material - Nextel Tape |  | 300 | 1
| Purchase Material - Inconel Bar |  | 1200 | 2
| Fabricate coil clamps - 36 ( 3 Field Periods 12 ea) |  |  |  |  | 90
| Fabricate ends |  |  | 4 | 32
| Fixture to Straighten Smooth SS Tube |  | 30 | 4 |  | 32
| Install Wound Coil into Protective SS Flex |  | 50 | [5 empty] | Included in Job 1810
| Install 3 Rogowski Coils | [7 empty] | Included in Job 1810
| Weld 36 coil clamps | [7 empty] | Included in Job 1810
| Engineering Support Field/Fab Activities (Title III) |  |  | 60
|  | TOTAL | 19630 | 281 | 72 | 142 | 4 | 0
| Description | Material |  | Labor
|  | Type | Cost $ | EMEM | EMSM | EMTB | EADM | EEEM
Added Cost for Voltage Loops and Protective Boxes
| Drawings- Engineering Sketch of Routing |  |  | 20 |  |  |  |  | Based on previous experience
| Drawings- Layout | [5 empty] | 16 |  | Based on previous experience
| Formal Release of Layout Drawing | [5 empty] | 4 |  | Based on previous experience
| Protective Box Design |  |  | 6 |  |  |  |  | Based on previous experience
| Protective Box Drawing |  |  | 20 |  |  |  |  | Based on previous experience
| Install Voltage 12 Loops on VV | [7 empty] | Included in Job 1810
| Twisted leads to Prot. Boxes | [7 empty] | Included in Job 1810
| Fab 3 Protective Boxes | 316 SS by 0.048 Thk | 120 |  |  | 12 |  |  | Based on previous experience
| Install 3 Protect. Boxes | [7 empty] | Included in Job 1810
| Engineering Support Field/Fab Activities (Title III) |  |  | 6 |  |  |  |  | Based on previous experience
| Purchsae additional 900 ft cable | 0.059 OD Inconel CoAx | 1600 | 2
|  | TOTAL | 1720 | 54 | 0 | 12 | 20 | 0
| Total |  | 28770 | 550 | 316 | 172 | 24 | 0

## Table III - FabAssy & Instl
WBS Number: 31
WBS Title: Magnetic Diagnostic Systems
Job Number: 3101
Job Title: Magnetic Diagnostic Systems
Job Manager: Brent Stratton
In-house Fabrication and Assembly and Installation
Included in Table II

## Table IV - Conting & Risk
WBS Number: 31
WBS Title: Magnetic Diagnostic Systems
Job Number: 3101
Job Title: Magnetic Diagnostic Systems
Job Manager: Brent Stratton
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Exception is Rogowski => Medium - design not finalized
-5%/+10%
| Design Complexity |  |  | X |  | Exception is Rogowski => Medium - design not finalized
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
High temperature Rogowski Loop damaged during installation resulting in loss of toroidal current measurement capability |  |  |  | 5% |  | Triple redundancy | 3 Installed - only one required. | +$0K | +$0K | +0.00 | +0.00
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)