## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 44
WBS Title: Control and Protection Systems
Job Number: 4401
Job Title: Control and Protection Systems
Job Manager: Raki Ramkrishnan
Description:
This WBS element consists of the following subsystems: (1) Electrical Interlock Systems - This WBS element consists of the effort to design, fabricate, and install an electrical interlock system for NCSXd which ensures the proper configuration of the power system in accordance with the commanded state from the NCSX control room and access control systems, and which provides coordinated fast fault response of the power supplies when faults are detected. (2) Kirk Key Interlock System - This WBS element consists of the effort to design, procure, fabricate, and install kirk key interlocks for NCSX. (3) Real Time Control Systems - This WBS element consists of the effort to develop the specification of the hardware requirements and software algorithms to be provided by WBS 5 (Central I&C) for the real time digital feedback control of the power supply system, including the high-speed digital input and output links. (4) Instrumentaion Systems - This WBS element consists of the effort to design, specify, procure, install, and implement current and voltage measurements for the NCSX coil systems. (5) Coil Protection Systems.
Schedule:
ETC Cost: (loaded in as-spent dollars from 5/1/07): $1,065,690
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 44
WBS Title: Control and Protection Systems
Job Number: 4401
Job Title: Control and Protection Systems
Job Manager: Raki Ramkrishnan
Description: This is a LOE effort for design intergration, interface definition, and oversight of diagnostic systems design, fabrication, and installation
|  | K$ |  | Labor Hours |  |  |  |  | Basis of Estimate
Task Description | Activity | M&S | Travel | EASM | ECEM | EEEM | EESM | EETB | (See Notes on Basis of Estimate Below)
WBS 441 Electrical Interlocks
Design Interlock sys | 441-095 |  |  | 40 |  | 80 | 80 |  |  | 200
Install Interlock sys | 441-097 |  |  |  |  | 80 | 80 |  | Needed prior to coil energization | 160
PLC Specification | 441-100 |  |  |  |  | 24 | 56 |  |  | 80
Prep Block diagrams | 441-105 |  |  |  |  | 24 | 80 |  |  | 104
PLC CWD's & Cabling | 441-110 |  |  |  |  | 16 | 240 | 320 |  | 576
deliver PLC | 441-115 | 70 | [7 empty] | 0
Program PLC Logic | 441-120 |  |  |  |  | 64 | 240 |  | Needed prior to coil energization | 304
Program Control pages | 441-125 |  |  |  | 40 | 32 | 120 |  | Needed prior to coil energization | 192
Pre-commissioning tests | 441-130 | 1 |  |  |  | 40 | 120 |  | Needed prior to coil energization | 160
Install I/O Cabling | 441-135 | 38 |  | 160 |  | 40 | 80 | 400 | Needed prior to coil energization | 680
WBS 442 Kirk Key Interlocks
Kirk Keys-Dsn | 442-1-2 |  |  | 80 |  | 40 | 40 |  |  | 160
Kirk Keys-Procure | 442-1-4 | 10 |  |  |  | 8 | 24 |  |  | 32
Kirk Keys-Install | 442-1-6 | 15 |  |  |  | 16 | 24 | 80 |  | 120
Kirk Keys-Commission | 442-1-8 |  |  |  |  | 16 | 20 | 20 | Needed prior to coil energization | 56
WBS 443 Real Time Control Systems | [8 empty] | Needed prior to coil energization
Develop Control Algorithms-Dsn | 443-1-2 |  |  |  |  | 80 |  |  | Needed prior to coil energization | 80
WBS 444 Instrument Systems
DC Potential Transducers (DCPTs)-Dsn | 444-2-2 |  |  | 40 |  | 24 |  |  |  | 64
DC Potential Transducers (DCPTs)-Procure | 444-2-4 | 6 |  | 16 | [5 empty] | 16
DC Potential Transducers (DCPTs)-Install | 444-2-6 |  |  | 16 |  | 16 | 24 | 160 |  | 216
DC Potential Transducers (DCPTs)-Commission | 444-2-8 |  |  |  |  | 24 | 24 | 60 | Needed prior to coil energization | 108
DC Shunts-Dsn | 444-3-2 |  |  | 32 |  | 24 |  |  |  | 56
DC Shunts-Procure**N/R** | 444-3-4 | [8 empty] | 0
DC Shunts-Install**N/R** | 444-3-6 | [8 empty] | 0
DC Shunts-Commission**N/R** | 444-3-8 | [8 empty] | 0
Signal Conditioning & Cabling-Dsn | 444-4-2 |  |  | 24 |  | 480 |  |  |  | 504
Signal Conditioning & Cabling-Procure | 444-4-4 | 12 |  |  |  | 16 |  |  |  | 16
Signal Conditioning & Cabling-Install | 444-4-6 |  |  |  |  | 24 |  | 280 |  | 304
Signal Conditioning & Cabling-Commission | 444-4-8 |  |  |  |  | 48 | 40 | 40 | Needed prior to coil energization | 128
WBS 445 Coil Protection Systems
Ground Fault Protection-Dsn | 445-1-2 |  |  | 40 |  | 160 | 16 |  |  | 216
Ground Fault Protection-Procure | 445-1-4 | 18 |  |  |  | 16 |  |  |  | 16
Ground Fault Protection-Install | 445-1-6 |  |  | 8 |  | 40 | 48 | 120 |  | 216
Ground Fault Protection-Commission | 445-1-8 |  |  |  |  | 24 | 24 | 32 | Needed prior to coil energization | 80
Overload Protect-Write spec and approve | 445-2-105 |  |  |  |  | 80 |  |  |  | 80
Overload Protect-Design | 445-2-110 |  |  | 32 |  | 96 | 32 |  |  | 160
Overload Protect-Fabr 4 chassis | 445-2-115 |  |  |  |  | 48 | 120 |  |  | 168
Overload Protect-Test 4 units | 445-2-120 |  |  |  |  | 32 | 32 |  |  | 64
Overload Protect-Install & Rack wiring | 445-2-125 |  |  |  |  | 48 | 77 |  |  | 125
Overload Protect-Write & perform ISTP | 445-2-130 |  |  |  |  | 32 | 32 |  | Needed prior to coil energization | 64
Overload Protect-Documentation | 445-2-135 |  |  | 64 |  | 32 |  |  | Needed prior to coil energization | 96
Overload Protection&cabling design,procure instl | 445-2-140 | 13 |  | 80 |  | 96 | 45 | 96 | Needed prior to coil energization | 317
Totals |  | 183 | 0 | 632 | 40 | 1920 | 1718 | 1608
Notes on the Basis of Estimate
(1) Design and Fabrication/Installation
Estimate based on estensive experience of engineer performing similar tasks at PPPL and EBASCO - e.g. recent experience on NSTX. This is basically a job modifying existing PPPL systems and re-installing for NCSX. Design and engineering estimates developed based on assessements of the number of drawings needed (new or modified), the effort to reconfigure existing designs, interfaces with other systems, supervision of on-site contractors, and all necessary re-activation and pre-operational testing needed.
(2) M&S
M&S estimated based on similar recent procurements and needed interfaces with installation contractors - this will be Davis-Bacon covered, except tor those activities within the Test Cell.

## Table II - M&S
WBS Number: 44
WBS Title: Control and Protection Systems
Job Number: 4401
Job Title: Control and Protection Systems
Job Manager: Raki Ramkrishnan
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 44
WBS Title: Control and Protection Systems
Job Number: 4401
Job Title: Control and Protection Systems
Job Manager: Raki Ramkrishnan
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 44
WBS Title: Control and Protection Systems
Job Number: 4401
Job Title: Control and Protection Systems
Job Manager: Raki Ramkrishnan
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Requirements still evolving, but similar to other projects' designs
-10%/+15%
| Design Complexity |  |  | X |  | Known technology from previous PPPL devices
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)