## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 45
WBS Title: Power Systems Design Integration
Job Number: 4501
Job Title: Power Systems Design Integration
Job Manager: Raki Ramkrishnan
Description:
This WBS element consists of the electrical system engineering and design/drafting, which includes the design and analysis of the overall electrical system, its documentation, and the conduct of design reviews. It also includes the T effort to ensure overall project coordination of electrical systems by providing electrical systems support to other systems, including diagnostics, which provides the engineering, design/drafting, and installation of diagnostic cabling. It also includes the the effort to conduct all systems-related preoperational testing.
Schedule:
ETC Cost: (loaded in as-spent dollars from 5/1/07): $684,768
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 45
WBS Title: Power Systems Design Integration
Job Number: 4501
Job Title: Power Systems Design Integration
Job Manager: Raki Ramkrishnan
Description: This is a LOE effort for design intergration, interface definition, and oversight of diagnostic systems design, fabrication, and installation
|  | K$ |  | Labor Hours |  |  |  |  | Basis of Estimate
Task Description | Activity | M&S | Travel | EASM | ECEM | EEEM | EESM | EETB | (See Notes Below on Basis of Estimate)
WBS 451 - Systems Design and Interfaces
Develop SRD | 451-0-2 |  |  |  |  | 40 |  |  | Needed before FDR on WBS4 | 40
Calculations-Dsn | 451-1-2 |  |  | 8 |  | 40 |  |  | Needed before FDR on WBS4 | 48
PDR Prep Power system -Dsn | 451-2-2 |  |  | 128 |  | 96 |  |  | Needeed before power Cable installation | 224
FDR C-Site | 451-2-2.1 |  |  | 120 |  | 80 |  |  | Needeed before power Cable installation | 200
PDR Power system -Dsn | 451-2-3 | [7 empty] | Needeed before power Cable installation | 0
Dwgs,asbuilts -Elect Dsn | 451-3-2 |  |  | 320 |  | 320 |  |  | Needed before coil energization | 640
FDR AC auxiliaries & grounding-Dsn | 451-4-2 |  |  | 40 |  | 40 |  |  | Needed before coil energization | 80
FDR C-Site -Cabling | 451-6-2 |  |  | 120 |  | 80 |  |  | Needeed before power Cable installation | 200
WBS 452 - Electrical Systems Support
Diagnostics AC Power Distr-Dsn | 452-1-2 |  |  | 160 |  | 80 |  |  |  | 240
Diagnostics AC Power Distr-Procure | 452-1-4 | 1 |  | 8 | [5 empty] | 8
Diagnostics AC Power Distr-Install | 452-1-6 |  |  | 80 |  | 24 | 80 | 640 |  | 824
Diagnostics AC Power Distr-Commission | 452-1-8 |  |  |  |  | 24 | 80 | 160 | Needed before first plasma | 264
Diagnostics sensor cabling-Dsn | 452-2-2 |  |  | 160 |  | 24 |  |  |  | 184
Diagnostics sensor cabling-Procure | 452-2-4 | 2 | [7 empty] | 0
Diagnostics sensor cabling-Install | 452-2-6 |  |  |  |  | 16 | 32 | 160 |  | 208
Diagnostics sensor cabling-Commission | 452-2-8 |  |  |  |  | 8 | 16 | 32 | Needed before first plasma | 56
WBS 453 - System Testing (PTP's)
New Procedures | 453-1-2 |  |  | 160 |  | 24 |  |  | Needed before FDR on WBS4 | 184
Preop Testing-Procure test equipt | 453-1-3 | 20 | [6 empty] | Needed before coil energization | 0
TF Coil Test | 453-1-4 | 1 |  | 8 |  | 32 | 40 | 54 | Needed before first plasma | 134
PF5 Coil Test | 453-1-5 | 1 |  | 8 |  | 32 | 40 | 54 | Needed before first plasma | 134
Trim Coil Test (per coil) | 453-1-6 | 0.5 |  | 8 |  | 32 | 40 | 54 | Needed before first plasma | 134
Testing PTPs, ISTPs | 453-1-7 | 10 |  | 160 |  | 240 | 320 | 376 | Needed before first plasma | 1096
Totals |  | 35.5 | 0 | 1488 | 0 | 1232 | 648 | 1530
Notes on the Basis of Estimate
(1) Design and Fabrication/Installation
Estimate based on estensive experience of engineer performing similar tasks at PPPL and EBASCO - e.g. recent experience on NSTX. This is basically a job modifying existing PPPL systems and re-installing for NCSX. Design and engineering estimates developed based on assessements of the number of drawings needed (new or modified), the effort to reconfigure existing designs, interfaces with other systems, supervision of on-site contractors, and all necessary re-activation and pre-operational testing needed.
(2) M&S
M&S estimated based on similar recent procurements and needed interfaces with installation contractors - this will be Davis-Bacon covered, except tor those activities within the Test Cell.

## Table II - M&S
WBS Number: 45
WBS Title: Power Systems Design Integration
Job Number: 4501
Job Title: Power Systems Design Integration
Job Manager: Raki Ramkrishnan
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 45
WBS Title: Power Systems Design Integration
Job Number: 4501
Job Title: Power Systems Design Integration
Job Manager: Raki Ramkrishnan
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 45
WBS Title: Power Systems Design Integration
Job Number: 4501
Job Title: Power Systems Design Integration
Job Manager: Raki Ramkrishnan
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Do not anticipate major changes in the design
-5%/+10%
| Design Complexity |  |  | X |  | Known technologies
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)