## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
The Diagnostic Data Acquisition System will provide a data management software structure to catalog and manage experimental results for subsequent retrieval and analysis. The design will use the existing MIT developed MDSplus software for data acquisition, data archiving and display. Individual diagnostic local control and data acquisition hardware will be designed with standard PC architecture or in Compact PCI chassis.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $165,118
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [14 empty] | Basis of Estimate
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate
Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience of experieince on other similar networking installation projects.
53-10 | Preliminary Design | [15 empty] | 40
53-20 | Final Design | [15 empty] | 80
53-30 | Procurement | 17 | 3 |  | 2 | [11 empty] | 20
53-40 | Installation | [17 empty] | 40
53-50 | MDSplus Installation | [15 empty] | 80
53-60 | MDSplus Programming - Tree Design | [15 empty] | 80
53-70 | MDSplus Programming - Shot Sync | [15 empty] | 80
53-80 | MDSplus Programming - Dispatcher | [15 empty] | 160
53-90 | MDSplus Programming - Acquisition | [15 empty] | 80
53-110 | Programming - Misc. | [15 empty] | 160
53-120 | Test | [15 empty] | 40 |  | 40
| Subtotal Job 5301 | 17 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | 80
| M&S Details: | K$ | Basis of M&S Estimate
| Linux MDSplus Server | 3 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| SAN - disk space (500 GB) | 6 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| misc. | 3 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| PC appl. TBD | 10 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| Total M&S | 22

## Table II - M&S
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Weldments & Assy H/w
Materials and Subcontracts (M&S) |  | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 53
WBS Title: Data Acquistion & Facility Computing Systems
Job Number: 5301
Job Title: Data Acquistion & Facility Computing Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although PDR, some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Duplication of NSTX architecture
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)