## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Description:
The real time software is divided into two functions, the power supply real time control system (PSRTC) and the plasma control system (PCS). The PSRTC will calculate the alpha control signal required by the power conversion firing generators. The basic code of the NSTX PSRTC will be modified for use on NCSX. The NCSX PCS will share that developed for NSTX with a new real time data acquisition system in the NCSX test cell.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $129,109
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [14 empty] | Basis of Estimate
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate
Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience of experieince on other similar networking installation projects.
55-10 | FCPC - Preliminary Design | [15 empty] | 40
55-20 | FCPC -Final Design | [15 empty] | 80
55-30 | FCPC - Procurement | 6 | 6 |  | 1 | [11 empty] | 20
55-40 | LabVIEW Programming | [15 empty] | 120
55-50 | FCPC PLC Integration - EPICS Prog. | [15 empty] | 40
55-50 | FCPC - Installation | [15 empty] | 40 |  | 40
55-60 | FCPC -Test | [15 empty] | 40 |  | 20
55-70 | GISRTC - Preliminary Design | [15 empty] | 40
55-80 | GISRTC -Final Design | [15 empty] | 20
55-90 | GISRTC - Procurement | 5 | 5.5 |  | 1 | [11 empty] | 20
55-100 | LabVIEW Programming | [15 empty] | 120
55-110 | GISRTC - Installation | [10 empty] | 24 |  |  |  |  | 20 |  | 20
55-120 | GISRTC -Test | [15 empty] | 20
| Subtotal Job 5501 | 11 | 11.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 620 | 0 | 80
| M&S Details: | K$ | Basis of M&S Estimate
| PC/LabVIEW control of C-Site Power Supplies | 12 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| PC/LabVIEW control of Gas Injection | 10.5 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| misc. | 2 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| Total M&S | 24.5

## Table II - M&S
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 55
WBS Title: Real Time Plasma and Power Supply Control Systems
Job Number: 5501
Job Title: Real Time Plasma and Power Supply Control Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although PDR, some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Duplication of NSTX architecture
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)