## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 56
WBS Title: Central Safety Interlock Systems
Job Number: 5601
Job Title: Central Safety Interlock Systems
Job Manager: Paul Sichta
Description:
The Central Safety Interlock System will provide system-wide coordination of personnel and hardware interlocks. Its primary man machine interface will be EPICS. The Central Safety Interlock System will be a fail-safe, hybrid system. Mechanical components and hardwired devices will provide primary protective functions. Each NCSX high-energy subsystem will interface with the Central Safety Interlock System. An access control system will be incorporated to grant access to the Test Cell for only authorized/trained personnel. UPS and Standby power will be used for critical components.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $223,144
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 56
WBS Title: Central Safety Interlock Systems
Job Number: 5601
Job Title: Central Safety Interlock Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [14 empty] | Basis of Estimate
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35TRVL | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate
We need to know what you are buying, the basis of that estimate, & the basis of your labor hours
56-10 | Requirements, Codes&Standards | [15 empty] | 40
56-20 | Preliminary Design | [15 empty] | 40
56-30 | PLC Training |  | 2 |  |  | 2 | [10 empty] | 80
56-40 | Final Design | [15 empty] | 140
56-40 | Procurement | 20 | 12 |  | 8 | [11 empty] | 40
56-50 | PLC Programming | [15 empty] | 120
56-60 | Installation | [8 empty] | 480 |  | 240 |  |  |  |  | 60 |  | 80
56-70 | Test | [15 empty] | 80 |  | 40
| Subtotal Job 5601 | 20 | 14 | 0 | 8 | 2 | 0 | 0 | 0 | 480 | 0 | 240 | 0 | 0 | 0 | 0 | 600 | 0 | 120

## Table II - M&S
WBS Number: 56
WBS Title: Central Safety Interlock Systems
Job Number: 5601
Job Title: Central Safety Interlock Systems
Job Manager: Paul Sichta
Weldments & Assy H/w
Materials and Subcontracts (M&S) |  | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 56
WBS Title: Central Safety Interlock Systems
Job Number: 5601
Job Title: Central Safety Interlock Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 56
WBS Title: Central Safety Interlock Systems
Job Number: 5601
Job Title: Central Safety Interlock Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  |  | X |  | First-of-a-Kind at PPPL, although certainly in main stream of industy
-15%/+25%
| Design Complexity |  |  | X |  | Very preliminary M&S estimates off web - need price quote from vendors
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)