## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Description:
This WBS element includes all the effort required to add cooling loops to the existing C-site (CS) and HVAC Water Systems as required for NCSX subsystems.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $49,628
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
|  | FY07$K |  |  |  |  | HOURS
|  | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 7780.468
TASK DESCRIPTION |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | Basis of Estimae
Design
| Final Design (Field Run) | [7 empty] | 20 |  |  |  |  | 80 |  |  |  |  | Based on engineering judgement from experience on NSTX
Procrurement & Fabrication/Installation
| Procurement lead time and award | [7 empty] | 20
| 3/4" Cu Pipe x 50 ft | 250 | [9 empty] | 8 | [6 empty] | Based on Means
| Solder Joints ( 25 ) | [10 empty] | 16 | [6 empty] | Based on Means
| Valves | 100 | [9 empty] | 8 | [6 empty] | Based on Means
| Elbows | 10 | [9 empty] | 8 | [6 empty] | Based on Means
| Tees | 10 | [9 empty] | 8 | [6 empty] | Based on Means
| New Instrumentation | 1500 | [6 empty] | 20 |  |  | 80 | [6 empty] | Based on Means
| Backflow preventer | 500 | [6 empty] | 8 |  |  | 16 | [6 empty] | Based on Means
| Heat Exchanger | 500 | [6 empty] | 8 |  |  | 16 | [6 empty] | Based on Means
| Pump | 100 | [6 empty] | 8 |  |  | 8
PTP Testing
| Test | [7 empty] | 8 |  |  | 40
| TOTALS | 2970 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 208 | 0 | 80 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Materials and Subcontracts (M&S) | Basis of Estimate
M&S in Table I

## Table III - FabAssy & Instl
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
In-house Fabrication and Assembly and Installation
Fabrication & Installation in Table I

## Table IV - Conting & Risk
WBS Number: 61
WBS Title: Water Cooling Systems
Job Number: 6101
Job Title: Water Cooling Systems
Job Manager: Larry Dudek
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Design not complicated, but still in a conceptual stage.
-10%/15%
| Design Complexity |  |  | X |  | Standard piping -- off-the-shelf components
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)