## Sheet1
WBS Number: 185 |  |  |  |  | color code
WBS Title: Assembly of Field Perids |  |  |  |  | parallel tasks
Job Numbes: 1802, 1810, and 1815
Job Title: FPA Oversight & support (1802) |  |  |  |  | Metrology Crew
Job Title: FPA Operations - Stations 1, 2, & 3 (1810)
Job Title: FPA Operations - Station 5 (1815)
Job Manager: Mike Viola
Fabrication and Assembly
Assumptions:
Assumes 5 day workweek 1 shift no overtime
Parallel ops for sta 5 (2 fixtures available)
Parallel ops for sta 5 (2 fixtures available)
Only 1 fixture for station 3 only one shift
Parallel ops for sta 2
| Reflects rls plan rev 6 |  | K$
| TASK DESCRIPTION | Work days | 41MS | 35TRVL | ORNL EM/DSN | SHTB | EMEM | EESM | EMTB | CREW | met crew | Basis of Estimate
Estimate based on recent NCSX FPA activities and the amount of oversight and supervision that is required, adjusted by recognition of complexity of work remaining.
Job 1802
Oversight & Supervision
| Metrology Engineering Supervision FY07 raftopolous 50% | [5 empty] | 0.5 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY08 raftopolous 50% | [5 empty] | 0.5 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY09 raftopolous 50% | [5 empty] | 0.5 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY07 Viola 100% | [5 empty] | 1 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY08 Viola 100% | [5 empty] | 1 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY09 Viola 100% | [5 empty] | 1 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Title III field period assembly FY07 ORNL suppor cole,goranson,williamson 65% total | [10 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole see attached backup from Cole
| Title III field period assembly FY0\8 ORNL suppor cole,goranson,williamson 65% total | [10 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole see attached backup from Cole
| Title III field period assembly FY07 & FY08 Support @ 40hr/month + travel (assume 10 months) - PJ Fogarty |  |  | 25 | 400 | [6 empty] | ??? Is this in addition to Cole's TitleIII?
| HP Coverage in the TFTR TC LOE FY07@.75 fte |  |  |  |  | 0.75 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY08 @.75 fte |  |  |  |  | 0.75 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY09 @.75 fte |  |  |  |  | 0.75 | [5 empty] | this is LOE thru stat3 only
Station 2-Modular Coil Sub- Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures written & approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 2
| Pre-job brief completed | 1
Station 2 operational
Station 3-Modular Coil to VVSA Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures approved | 10
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 6
| Pre-job brief completed | 6
| Station 3 operational | 1
| Fixtures installed | 6
Station 5-Final Field Period Assembly
Sequence Plan (Brown) - Covered in Job 1803
Metrology Plan (Elllis) - Covered in Job 8202
| Procedures approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 7
| Pre-job brief completed | 7
| Station 5 operational | 1
Job: 1802 - FP Assy Oversight&Support-VIOLA Total |  |  | 0 | 25 | 400 | 2.25 | 4.5 | 0 | 0
Job: 1810 - Field Period Assembly-VIOLA
Station 1: Based on actual VV #1 costs - almost completed.
Station 2: Based on actual VV #1 costs - almost completed.
[12 empty] | Also, it appears that your single shift activity is running parallel resources that are not available. i.e. the trials development crew are the same as the FP crew. Larry and I have requested more techs without success yet. | Based on experience to accomplish similar tasks (e.g., metrology scans/lock-ins, coil trial fitups, gross checks)
[12 empty] | Ron, I spoke with Wayne and he asked that I include reasonable times for the back office support. He also mentioned that Bob Ellis was being shifted 100% to support Tom Brown. | Nose/Bushing related items based on conceptual designs and rough estimates
Assumed nose concept based on application of epoxy & set-up times
Station 3: Setup and Metrology estimates based on conceptual designs tempered with experieince in alignment of multiple components (half field periods and screens proof-of principle tests)
General F.P. Assy support
| LOE Crane support, fixture setupfor TFTR TC. FY07 1.2 fte | [7 empty] | 1.2 |  |  | 2 men 3 day a week .LOE adjust consistent with schedule thru station 5
| LOE Crane support, fixture setupfor TFTR TC. FY08 1.2 fte | [7 empty] | 1.2 |  |  | 2 men 3 day a week .LOE adjust consistent with schedule thru station 5
| LOE Crane support, fixture setupfor TFTR TC. FY09 1.2 fte | [7 empty] | 1.2 |  |  | 2 men 3 day a week .LOE adjust consistent with schedule thru station 5
| LOE Field Supervision for TFTR TC FY07 edwards | [6 empty] | 1 |  |  |  | this is LOE adjust consistent with overall schedule thru station 5
| LOE Field Supervision for TFTR TC FY08 edwards | [6 empty] | 1 |  |  |  | this is LOE adjust consistent with overall schedule thru station 5
| LOE Field Supervision for TFTR TC FY09 edwards | [6 empty] | 1 |  |  |  | this is LOE adjust consistent with overall schedule thru station 5
| LOE Metrology support FY07 1.5 fte engr plus ducco 100% | 181 |  |  |  |  | 1.5 |  | 1 |  |  | this is LOE adjust consistent with overall schedule thru station 5
| LOE Metrology support FY08 1.5 fte engr plus ducco 100% | 362 |  |  |  |  | 1.5 |  | 1 |  |  | this is LOE adjust consistent with overall schedule thru station 5
| LOE Metrology support FY09 1.5 fte engr plus ducco 100% | 181 |  |  |  |  | 1.5 |  | 1 |  |  | this is LOE adjust consistent with overall schedule thru station 5
| Misc M&S FY07 | 181 | 18 | [8 empty] | 3K/month
| Misc M&S FY08 | 362 | 36 | [8 empty] | 3K/month
| Misc M&S FY09 (6 months???tbd) | 181 | 18 | [8 empty] | 3K/month
Station 1-FP #1 VV Prep (hard surface components)
| Layout diagnostic&coolant paths on vessel - Completed | 35
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs for coolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5
| Verify installation of local I&C | 2
| Install cooling/htg lines to vac vsl | 15 | [6 empty] | 300 | 2.5
| Weld cooling/htg risers | 16 | 2 | [5 empty] | 320 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men Experience is 8 tubes per day 128 tubes per VVSA | Delayed due to coil tests
| Verify Instl of H/C lines,headers,manifolds | 5 | [6 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Serial tasks are showing up as parallel on schedule
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [5 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Need to buy high strength nibbler
| Loop termination & verification | 18 | [6 empty] | 360 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [6 empty] | 80 | 2.5
| Final Scan | 4 | [6 empty] | 80 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install heater tape and insulation on removeable ports | 10 | [6 empty] | 200 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #2 VV Prep (hrd surf cmpnts)
| Misc Hardware |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs forcoolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5 | [9 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C - Completed | 2 | [9 empty] | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [6 empty] | 300 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | 100% complete
| Weld cooling/htg risers | 16 | 2 | [5 empty] | 320 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men Experience is 8 tubes per day 128 tubes per VVSA
| Verify Instl of H/C lines,headers,manifolds | 5 | [6 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [5 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [6 empty] | 360 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [6 empty] | 80 | 2.5
| Final Scan | 4 | [6 empty] | 80 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install heater tape and insulation on removeable ports | 10 | [6 empty] | 200 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #3 VV Prep (hrd surf cmpnts)
| Misc Hardware |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12 | [6 empty] | 240 | 2.5 |  | Missing from schedule | 15% complete
| Install heater tape on vertical ports | 7 | [6 empty] | 140 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Not started yet due to coil alignment tests
| Verify installation of heater tapes | 1 | [6 empty] | 20 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Not started yet due to coil alignment tests
| Attach studs for coolant lines | 3 | [6 empty] | 60 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Not started yet due to coil alignment tests
| Wind magnetic diagnostic sensors | 14 | [6 empty] | 280 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men | Not started yet due to coil alignment tests
| Install precision magnetic diagnostic sensors - Completed | 3 | [6 empty] | 60 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Verify installation magnetic diagnostic sensors - Completed | 4 | [6 empty] | 80 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install local I&C (incl thermocouples) | 5 | [6 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [6 empty] | 300 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Weld cooling/htg risers | 16 | 2 | [5 empty] | 320 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men Experience is 8 tubes per day 128 tubes per VVSA
| Verify Instl of H/C lines,headers,manifolds | 5 | [6 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [5 empty] | 100 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [6 empty] | 360 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install Final Internal and External monuments and measure | 4 | [6 empty] | 80 | 2.5
| Final Scan | 4 | [6 empty] | 80 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Install heater tape and insulation on removeable ports | 10 | [6 empty] | 200 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [6 empty] | 40 | 2.5 |  | serial tasks alternating between FPA constant 2.5 men
Station 1-Spool pieces (3) (spacers)
| Attach diagnostics, studs and coolant lines | 17 | [6 empty] | 340 | 2.5
| install Final Internal and External monuments and measure | 2 | [6 empty] | 40 | 2.5
Station 2 Trials
| Trial tensioning test on prototype | 2 | 3 | [5 empty] | 40 | 2.5
| Trial bushing and shim test on prototype | 12 | 2 | [5 empty] | 240 | 2.5
| Perform trial x-y-z alignments on A1-A2. | 7 | 2 | [5 empty] | 140 | 2.5
| Perform developmental trials on A1-A2. | 30 | 2 | [5 empty] | 600 | 2.5
| Alignment mechanisms, metro equipt &positioning | 6 | 40 | [5 empty] | 120 | 2.5
| Procure alignment mechanisms, fiducials, lifting | 20 | 25 | [5 empty] | 400 | 2.5
| Develop procedures for torquing bolts | 4 | [6 empty] | 80 | 2.5
| Development trials for NOSE WELDING | 30 | 70 | [5 empty] | 600 | 2.5 |  | Perform welding trials and procure EWI and Bob Parcells support
| Determine fiducial types&locations | 11 | 2 | [5 empty] | 220 | 2.5
| Procure monuments&related metrology equipment | 15 | 15 | [5 empty] | 300 | 2.5
| Hardware rework (1/2 FTE) | 120 | 10 | [5 empty] | 960 | 1 |  | MISC LOE SUPPORT
Station 2 SETUP
| Misc Hardware |  | 5
| Test out equipt & procedures | 7 | [6 empty] | 140 | 2.5
| Receive drawings and hardware (shims and bolts) | 7 | [6 empty] | 140 | 2.5
3 | Shim sizing / preparations
3.01 | Using flange measurement of the coils, define the A/A and A/B shim thickness. | [10 empty] | Back Office
3.02 | Surface grind a set of metal shims that will be used on the first MCHP article for assembly process qualifications. (for 3 Joints) | 12 | [6 empty] | 240 | 2.5 |  | Actual experience (LED: actual Experience Was 4 days per JOINT)
3.03 | Compress alumina coated shims and sort by thickness the shim set that will be installed on the MCHP. | 6 | [6 empty] | 120 | 2.5 |  | 800 shims not critical path
4 | Pre-Installation Station 2 set-up | [10 empty] | Metrology plan covering Station 2:
4.01 | Install MCHP fixtures and metrology equipment. | [10 empty] | not critical path separate crew in parallel
4.02 | Perform metrology set-up and checks | 5 | [6 empty] | 100 | 2.5 |  | not critical path separate crew in parallel
| Install FIRST Holding 20 deg fixture | 4 | 2 | [5 empty] | 80 | 2.5
| Install SECOND Holding 20 deg fixture | 3 | 2 | [5 empty] | 60 | 2.5 |  |  | Just received - Not done yet
| Install THIRD Holding 20 deg fixture | 6 | 2 | [5 empty] | 120 | 2.5 |  |  | Just received - Not done yet
| Install LAST Holding 20 deg fixture | 3 | 2 | [5 empty] | 60 | 2.5 |  |  | Just received - Not done yet
| Tools&tooling available for FPA operations | 2 | [6 empty] | 40 | 2.5
Station 2 SETUP subtotal |  | 55 | [6 empty] | 1100
Station 2 FIRST ARTICLE FP #1 of 6
1 | MC fit-up pre-check and surface insulation | [10 empty] | Sequence Plan R5
1.01 | Verify that mating MC's of a MCHP will come together without interferences by pre-fitting mating coils. This will include the Type-C coil with its interfacing Period Type-C coil. | 4 | [6 empty] | 80 | 2.5
1.02 | Epoxy paint all close fitting interfacing surfaces. | 3 | [6 empty] | 60 | 2.5
2 | Pre-measurement of MCHP Type A, B and C coils flanges plus interfacing Type-A coil flange | [10 empty] | 2 at a time on the 2 20 degree wedges
2.01 | Set the Type-A coil on the pre-measurement fixture, “B” side flange down. | 1 | [6 empty] | 20 | 2.5 |  | May be done early
2.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
2.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 7 | [8 empty] | 140 | Metrology Staff Budgeted as LOE
2.04 | Measure all of the tooling ball monuments on the winding form. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
2.05 | Scan the “A” flange of the Type-A coil. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
2.06 | Flip the Type-A coil placing the "B" side down and follow steps 2.02 thru 2.04 and scan the "A" side flange. | 5 | [6 empty] | =8*M195*D195 | 2.5
2.07 | Remove Type-A coil from stand and move to holding area. | 1 | [6 empty] | 20 | 2.5
2.08 | Measure Type B "A" flanges | 14 | [6 empty] | 40 | 2.5 |  | Repeats 2.01-2.07
2.11 | Measure Type C "A" flanges | 13 | [6 empty] | 40 | 2.5 |  | Repeats 2.01-2.07
2.14 | Measure Type A-A "A" flange | 13 | [6 empty] | 40 | 2.5 |  | Repeats 2.01-2.07
3 | Shim sizing / preparations | [10 empty] | Sequence Plan R5
3.01 | Using flange measurement of the coils, define the A/A and A/B shim thickness. | [10 empty] | Back Office
3.02 | Surface grind a set of metal shims that will be used on the first MCHP article for assembly process qualifications. | 4 | [6 empty] | 80 | 2.5 |  | Actual experience
5 | Pre-assemble A1-A2 | [7 empty] | 0 | 2.5 |  | Sequence Plan R5
5.01 | Position the Type-A modular coil on the fixture, “B” flange down. Obtain a set of “realigned” fiducial positions. | 2 | [9 empty] | Metrology Staff Budgeted as LOE
5.02 | Align the laser tracker to the conical seats locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE |  |  | 380 | 220 | 600
5.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE |  |  | 480 | 580 | 1060
5.04 | Place the an initial set of metal shims on the coil in the designated locations, identical to those in the A1-A2 fit up test. | 0.5 | [6 empty] | 10 | 2.5
5.05 | Install dial indicators on the modular coil in areas where we expect to see deflection. | 2 | [6 empty] | 40 | 2.5
5.06 | Lower the mating type A modular coil into position. | 1 | [6 empty] | 20 | 2.5
5.07 | Measure the monuments on the bottom coil. Jack areas of the coil as necessary to bring displaced monuments back to within .002” of their original position. | 1 | [6 empty] | 20 | 2.5
5.08 | Using three target points, perform the positioning as was done in the A1-A2 fit up test. | 1 | [6 empty] | 20 | 2.5
5.09 | Install the remaining metal shims install studs, supernuts, and torque to 50% of final value. | 2 | [6 empty] | 40 | 2.5
5.1 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
5.11 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
5.12 | If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
5.13 | Loosen studs to extract Fuji paper. Evaluate shim pressure distribution and make shim adjustments if shim pressure is unacceptable. Re-torque all studs to 50% and recheck alignment. | 1 | [6 empty] | 20 | 2.5
5.14 | Install the A-A locator bushings at two stud locations for use in re-positioning MCHP in Stage 3. | 2 | [6 empty] | 40 | 2.5
5.15 | Remove all studs, nuts, shims etc. Identify shim locations. | 1 | [6 empty] | 20 | 2.5
6 | A-B modular coil assembly | [7 empty] | 0 | 2.5 |  | Sequence Plan R5
6.01 | Place the Type-A coil, “A” flange down, on the 20deg fixture. Obtain a set of “realigned” fiducial positions for the “A” and “B” coils. | 2 | [6 empty] | 40 | 2.5
6.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
6.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
6.04 | Place the an initial set of metal shims on the coil in the designated locations. | 2 | [6 empty] | 40 | 2.5
6.04.1 | Stuff Shim Bag with Fiberglas, Reseal, Place Shim Bag on Wing | 0.25 | [6 empty] | 5 | 2.5 |  | LED: Must place bag before coil assembly
6.05 | Lower the Type-B coil onto the Type-A coil. | 1 | [6 empty] | 20 | 2.5
6.06 | Measure the monuments on the A coil. Jack areas of the coil as necessary to bring displaced monuments back to within .002” of their original position. | 1 | [6 empty] | 20 | 2.5
6.06.1 | Install Dial indicators for X-Y Positioning | 1 | [6 empty] | 20 | 2.5 |  | LED: Missing from sequence
6.07 | Using three target points on the B coil, perform the X-Y positioning of the B coil. | 1 | [6 empty] | 20 | 2.5
6.08 | Install the remaining metal shims with Fuji paper, install studs, supernuts, and torque to 50% of final value. | 2 | [6 empty] | 40 | 2.5
6.09 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
6.1 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
6.11 | If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
6.12 | Loosen all studs, reduce load on flanges and install an equivalent set of alumina coated metal shims. Re-torque all studs to 50%. | 1 | [6 empty] | 20 | 2.5
6.13 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
6.14 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
6.15 | If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
6.16 | One hole at a time, remove the supernut. Using the eccentric gage slid onto the stud define the hole eccentricity. Select bushing and machine to match required eccentricity. Install bushing. Replace nut and tighten back to 50% and recheck alignment. | 1.5 | [6 empty] | 30 | 2.5 |  | LED: Technical Issue space in some areas is insufficient to remove nuts with flanges in position. If there is space duration should be 1.5 days
6.17 | Complete tightening of flange bolts to 100%. | 1 | [6 empty] | 20 | 2.5
6.18 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
6.19 | Scan the “B” flange of Type-B coil | 1 | [6 empty] | 20 | 2.5
6.2 | Using the "B" flange measurement of the Type-B coil and the earlier "A" flange measurement of the Type-C coil, define all B/C flange shim thickness. |  | Why measure Type B earlier if never used | [8 empty] | Back office
7 | (A-B) to C modular coil assembly (MCHP) |  | Change durations to the A-B joint times | [8 empty] | Sequence Plan R5
7.01 | Place the “A/B” assembly, “A” coil down, on the 40deg fixture. Obtain a set of “realigned” fiducial positions. For the “A”, “B”, and “C” coils. | 3 | [6 empty] | 60 | 2.5
7.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
7.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
7.04 | Place the an initial set of metal shims on the coil in the designated locations. | 2 | [6 empty] | 40 | 2.5
7.05 | Lower the Type-C coil onto the Type-B coil. | 1 | [6 empty] | 20 | 2.5
7.06 | Measure the monuments on the A coil to evaluate monument displacements. If movement greater than .002" is observed discuss with back office on how to proceed in bringing displaced monuments back to within .002" of their original position. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
7.07 | Using three target points on the Type-C coil, perform the X-Y positioning of the coil. | 1 | [6 empty] | 20 | 2.5
7.08 | Install the remaining metal shims with Fuji paper, install studs, supernuts, and torque to 50% of final value. | 2 | [6 empty] | 40 | 2.5
7.09 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
7.1 | Measure the tooling balls on all coils. The maximum deviation from the “realigned” points should be .010” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
7.11 | If the above step does not fall within .010" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
7.12 | Loosen all studs, reduce load on flanges and install an equivalent set of alumina coated metal shims. Re-torque all studs to 50%. | 1 | [6 empty] | 20 | 2.5
7.13 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
7.14 | Measure the tooling balls on all coils. The maximum deviation from the “realigned” points should be .010” or less. | 5 | [6 empty] | 100 | 2.5
7.15 | If the above step does not fall within .010" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
7.16 | One hole at a time, remove the supernut. Using the eccentric gage slid onto the stud define the hole eccentricity. Select bushing and machine to match required eccentricity. Install bushing. Replace nut and tighten back to 50% and recheck alignment. | 1.5 | [6 empty] | 30 | 2.5 |  | LED: Increase duraction to 1.5
7.17 | Complete tightening of flange bolts to 100%. | 1 | [6 empty] | 20 | 2.5
11.01 | Install or identify three primary fiducials that will be used in positioning the Period in Station 3. | 1 | [6 empty] | 20 | 2.5
7.18 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .010” or less. Make final metrology measurement of all fiducials. Scan the “B” flange of Type-C coil. Record the results. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
8 | Tack weld inboard welded shims | [10 empty] | Sequence Plan R5
8.01 | Partially tack weld all inboard shims to one flange to keep them in place. The final welding of all welded shims to take place in Station 3. | 2 | Perform at A-B also | [5 empty] | 40 | 2.5
9 | Install trim coil | [10 empty] | Sequence Plan R5
9.01 | Install trim coil on the top surface of the Type-C on Period 1 and 2 only on the MCHP - Right Side (See Figure 3 below). | 6 | [6 empty] | 120 | 2.5
10 | Complete local service and interface details | [10 empty] | Sequence Plan R5
10.01 | Inflate all wing support bladders between wing surfaces (A/B, B/C) and on the C wing (MCHP - Right Side only). | 2 | [6 empty] | 40 | 2.5 |  | LED: Bags were placed earlier
10.02 | Make local service runs/connections on the shell of each MC. | 8 | [6 empty] | 160 | 2.5 |  | 4 days for coolant lines 4 days for mod coils thermocouples and strain gages terminations
10.03 | Inject stycast or some compound to fill in all shim spaces in order to prevent VV/MC insulation from falling out. | 1 | [6 empty] | 20 | 2.5
11 | Final measurements / transfer completed MCHP to holding area | [10 empty] | Sequence Plan R5
11.02 | Make final metrology measurement of all fiducials. Scan the “B” flange of Type-C coil. Record the results. | [7 empty] | 0 | 2.5 |  | Done at 7.18
11.03 | Using tension tester measure bolt length on all tension fasteners and record the results. | 0.5 | [6 empty] | 10 | 2.5
11.04 | Mark part for identification | 0 | [6 empty] | 0 | 2.5
11.05 | Install lift support beams | 2 | [6 empty] | 40 | 2.5
11.06 | Remove from stand and measure weight of completed assembly | 1 | [6 empty] | 20 | 2.5
11.07 | Move to holding area. | 0 | [6 empty] | 0 | 2.5 |  | 246 shifts
| A1,B1,C1 subtotal task 5-11 | 122.75 | [6 empty] | 1745 |  | 740
Station 2 - Production Articles (HPA) and second half of FP #1 A2,B2,C2 | [11 empty] | Sequence Plan R5
1 | MC fit-up pre-check and surface insulation | [10 empty] | Sequence Plan R5
1.01 | Verify that mating MC's of a MCHP will come together without interferences by pre-fitting mating coils. This will include the Type-C coil with its interfacing Period Type-C coil. | 4 | [6 empty] | 80 | 2.5
1.02 | Epoxy paint all close fitting interfacing surfaces. | 3 | [6 empty] | 60 | 2.5
2 | Pre-measurement of MCHP Type A, B and C coils flanges plus interfacing Type-A coil flange | [10 empty] | Sequence Plan R5
2.01 | Set the Type-A coil on the pre-measurement fixture, “A” side flange down. | 1 | [6 empty] | 20 | 2.5 |  | 2 at a time on the 2 20 degree wedges
2.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
2.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
2.04 | Measure all of the tooling ball monuments on the winding form. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
2.05 | Scan the “B” flange of the Type-A coil. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
2.06 | Flip the Type-A coil placing the "B" side down and follow steps 2.02 thru 2.04 and scan the "A" side flange. | 5 | [6 empty] | 100 | 2.5
2.07 | Remove Type-A coil from stand and move to holding area. | 1 | [6 empty] | 20 | 2.5
2.08 | Set the Type-B coil on the fixture, “B” side flange down. | 2 | Why measure Type B earlier if never used | [5 empty] | 40 | 2.5 |  | 2 at a time on the 2 20 degree wedges
2.09 | Follow steps 2.02 thru 2.04 and scan the "A" side flange. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
2.1 | Remove Type-B coil from stand and store coil. | 1 | [6 empty] | 20 | 2.5
2.11 | Set the Type-C coil on the fixture, “B” side flange down. | 1 | [6 empty] | 20 | 2.5 |  | 2 at a time on the 2 20 degree wedges
2.12 | Follow steps 2.02 thru 2.04 and scan the "A" side flange. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
2.13 | Remove Type-C coil from stand and store coil. | 1 | [6 empty] | 20 | 2.5
2.14 | Set the adjoining MCHP Type-A coil on the fixture, “A” side flange down. | 1 | [6 empty] | 20 | 2.5
2.15 | Follow steps 2.02 thru 2.04 and scan the "B" side flange. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
2.16 | Flip the Type-A coil placing the "B" side down and follow steps 2.02 thru 2.04 and scan the "A" side flange. | 6 | [8 empty] | 120 | Metrology Staff Budgeted as LOE
2.17 | Remove the adjoining Type-A coil from stand and store coil. | 1 | [6 empty] | 20 | 2.5
3 | Shim sizing / preparations | [10 empty] | Sequence Plan R5
3.01 | Using flange measurement of the coils, define the A/A and A/B shim thickness.
3.02 | Compress alumina coated shims and sort by thickness the shim set that will be installed on the MCHP. | 3 | [6 empty] | 60 | 2.5 |  | May need more shims
4 | Pre-Installation Station 2 set-up recalibration | [10 empty] | Sequence Plan R5
4.01 | Install MCHP fixtures and metrology equipment. | [7 empty] | 0 | 2.5
4.02 | Perform metrology set-up and checks | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
5 | Pre-assemble A-A (Needs to be done total of 3 timee A1-A2, A3-A4, A5-A6)
5.01 | Position the Type-A modular coil on the fixture, “B” flange down. Obtain a set of “realigned” fiducial positions.
5.02 | Align the laser tracker to the conical seats locking into a minimum of 8 of them.
5.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls.
5.04 | Place all alumina and grind inboard weld shims on the coil.
5.05 | Install dial indicators on the modular coil in areas where we expect to see deflection.
5.06 | Lower the mating type A modular coil into position.
5.07 | Measure the monuments on the bottom coil. Jack areas of the coil as necessary to bring displaced monuments back to within .002” of their original position.
5.08 | Using three target points, perform the positioning as was done in the A1-A2 fit up test.
5.09 | Install studs, supernuts, and torque to 50% of final value.
5.1 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck.
5.11 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less.
5.12 | If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%.
5.13 | Install the A-A locator bushings at two stud locations for use in re-positioning MCHP in Stage 3.
5.14 | Remove all studs, nuts, shims etc. Identify shim locations.
6 | A-B modular coil assembly | [10 empty] | Sequence Plan R5
6.01 | Place the Type-A coil, “A” flange down, on the 20deg fixture. Obtain a set of “realigned” fiducial positions for the “A” and “B” coils. | 1 | [6 empty] | 20 | 2.5
6.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
6.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
6.04 | Place all alumina and grind inboard weld shims on the coil. | 2 | [6 empty] | 40 | 2.5
6.05 | Lower the Type-B coil onto the Type-A coil. | 1 | [6 empty] | 20 | 2.5
6.06 | Measure the monuments on the A coil. Jack areas of the coil as necessary to bring displaced monuments back to within .002” of their original position. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
6.07 | Using three target points on the B coil, perform the X-Y positioning of the B coil. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
6.08 | Install studs, supernuts, and torque to 50% of final value. | 2 | [6 empty] | 40 | 2.5
6.09 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
6.1 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
6.11 | If the above step does not fall within .007" or less then loosen all studs, adjust shims locally. Re-torque all studs to 50%. | 3 | [6 empty] | 60 | 2.5
6.12 | One hole at a time, remove the supernut. Using the eccentric gage slid onto the stud define the hole eccentricity. Select bushing and machine to match required eccentricity. Install bushing. Replace nut and tighten back to 50% and recheck alignment. | 1.5 | [6 empty] | 30 | 2.5 |  | LED: See above
6.13 | Complete tightening of flange bolts to 100%. | 1 | [6 empty] | 20 | 2.5
6.14 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .007” or less. | 3 | [8 empty] | 60 | Metrology Staff Budgeted as LOE
6.15 | Scan the “B” flange of Type-B coil | 1 | [6 empty] | 20 | 2.5
6.16 | Using the "B" flange measurement of the Type-B coil and the earlier "A" flange measurement of the Type-C coil, define all B/C flange shim thickness.
7 | (A-B) to C modular coil assembly (MCHP) | [10 empty] | Sequence Plan R5
7.01 | Place the “A/B” assembly, “A” coil down, on the 40deg fixture. Obtain a set of “realigned” fiducial positions. For the “A”, “B”, and “C” coils. | 2 | [6 empty] | 40 | 2.5
7.02 | Using the laser tracker, align to the conical seats locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
7.03 | Establish a global coordinate system based on the modular coil geometry. Measure the monuments on the fixture and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
7.04 | Place all alumina and grind inboard weld shims on the coil. | 2 | [6 empty] | 40 | 2.5
7.05 | Lower the Type-C coil onto the Type-B coil. | 1 | [6 empty] | 20 | 2.5
7.06 | Measure the monuments on the A coil to evaluate monument displacements. If movement greater than .002" is observed discuss with back office on how to proceed in bringing displaced monuments back to within .002" of their original position. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
7.07 | Using three target points on the Type-C coil, perform the X-Y positioning of the coil. | 1 | [6 empty] | 20 | 2.5
7.08 | Install studs, supernuts, and torque to 50% of final value. | 2 | [6 empty] | 40 | 2.5
7.09 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
7.1 | Measure the tooling balls on all coils. The maximum deviation from the “realigned” points should be .010” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
7.11 | One hole at a time, remove the supernut. Using the eccentric gage slid onto the stud define the hole eccentricity. Select bushing and machine to match required eccentricity. Install bushing. Replace nut and tighten back to 50% and recheck alignment. | 1.5 | [6 empty] | 30 | 2.5 |  | LED: See above
7.12 | Complete tightening of flange bolts to 100%. | 1 | [6 empty] | 20 | 2.5
7.13 | Measure the tooling balls on both coils. The maximum deviation from the “realigned” points should be .010” or less. | 4 | [8 empty] | 80 | Metrology Staff Budgeted as LOE
8 | Tack weld inboard welded shims | [10 empty] | Sequence Plan R5
8.01 | Partially tack weld all inboard shims to one flange to keep them in place. The final welding of all welded shims to take place in Station 3. | 1 | [6 empty] | 20 | 2.5
9 | Install trim coil | [10 empty] | Sequence Plan R5
9.01 | Install trim coil on the top surface of the Type-C on Period 1 and 2 only on the MCHP - Right Side (See Figure 3 below). | 6 | [6 empty] | 120 | 2.5
10 | Complete local service and interface details | [10 empty] | Sequence Plan R5
10.01 | Inflate all wing support bladders between wing surfaces (A/B, B/C) and on the C wing (MCHP - Right Side only). | 2 | [6 empty] | 40 | 2.5 |  | See above
10.02 | Make local service runs/connections on the shell of each MC. | 8 | [6 empty] | 160 | 2.5 |  | 4 days for coolant lines 4 days for mod coils thermocouples and strain gages terminations
10.03 | Inject stycast or some compound to fill in all shim spaces in order to prevent VV/MC insulation from falling out. | 1 | [6 empty] | 20 | 2.5
11 | Final measurements / transfer completed MCHP to holding area | [10 empty] | Sequence Plan R5
11.01 | Install or identify three primary fiducials that will be used in positioning the Period in Station 3. | 1 | [6 empty] | 20 | 2.5
11.02 | Make final metrology measurement of all fiducials. Scan the “B” flange of Type-C coil. Record the results. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
11.03 | Using tension tester measure bolt length on all tension fasteners and record the results. | 0.5 | [6 empty] | 10 | 2.5
11.04 | Mark part for identification | 0 | [6 empty] | 0 | 2.5
11.05 | Install lift support beams | 2 | [6 empty] | 40 | 2.5
11.06 | Remove from stand and measure weight of completed assembly and Move to holding area. | 2 | [6 empty] | 40 | 2.5
A2,B2,C2 Subtotal task 5-11 |  | 79.5 | [6 empty] | 970 |  | 620
Station 2-Modular Coil Subassembly-FP#2
| Assemble/Align Mod-Coils A3/B3/C3 | 122.75 | [6 empty] | 1745 |  | 740 | Sequence Plan R5
| Assemble/Align Mod-Coils A4/B4/C4 | 79.5 | [6 empty] | 970 |  | 620 | Sequence Plan R5
Station 2-Modular Coil Subassembly-FP#3
| Assemble/Align Mod-Coils A5/B5/C5 | 122.75 | [6 empty] | 1745 |  | 740 | Sequence Plan R5
| Assemble/Align Mod-Coils A6/B6/C6 | 79.5 | [6 empty] | 970 |  | 620 | Sequence Plan R5 |  | 3575 | 2160 | 10725 | 6480 | 17205
Station 3-Assemble Mod Coils and VVSA-FP#1
| Misc Hardware |  | 5
| Procure and load test 3 legged actuator System | 4 | 43 | [5 empty] | 96 | 3
| Procure, Fabricate and load test 3 legged actuator Lift Fixture | 8 | 6 | [5 empty] | 128 | 2
| Begin Assembly of First Field Period Assy | 2 | [6 empty] | 40 | 2.5
| Fab new platform legs | 4 | [6 empty] | 64 | 2
| Install station 3 platforms (8 required) | 4 | 10 | [5 empty] | 112 | 3.5
| Test out station 3 equipment and procedures |  | 10 | [5 empty] | 0 | 2.5
Step | Assembly Step
1 | Pre-Installation set-up
1.01 | Install Station 3 site monuments as needed to perform metrology measurements. | 3 | 2 | [5 empty] | 60 | 2.5
1.02 | Install floor mounted tracks and VV base support | 5 | 1 | [5 empty] | 100 | 2.5
1.03 | Use rigging operations to establish the MCHP CG location. | 2 | [6 empty] | 40 | 2.5
2 | Pre-assemble left MCHP | [7 empty] | 0 | 2.5
2.01 | Install MCHP support cart assemblies | 4 | [6 empty] | 80 | 2.5
2.02 | Verify cart motion. Move left cart to final assembly position to accept left MCHP and secure to the floor supports. Move right cart far to the right. | 2 | [6 empty] | 40 | 2.5
2.03 | Install adjustor bar support weldment on Left Side | 0 | [6 empty] | 0 | 2.5
2.04 | Using the SISSCO crane, position left MCHP on the cart assembly | 1 | [6 empty] | 20 | 2.5
2.05 | Secure left MCHP at three location to vertical support posts on support cart base. | 2 | [6 empty] | 40 | 2.5
2.06 | Measure the monuments on the positioned left MCHP and on the walls to establish the machine coordinate for further assembly operations. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
2.07 | Set the positioning stop on the cart so it returns to the machine coordinate defined position in further assembly steps. | 1 | [6 empty] | 20 | 2.5
3 | Pre-assemble right MCHP | [7 empty] | 0 | 2.5
3.01 | Move the right base support cart to its final position ready to accept the right MCHP. Position the AirLoc Wedgemount in a lowered position. | 0.5 | [6 empty] | 10 | 2.5
3.02 | Lift the right side MCHP using the SISSCO crane and position it to be ready to engage the preinstalled Type-A flange guide bushings. | 1 | [6 empty] | 20 | 2.5
3.03 | Temporary fasteners located adjacent to the alignment bushings can be used to help bring the parts together. | 0 | [6 empty] | 0 | 2.5
3.04 | While held by the crane bring the AirLoc Wedgemount leveler up to take the load. | 0 | [6 empty] | 0 | 2.5
3.05 | Install temporary scaffolding to install flange hardware | 1 | [6 empty] | 20 | 2.5
3.06 | Install bolts and shims as needed for assembly tolerances. | 1 | [6 empty] | 20 | 2.5
3.07 | Tighten flange fasteners to 50% | 1 | [6 empty] | 20 | 2.5
3.08 | Perform metrology measurements of all alignment fiducials on both MCHP's. The maximum deviation from the reference points should be .020” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
3.09 | Perform position adjustments on the right side MCHP if needed. Loosen all studs, adjust AirLock Wedgemounts as needed and install alternate sized shims. Re-torque all studs to 50% and recheck. | 2 | [6 empty] | 40 | 2.5
3.1 | Verify position of the VV support hanger locations (top and bottom) on the left and right MCHP. May be done as part of 3.08 if 3.09 not needed | 3 | [8 empty] | 60 | Metrology Staff Budgeted as LOE
3.11 | Remove flange hardware and temporary platforms | 1 | [6 empty] | 20 | 2.5
4 | Install laser screens |  | 2
4.01 | Establish a global coordinate system based on the full period geometry. Measure the monuments on the MCHP's and on the walls. | 2 | [8 empty] | 40 | Metrology Staff Budgeted as LOE
4.02 | Using metrology and the established global coordinate system place all of the laser screens as called out in the Stage 3 drawings. | 2 | [6 empty] | 40 | 2.5
4.03 | Turn each lasers on and with metrology determine their alignment. Record the laser position. | 1 | [6 empty] | 20 | 2.5
4.04 | Based on metrology measurements of the screens and lasers the screens path can be defined by the back office. Print the path on milar paper and using metrology mount the milar on the screens. | [7 empty] | 0 | 2.5
4.05 | Disengage the MCHP's by using the left support and adjustor bar to move the left MCHP. | 1 | [6 empty] | 20 | 2.5
4.06 | Remove both MCHP's. | 2 | [6 empty] | 40 | 2.5 |  | Can these stay on the carts and be rolled all the way back?
5 | Install vacuum vessel | [7 empty] | 0 | 2.5
5.01 | Remove the adjustor bar support from left side. | 0 | [6 empty] | 0 | 2.5
5.02 | Install VV NBI port support stand. | 2 | [6 empty] | 40 | 2.5
5.03 | Install VVSA to base support and make the connection to the NBI port attachment. | 1 | [6 empty] | 20 | 2.5
5.04 | Using metrology take tooling ball readings off the VV shell to properly position the VVSA to the global coordinate system. Secure the VVSA to the base and at the NBI port support stand. | 2 | [6 empty] | 40 | 2.5
6 | Install left MCHP over VV | [7 empty] | 0 | 2.5
6.01 | Install any bumper protection components on the VV (left and right side) before manipulating left MCHP over the VV. | 0.5 | [6 empty] | 10 | 2.5
6.02 | Move the left base support cart to the far left so it will not interfere with the MCHP installation. Position the AirLoc Wedgemount in a lowered position. | 0 | [6 empty] | 0 | 2.5
6.03 | Using the SISSCO actuators with laser guidance move the left MCHP over the VV. | 2 | [6 empty] | 40 | 2.5
6.04 | Re-install the left adjustor bar. | 0 | [6 empty] | 0 | 2.5
6.05 | Once the MCHP has been moved over the VV bring up Wedgemount levelers to stabilize the unit and take metrology measurements. Make position adjustments to properly align the MCHP. | 2 | [6 empty] | 40 | 2.5
6.06 | Transfer the full load to the AirLoc Wedgemount leveler. | 0 | [6 empty] | 0 | 2.5
6.07 | Using the adjustor bar on the left side move the MCHP to the left 1/2". | 0 | [6 empty] | 0 | 2.5
7 | Install right MCHP over VV | [7 empty] | 0 | 2.5
7.01 | Move the right base support cart to the far right so it will not interfere with the MCHP installation. Position the AirLoc Wedgemount in a lowered position. | 0 | [6 empty] | 0 | 2.5
7.02 | Using the SISSCO actuators with laser guidance move the right MCHP over the VV TO WITHIN 1/2" OF ITS FINAL POSITION and pause. Go to the next step. | 2 | [6 empty] | 40 | 2.5
7.03 | Using the adjustor bar on the left side move the left MCHP to its final position. | 0.5 | [6 empty] | 10 | 2.5
7.04 | With the left MCHP in place, move the right side MCHP using the CISSCO crane and position it to be ready to engage the preinstalled Type-A flange guide bushings. | 0.5 | [6 empty] | 10 | 2.5
7.05 | Temporary fasteners located adjacent to the alignment bushings can be used to help bring the parts together. | 0 | [6 empty] | 0 | 2.5
7.06 | While held by the crane bring the AirLoc Wedgemount leveler up to take the load. | 0.5 | [6 empty] | 10 | 2.5
7.07 | Remove the laser screens to provide more floor space for scaffolding. | 0 | [6 empty] | 0 | 2.5
7.08 | Install temporary scaffolding to install flange hardware | 4 | [6 empty] | 80 | 2.5
7.09 | Install bolts and all alumina and inboard weld shims. | 2 | [6 empty] | 40 | 2.5
7.1 | Tighten flange fasteners to 50% | 1 | [6 empty] | 20 | 2.5
7.11 | Make a hand "wiggle" test (rotate on bolt) on all shims to make sure that they are tight. If a loose shim is found back off on sufficient adjacent bolts to allow a replacement shim to be inserted. Tighten bolt and recheck. | 1 | [6 empty] | 20 | 2.5
7.12 | Perform metrology measurements of all alignment fiducials on both MCHP's. The maximum deviation from the reference points should be .020” or less. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
7.13 | Perform position adjustments on the right side MCHP if tolerance is not met. Loosen all studs, adjust AirLock Wedgemounts as needed; install alternate sized shims. Re-torque all studs to 50% and recheck. | 3 | [6 empty] | 60 | 2.5
7.14 | Remove SISSCO actuator from right MCHP. | 0 | [6 empty] | 0 | 2.5
7.15 | One hole at a time, remove the supernut. Using the eccentric gage slid onto the stud define the hole eccentricity. Select bushing and machine to match required eccentricity. Install bushing. Replace nut and tighten back to 50% and recheck alignment. | 0.5 | [6 empty] | 10 | 2.5
7.16 | Tighten nuts 100%. Measure before welding adequate coil alignment and fit-up of shims | 1 | [6 empty] | 20 | 2.5
8 | Weld all inboard shims | [7 empty] | 0 | 2.5
8.01 | Follow a predefined weld sequence at all MC's and partially weld the inboard shim. Perform weld peening operation. Perform a metrology measurement to re-verify coil alignment. | 15 | [6 empty] | 300 | 2.5
8.02 | Final complete MC scan to verify period alignment. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
9 | VVSA attachment to MC. | [7 empty] | 0 | 2.5
9.01 | Attach VV permanent vertical supports to the MC at the two outboard connection points at the top and bottom of the Type-A MC. | 2 | [6 empty] | 40 | 2.5
9.02 | Attach temporary VV vertical supports to the MC at the two connection points at the top and bottom of the Type-B MC. | 1 | [6 empty] | 20 | 2.5
9.03 | Disconnect base support and transfer load to VV vertical supports. | 1 | [6 empty] | 20 | 2.5
9.04 | Install VV lateral supports and align VVSA to modular coils | 4 | [6 empty] | 80 | 2.5
9.05 | Prepare VVSA for transport. Install blocking as required to prevent any motion relative to the modular coils. | 2 | [6 empty] | 40 | 2.5
10 | Transfer Period to NCSX test cell. | [7 empty] | 0 | 2.5
10.01 | Install crane rigging to MCWF and transfer the unit to the transfer support frame. Secure Period /support frame to the transporter. | 2 | [6 empty] | 80 | 5
10.02 | Transfer completed Period to Station 5 located in NCSX test cell. | 1 | [6 empty] | 40 | 5
| subtotal FP#1 | 112 | [6 empty] | 1800
Station 3-Assemble Mod Coils and VVSA-FP#2
| Perform above sequence | 112 | [6 empty] | 1800 | 2.6
Station 3-Assemble Mod Coils and VVSA-FP#3
| Perform above sequence | 112 | [6 empty] | 1800 | 2.6
Job: 1810 - Field Period Assembly-VIOLA |  |  | 357 | 0 | 0 | 0 | 4.5 | 3 | 31526.6
Based on quotes from PPPL Tech Shop based on similar tasks, tempered (adjusted) for complexity of having to do all welds from inside of the vessel.
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA
Station 5- Final FP Assy -FP#1 (in NCSX TC)
| metrology network | 10 | 7 | [5 empty] | 160
| Bolt on 2 Port Extensions needed for first Plasma diagnostics | 1 | [6 empty] | 16 | 2 |  | 10" ports provided by WBS 38
| MTM NCR Hardware repurchase (bolt kits & cover plates) |  | 42
| Weld Wire & weld supples |  | 15
| Testout Sta 5 equipt & procedures | 5 | [6 empty] | 160 | 4
| Check 3 sled interfaces adjust holes | 12 | [6 empty] | 384 | 4
| Fixtures installed - final metrology | 6 | [6 empty] | 192 | 4
| Miscellaneous for tooling |  | 12
Station 5 preinstallation in parallel
1 | Component preparations
1.01 | The short dome port (the one on the top of the dome) needs to cut off near the dome. The longest port can remain. | 2 | [6 empty] | 40 | 2.5
1.02 | Install heat tape and theomocouples on all ports. | 0 | [6 empty] | 0 | 2.5 |  | Covered in Station 2 LED: Reversed order of 1.02 & 1.03
1.03 | Install insulation system around all ports. | 0 | [6 empty] | 0 | 2.5 |  | Covered in Station 2
2 | Pre-Installation set-up
2.01 | Install period support fixture | 2 | [6 empty] | 40 | 2.5
2.02 | Install FPA on support stand. Use leveler pad to engage base of MC. Add bolts to secure in place. | 2 | [6 empty] | 40 | 2.5
2.03 | Install external working platforms | 4 | [6 empty] | 80 | 2.5
2.04 | Install internal VV working platforms | 3 | [6 empty] | 60 | 2.5
3 | VV port installation
3.01 | Install the domes (left and right side), inserting the long dome port through the MC opening, and weld the dome shell to the VV. | 2 | [6 empty] | 40 | 2.5
3.02 | Install small dome ports and remaining circular ports. Use a guide tool located at the MC hole opening to help support and center the port. Ports should already have insulation, heater tape and thermocouples on them. | 30 | [6 empty] | 600 | 2.5
3.03 | Leak check each port immediately after it is welded. | 30 | [6 empty] | 600 | 2.5 |  | In parallel with welding or on second shift
4 | Install port boot seal assembly
4.01 | Install boots on all ports except for the two port 4's. | 16 | [6 empty] | 320 | 2.5
5 | MC lead and coolant connections
5.01 | Install MC lead connections on each of the MC's and temporally position the leads so they will not interfere with the TF coil installation and for routing through the PF structure. | [10 empty] | Done in Station 6
5.02 | Install MC coolant lines on each MC and position them for the TF installation and routing through PF structure. | 12 | [6 empty] | 240 | 2.5
5.03 | Platforms may need to be altered or moved for the installation of the TF coils. | 3 | [6 empty] | 60 | 2.5
6 | TF installation - right side
6.01 | Rotate two individual TF coils over the MC on the right side and temporarily support them off the Type-B and C MC's. | 2 | [6 empty] | 40 | 2.5
6.02 | Attach the temporary support at the end of the Type-C MC used to unload the a pair of center supports. | 1 | [6 empty] | 20 | 2.5
6.03 | Lower leveler pad to disengage base of MC on the right side. Remove right side leveler pad and intermediate support. | 0 | [6 empty] | 0 | 2.5
6.04 | Install TF support brackets (top & bottom) to the port 12 side on the Type-A MC (platforms will be needed). | 2 | [6 empty] | 40 | 2.5
6.05 | Slide the first TF assembly against the TF support bracket and secure in place with the mating support bracket. | 1 | [6 empty] | 20 | 2.5
6.06 | Install TF support brackets (top & bottom) to the port 12 side on the Type-B MC. | 2 | [6 empty] | 40 | 2.5
6.07 | Slide the second TF assembly against the support bracket and secure in place with the mating support bracket. | 1 | [6 empty] | 20 | 2.5
6.08 | Install machine support plates (inboard and outboard) on the bottom, spanning two TF coil support brackets. | 3 | [6 empty] | 60 | 2.5
6.09 | Reinstall leveler pad to engage base of MC on the right side. | 0 | [6 empty] | 0 | 2.5
6.1 | Installed one side of the TF support brackets on the Type-C coil (top and bottom) for the TF installation to occur at Station 6. | 1 | [6 empty] | 20 | 2.5
7 | TF installation - left side
7.01 | The TF installation on the left side will follow the same ten (10) steps that were followed on the right side. | 13 | [6 empty] | 260 | 2.5
8 | TF fit-up check
8.01 | Perform a fit-up check of the four TF coils to determine if they can be positioned within tolerances. | 5 | [6 empty] | 100 | 2.5
9 | Install Ports 4
9.01 | Tack weld the left and right port 4's. Use a local laser attached to the port cover to define the port trajectory and to aid positioning in port during welding. | 2 | [6 empty] | 40 | 2.5
9.02 | Install boots on both port 4's. | 4 | [6 empty] | 80 | 2.5
10 | Installation of PF structural members and routing of MC coolant and leads.
10.01 | Install the PF coil support structure that surround the TF coils. In doing this the MC leads and coolant lines need to be routed to the outside of the PF structure. PF structure is only partially installed at the Type-C MC's. | 8 | [6 empty] | 160 | 2.5
11 | MC header installation and coolant connections
11.01 | Install the MC coolant manifold outside of the PF structure in the area of PF6. | 3 | [6 empty] | 60 | 2.5
11.02 | Connect all MC coolant lines to the manifold (40 lines top and bottom) | 20 | [6 empty] | 400 | 2.5 |  | Flex lines but need field supports installed
12 | Diagnostic
12.01 | Install Rogowski coils on the end of the VV, left side. Route leads through space between port 8 and spool port opening and coil onto shell of MC for future routing | 5 | [6 empty] | 100 | 2.5
13 | Final measurements
13.01 | Obtain a set of Period 1 alignment fiducial positions to use in locating the VV within the MC. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
13.02 | Using the laser tracker, align to tooling balls on each MCHP, locking into a minimum of 8 of them. | 1 | [8 empty] | 20 | Metrology Staff Budgeted as LOE
13.03 | Using monuments on the VV for alignment, bring the VV into proper alignment. Make final adjust in the VV supports to secure VV in place. | 4 | [6 empty] | 80 | 2.5
13.04 | Install or identify three primary fiducials that will be used in positioning the Period in Station 6. | 2 | [6 empty] | 40 | 2.5
13.05 | Make a final measurement of all fiducials, the VV end flanges and the Type-C MC end flanges. Record the results. | 5 | [8 empty] | 100 | Metrology Staff Budgeted as LOE
13.1 | Final Acceptance tests
13.11 | Check Assembly (bolts, etc) | 5 | [6 empty] | 100 | 2.5
13.12 | Check Diagnostics (Loops, thermocouples) | 5 | [6 empty] | 100 | 2.5
13.13 | Check manifolds (pressure, flow, etc.) | 5 | [6 empty] | 100 | 2.5
13.14 | Check 6 modcoils (voltage etc) | 6 | [6 empty] | 120 | 2.5
13.15 | Check trim coils (voltage etc) | 3 | [6 empty] | 60 | 2.5
13.16 | Check TF coils (voltage etc) | 6 | [6 empty] | 120 | 2.5
14 | Transfer Period to final assembly (Station 6).
14.01 | Install crane rigging to completed Period assembly | 2 | [6 empty] | 40 | 2.5
14.02 | Remove platforms | 1 | [6 empty] | 20 | 2.5
14.03 | Transfer completed Period to Station 6 located in NCSX test cell. | 2 | [6 empty] | 40 | 2.5
| Install on support platform | 15 | 12 | [5 empty] | 600 | 5
| subtotal | 211 | [6 empty] | 5000
Station 5- Final FP Assy -FP#2 (in NCSX TC)
| Repeat steps for FP #1 | 211 | [6 empty] | 5000 | 2.5
Station 5- Final FP Assy -FP#3 (in NCSX TC)
| Repeat steps for FP #1 | 211 | [6 empty] | 5000 | 2.5
Job:1810 - Field Period Assembly-VIOLA Total |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA |  |  | 88 | 0 | 0 | 0 | 0 | 0 | 15912
|  |  | 802 | 50 | #REF! | #REF! | #REF! | #REF! | #REF!
HP Techs EMEM???
Is this in Job 1805?
What is this?
Is this in Job 1805?
A-A done above