## Risk Analysis Results
Percentiles | Cost/Schedule Unceratinty Contingency | Risk Contingency (Cost & Schedule) | Schedule Contingency - Risks | Schedule Uncertainty Contingency | Total Cost Contingency | Total Project Cost | Total Schedule Contingency
0% | 2007.9977 | -2609.3413 | -8.1749 | -4.4579 | 2953.2197 | 115421.4027 | -8.563
5% | 5096.0817 | 167.4752 | -2.3007 | -0.5869 | 6780.831 | 119249.014 | -0.54537
10% | 5733.57 | 594.917 | -1.1751 | 0.10911 | 7602.3605 | 120070.5435 | 0.85404
15% | 6182.6782 | 878.2255 | -0.3696 | 0.57485 | 8209.3941 | 120677.5771 | 1.7916
20% | 6553.2448 | 1168.1054 | 0.13131 | 0.96625 | 8659.135 | 121127.318 | 2.5115
25% | 6894.8486 | 1424.8283 | 0.6447 | 1.3301 | 9047.6485 | 121515.8315 | 3.1359
30% | 7170.1434 | 1666.009 | 1.0972 | 1.6914 | 9424.5382 | 121892.7212 | 3.6641
35% | 7449.7113 | 1891.2892 | 1.4949 | 1.9911 | 9761.3747 | 122229.5577 | 4.1699
40% | 7709.0205 | 2107.6454 | 1.8452 | 2.2835 | 10090.99 | 122559.173 | 4.6871
45% | 7964.9781 | 2311.5696 | 2.1951 | 2.6145 | 10408.2549 | 122876.4379 | 5.158
50% | 8245.3052 | 2497.0309 | 2.5458 | 2.9348 | 10717.0159 | 123185.1989 | 5.6239
55% | 8493.9574 | 2675.2281 | 2.9133 | 3.2609 | 11028.3144 | 123496.4974 | 6.1379
60% | 8759.3535 | 2871.2145 | 3.3009 | 3.596 | 11357.5681 | 123825.7511 | 6.6279
65% | 9046.2779 | 3066.4609 | 3.6903 | 3.972 | 11696.8422 | 124165.0252 | 7.1328
70% | 9327.4731 | 3245.1648 | 4.0791 | 4.3711 | 12057.6836 | 124525.8666 | 7.6462
75% | 9646.3933 | 3449.4109 | 4.4943 | 4.7839 | 12418.7294 | 124886.9124 | 8.2137
80% | 10013.9501 | 3667.4767 | 4.9669 | 5.2671 | 12853.3211 | 125321.5041 | 8.8458
85% | 10423.1909 | 3963.0375 | 5.5264 | 5.857 | 13367.9347 | 125836.1177 | 9.5842
90% | 10909.1375 | 4333.5621 | 6.2427 | 6.541 | 14003.6561 | 126471.8391 | 10.5429
95% | 11700.0843 | 4897.6529 | 7.1827 | 7.4581 | 14911.8211 | 127380.0041 | 11.8468
100% | 15181.7659 | 7504.0482 | 13.5513 | 11.0289 | 19557.7244 | 132025.9074 | 18.3602
Total Project Cost at 80% |  | 125321.5041
Less Actual through April |  | 67242
Less ETC w/o Contingency |  | 45226.183
| Contingency Allowace | 12853.3211
| % of ETC | 28.42%
If above analysis is used it is not possible to segregate risk and uncertainty contingency requirements.
However, the cost contingency for schedule stretch can be calculated as |  |  |  | 2299.9187 | for a contingency of | 8.8458 | months
This leaves a cost contingency of |  | 10553.4024 | or as % of ETC | 23.33%
So for spreading contingency by year, assume that percentage of costs planned for each year and put the schedule amount in the last year.

## Model
Total Project Cost Summary
Actual Cost Incurred | 67242
Base ETC without Contingency | 45226.183
Total Project Cost w/o Conting. | 112468.183
Cost Contingency Allowance
Cost/Schedule Unceratinty | -56926.183
Risk Contingency (Cost & Schedule) | 0
Total Cost Contingency | -56926.183
Total Project Cost | 55542
Schedule Contingency
Schedule Uncertainty | -45
Risk Contingency | 0
Total Schedule Contingency | -45

## Estimate Uncertainty Matrix
Estimate Uncertainty Matrix
Design Complexity
| Design Maturity | Low |  | Medium |  | High
| Low | -15% | 25% | -20% | 40% | -30% | 60%
| Medium | -10% | 15% | -15% | 25% | -20% | 40%
| High | -5% | 10% | -10% | 15% | -15% | 25%
|  | Low | High
| HH | -15% | 25%
| HL | -5% | 10%
| HM | -10% | 15%
| LH | -30% | 60%
| LL | -15% | 25%
| LM | -20% | 40%
| MH | -20% | 40%
| ML | -10% | 15%
| MM | -15% | 25%
| PM | 50% | 100% | per PM direction - high uncertainty
assumed for 8101 and 8102
Definitions
Design Maturity
| High | Final design available. All design features/requirements well known.
No further design development or evolution expected that will impact estimate
| Medium | Preliminary design available. Some additional design evolution likely
Further developments can be somewhat expected/anticipated and reflected in estimate
| Low | No better than conceptual design basis currently available. Design details, procedures,
etc. still need much development and evolution of requirements beyond estimate basis is likely and expected
Design Complexity
| Low | Work is fairly well understood -- either standard construction or repetition of activities performed in past
Little likelihood of estimate not being well understood and requirements not being well defined
| Medium | More complex work requirements that have potential to impact cost and schedule estimates
Limited experience performing similar tasks, so ability to estimate accurately is somewhat suspect
| High | Extremely challenging tasks and/or requirements. Unique or first-of-a-kind assembly or work tasks
No good basis for estimating work exists so there is a high degree of estimate uncertainty
Basis for Estimate Uncertainties
Per AACEI Recommended Practice 18R-97, Cost Estimate Classification System
As Applied in Engineering, Procurement and Construction for the Process Industry
| Estimate Class | Level of Definition |  | Accuracy Range |  |  |  | NCSX Definition | Range Used
| 5 | 0 - 2% |  | -20 to -50% - +30 to +100% |  |  |  | L maturity; H complexity | -30/+60%
| 4 | 1 - 15% |  | -15 to -30% - +20 to +50% |  |  |  | MH and LM | -20/+40%
| 3 | 10 - 40% |  | -10 to -20% - +10 to +30% |  |  |  | MM and LL | -15/+25%
| 2 | 30 - 70% |  | -5 to -15% - +5 to +20% |  |  |  | ML and HM | -10/+15%
| 1 | 50 - 100% |  | -3 to -10% - +3 to +15% |  |  |  | H maturity; L complexity | -5/+10%

## Estimate Ranges
NCSX Cost Estimate Ranges
[7 empty] | Range Estimate Using Standard Matrix for Uncertainty |  |  | Job Manager Uncertainty |  | Range Estimate Using Job Manager Uncertainty |  |  | Variance
WBS | Job | Sub-Job | Estimate | Maturity | Complexity |  | Low | High | Risk Calc | Low | High | Low | High | Risk Calc | Low | High
2 | Job: 2101 - Fueling Systems-BLAMCHARD |  | 63.168 | L | L | LL | 53.6928 | 78.96 | 0 | -5% | 25% | 60.0096 | 78.96 | 0 | 6.3168 | 0
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD |  | 174.41 | L | L | LL | 148.2485 | 218.0125 | 0 | -5% | 25% | 165.6895 | 218.0125 | 0 | 17.441 | 0
2 Total |  |  | 237.578
3 | Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | 23.453
|  | 124V - Flux loop junction boxes and spacer templates | 58.268
|  | MD2 - Modular Coil C-wound Loops | 18.626
|  | MD3 - Rogowski Coils | 158.313
|  | MD4 - TF and PF Co-wound Loops | 23.994
| Job: 3101 - Magnetic Diagnostics-STRATTON Total |  | 282.654 | H | L | HL | 268.5213 | 310.9194 | 0 | -5% | 15% | 268.5213 | 325.0521 | 0 | 0 | 14.1327
| Job: 3601 - Edge Divertor Diagnostics-STRATTON |  | 25.318 | H | L | HL | 24.0521 | 27.8498 | 0 | -10% | 10% | 22.7862 | 27.8498 | 0 | -1.2659 | 0
| Job: 3801 - Electron Beam Mapping-STRATTON |  | 250.677 | M | M | MM | 213.0754 | 313.3462 | 0 | -10% | 25% | 225.6093 | 313.3462 | 0 | 12.5339 | 0
| Job: 3901 - Diagnostics sys Integration-STRATTON |  | 132.944 | H | L | HL | 126.2968 | 146.2384 | 0 | -5% | 10% | 126.2968 | 146.2384 | 0 | 0 | 0
3 Total |  |  | 691.593
4 | Job: 4101 - AC Power-RAMAKRISHNAN | 411 - Auxiliary AC Power Systems | 123.701
|  | 412 - Experimental AC Power Systems | 34.881
| Job: 4101 - AC Power-RAMAKRISHNAN Total |  | 158.582 | H | L | HL | 150.6529 | 174.4402 | 0 | -10% | 15% | 142.7238 | 182.3693 | 0 | -7.9291 | 7.9291
| Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - C-Site DC Systems | 592.095 | H | L | HL | 562.4903 | 651.3045 | 0 | -10% | 15% | 532.8855 | 680.9093 | 0 | -29.6048 | 29.6047
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - Electrical Interlocks | 460.925
|  | 442 - Kirk Key Interlocks | 83.588
|  | 443 - Real Time Control Systems | 14.772
|  | 444 - Instrument Systems | 216.443
|  | 445 - Coil Protection Systems | 280.161
| Job: 4401 - Control & Protection-RAMAKRISHNAN Total |  | 1055.889 | M | L | ML | 950.3001 | 1214.2724 | 0 | -5% | 15% | 1003.0946 | 1214.2724 | 0 | 52.7944 | 0
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - System Design & Interfaces | 211.618
|  | 452 - Electrical Systems Support | 199.076
|  | 453 - System Testing (PTP's) | 267.153
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN Total |  | 677.847 | H | L | HL | 643.9547 | 745.6317 | 0 | -10% | 15% | 610.0623 | 779.524 | 0 | -33.8924 | 33.8923
4 Total |  |  | 2484.413
5 | Job: 5101 - Network and Fiber Infrastruct-SICHTA |  | 144.271 | M | L | ML | 129.8439 | 165.9116 | 0 | -20% | 30% | 115.4168 | 187.5523 | 0 | -14.4271 | 21.6406
| Job: 5201 - I&C Systems-SICHTA |  | 196.596 | M | L | ML | 176.9364 | 226.0854 | 0 | -20% | 30% | 157.2768 | 255.5748 | 0 | -19.6596 | 29.4894
| Job: 5301 - Data Acquisition-SICHTA |  | 164.14 | M | L | ML | 147.726 | 188.761 | 0 | -20% | 30% | 131.312 | 213.382 | 0 | -16.414 | 24.621
| Job: 5401 - Facility Timing & Synchron.-SICHTA |  | 203.111 | M | M | MM | 172.6444 | 253.8887 | 0 | -20% | 30% | 162.4888 | 264.0443 | 0 | -10.1556 | 10.1555
| Job: 5501 - Real Time Control System-SICHTA |  | 129.109 | M | L | ML | 116.1981 | 148.4754 | 0 | -20% | 30% | 103.2872 | 167.8417 | 0 | -12.9109 | 19.3663
| Job: 5601 - Central Safety &Interlock Sys-SICHTA |  | 221.284 | L | M | LM | 177.0272 | 309.7976 | 0 | -20% | 50% | 177.0272 | 331.926 | 0 | 0 | 22.1284
| Job: 5801 - Central I&C Integr& Oversight-SICHTA |  | 63.117 | H | L | HL | 59.9611 | 69.4287 | 0 | -5% | 5% | 59.9611 | 66.2728 | 0 | 0 | -3.1559
5 Total |  |  | 1121.628 | [11 empty] | 0 | 0
6 | Job: 6101 - Water Systems-DUDEK | 613 - Vacuum Pumping System | 49.628 | L | L | LL | 42.1838 | 62.035 | 0 | -15% | 25% | 42.1838 | 62.035 | 0 | 0 | 0
| Job: 6201 - Cryogenic Systems-DUDEK | 621 - LN2-LHe Supply System | 106.847
|  | 622 - LN2 Coil Cooling Supply | 85.764
|  | 623 - GN2 Cryostat Cooling System | 422.121
| Job: 6201 - Cryogenic Systems-DUDEK Total |  | 614.732 | L | M | LM | 491.7856 | 860.6248 | 0 | -20% | 30% | 491.7856 | 799.1516 | 0 | 0 | -61.4732
| Job: 6301 - Utility Systems-DUDEK |  | 116.634 | L | L | LL | 99.1389 | 145.7925 | 0 | -15% | 25% | 99.1389 | 145.7925 | 0 | 0 | 0
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK |  | 548.642 | L | M | LM | 438.9136 | 768.0988 | 0 | -20% | 40% | 438.9136 | 768.0988 | 0 | 0 | 0
6 Total |  |  | 1329.636
7 | Job: 7301 - Platform Design & Fab-PERRY |  | 203.23 | L | L | LL | 172.7455 | 254.0375 | 0 | -0.01% | 10% | 203.2097 | 223.553 | 0 | 30.4642 | -30.4845
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY |  | 1116.686 | L | M | LM | 893.3488 | 1563.3604 | 0 | -20% | 40% | 893.3488 | 1563.3604 | 0 | 0 | 0
| Job: 7501 - Construction Support Crew-PERRY |  | 1587.706 | M | L | ML | 1428.9354 | 1825.8619 | 0 | -0.01% | 15% | 1587.5472 | 1825.8619 | 0 | 158.6118 | 0
| Job: 7503 - Machine Assembly (station 6)-PERRY |  | 2777.799 | L | M | LM | 2222.2392 | 3888.9186 | 0 | -0.01% | 15% | 2777.5212 | 3194.4689 | 0 | 555.282 | -694.4497
| Job: 7601 - Tooling Design & Fabrication-PERRY |  | 415.69 | L | L | LL | 353.3365 | 519.6125 | 0 | -0.01% | 10% | 415.6484 | 457.259 | 0 | 62.3119 | -62.3535
7 Total |  |  | 6101.111
8 | Job: 8101 - Project Management & Control-NEILSON | FY07 Rebaseline Exercise | 4.527
1938.873
| Job: 8101 - Project Management & Control-NEILSON Total |  | 1943.4 | N/A | N/A | PM | 2915.1 | 3886.8 | 0 | 50% | 100% | 2915.1 | 3886.8 | 0 | 0 | 0
| Job: 8102 - NCSX MIE Management ORNL-LYON |  | 394.62 | N/A | N/A | PM | 591.93 | 789.24 | 0 | 50% | 100% | 591.93 | 789.24 | 0 | 0 | 0
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | FY07 Rebaseline Exercise | 30.228
1810.263
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN Total |  | 1840.491 | H | L | HL | 1748.4664 | 2024.5401 | 0 | -15% | 20% | 1564.4173 | 2208.5892 | 0 | -184.0491 | 184.0491
| Job: 8203 - Design Integration-BROWN |  | 1404.328 | H | L | HL | 1334.1116 | 1544.7608 | 0 | -15% | 20% | 1193.6788 | 1685.1936 | 0 | -140.4328 | 140.4328
| Job: 8204 - Systems Analysis-BROOKS |  | 1706.183 | H | L | HL | 1620.8738 | 1876.8013 | 0 | -15% | 20% | 1450.2556 | 2047.4196 | 0 | -170.6183 | 170.6183
| Job: 8205 - Dimensional Control Coordin-REIERSEN |  | 752.84 | H | L | HL | 715.198 | 828.124 | 0 | -15% | 20% | 639.914 | 903.408 | 0 | -75.284 | 75.284
| Job: 8210 - FY07 Rebaseling tasks | FY07 Rebaseline Exercise | 39.438 | H | L | HL | 37.4661 | 43.3818 | 0 | -15% | 20% | 33.5223 | 47.3256 | 0 | -3.9438 | 3.9438
| Job: 8215 Plant Design | FY07 Rebaseline Exercise | 134.646 | H | L | HL | 127.9137 | 148.1106 | 0 | -15% | 20% | 114.4491 | 161.5752 | 0 | -13.4646 | 13.4646
| Job: 8501 - Integrated Systems Testing-GENTILE | Startup Documentation | 346.004
411.63
| Job: 8501 - Integrated Systems Testing-GENTILE Total |  | 757.634 | H | L | HL | 719.7523 | 833.3974 | 0 | -15% | 20% | 643.9889 | 909.1608 | 0 | -75.7634 | 75.7634
| Job: 8998 - Allocations-STRYKOWSKY |  | 1016.404 | H | L | HL | 965.5838 | 1118.0444 | 0 | -5% | 15% | 965.5838 | 1168.8646 | 0 | 0 | 50.8202
8 Total |  |  | 9989.984
12 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | 227.094
|  | 124P - VV Personnel Access Port & Lateral sprts | 83.786
|  | 124T - Heater Tape for Port Stub | 19.65
|  | 124U - T/C and Heater Tape Leads | 36.047
|  | 124V - Flux loop junction boxes and spacer templates | 12.275
|  | 125 - VV Local I&C | 34.401
| Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK Total |  | 413.253 | H | L | HL | 392.5904 | 454.5783 | 0 | -0.01% | 5% | 413.2117 | 433.9156 | 0 | 20.6213 | -20.6627
12 Total |  |  | 413.253
13 | Job: 1302 - PF Design -KALISH | FY07 Rebaseline Exercise | 7.112
251.277
| Job: 1302 - PF Design -KALISH Total |  | 258.389 | L | L | LL | 219.6307 | 322.9863 | 0 | -10% | 20% | 232.5501 | 310.0668 | 0 | 12.9195 | -12.9195
| Job: 1352 - PF Coil Procurement-KALISH | PF Coil Fabrication | 1606.752 | L | L | LL | 1365.7392 | 2008.44 | 0 | -10% | 20% | 1446.0768 | 1928.1024 | 0 | 80.3376 | -80.3376
| Job: 1353 - CS Structure Procurement-DAHLGREN | CS Support Structure | 337.329 | H | L | HL | 320.4626 | 371.0619 | 0 | -0.01% | 10% | 337.2953 | 371.0619 | 0 | 16.8327 | 0
| Job: 1354 - Trim Coil Design &Procurement-KALISH | Trim Coils | 122.664 | L | L | LL | 104.2644 | 153.33 | 0 | -10% | 20% | 110.3976 | 147.1968 | 0 | 6.1332 | -6.1332
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | TF/PF Loacl I&C | 71.991 | M | L | ML | 64.7919 | 82.7896 | 0 | -20% | 20% | 57.5928 | 86.3892 | 0 | -7.1991 | 3.5996
| Job: 1361 - TF Fabrication-KALISH | FY07 Rebaseline Exercise | 1.422
|  | TF Fabrication Contract | 834.463
|  | TF Title III and Fabrication Oversight | 163.919
| Job: 1361 - TF Fabrication-KALISH Total |  | 999.804 | H | M | HM | 899.8236 | 1149.7746 | 0 | -25% | 25% | 749.853 | 1249.755 | 0 | -149.9706 | 99.9804
13 Total |  |  | 3396.929
14 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI |  | 329.745 | L | M | LM | 263.796 | 461.643 | 0 | -5% | 0% | 313.2577 | 329.745 | 0 | 49.4617 | -131.898
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER |  | 8.912 | H | L | HL | 8.4664 | 9.8032 | 0 | -5% | 10% | 8.4664 | 9.8032 | 0 | 0 | 0
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | 1.557
|  | MCDC - Blanket thermal insulation | 7.681
|  | MCDE - Top level assy models/drawings | 5.995
|  | MCDF - Analysis and closeout documentation | 54.097
|  | RBLX - FY07 Rebaseline Exercise | 1.246
|  | TCCO - Type C Design Closeout | 7.186
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON Total |  | 77.762 | M | H | MH | 62.2096 | 108.8668 | 0 | -20% | 40% | 62.2096 | 108.8668 | 0 | 0 | 0
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | IHF - Complete Design of MC Interface | 38.349
|  | IHG - Tension Tests of Bolted Joint | 72.837
|  | IHH - Bolt Shear Test at 77k | 34.561
|  | NEWP - Interface Design | 257.823
|  | RBLX - FY07 Rebaseline Exercise | 4.983
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON Total |  | 408.553 | M | H | MH | 326.8424 | 571.9742 | 0 | -20% | 40% | 326.8424 | 571.9742 | 0 | 0 | 0
| Job: 1429 - MC Interface R&D-GETTELFINGER | Coefficient of Friction (COF) | 37.711 | M | H | MH | 30.1688 | 52.7954 | 0 | -20% | 40% | 30.1688 | 52.7954 | 0 | 0 | 0
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | 16.397
|  | BUSH - Bushings | 42.143
|  | SHMS - Shims | 170.155
|  | STUD - Studs Washers Nuts | 641.024
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK Total |  | 869.719 | M | M | MM | 739.2612 | 1087.1488 | 0 | -0.01% | 20% | 869.632 | 1043.6628 | 0 | 130.3709 | -43.486
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | 203.766
|  | 1A - Station 1a/4 Casting Prep | 244.471
|  | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | 579.958
|  | 3 - Station 4-Winding Instl Chill Plates Tubing Bag | 646.331
|  | 5 - Station 5-VPI | 328.485
|  | LABR - LOE Oversight & Supervision | 709.164
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI Total |  | 2712.175 | L | H | LH | 1898.5225 | 4339.48 | 0 | -0.01% | 10% | 2711.9038 | 2983.3925 | 0 | 813.3813 | -1356.0875
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | 324.583
|  | PLTS - Punchlist Tech shop/RESA | 147.452
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI Total |  | 472.035 | M | L | ML | 424.8315 | 542.8402 | 0 | -0.01% | 10% | 471.9878 | 519.2385 | 0 | 47.1563 | -23.6017
14 Total |  |  | 4916.612
15 | Job: 1501 - Coil Structures Design-DAHLGREN |  | 177.639 | M | L | ML | 159.8751 | 204.2849 | 0 | -0.01% | 0.01% | 177.6212 | 177.6568 | 0 | 17.7461 | -26.6281
| Job: 1550 - Coil Struct. Procurement -DAHLGREN |  | 1953.295 | M | L | ML | 1757.9655 | 2246.2893 | 0 | -10% | 30% | 1757.9655 | 2539.2835 | 0 | 0 | 292.9942
15 Total |  |  | 2130.934
16 | Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | 346.184
|  | 162 - 162 - Electrical Leads | 471.374
|  | 163 - 163 - Coil Protection System | 35.587
|  | RBLX - FY07 Rebaseline Exercise | 6.229 | [11 empty] | 0 | 0
| Job: 1601 - Coil Services Design-GORANSON Total |  | 859.374 | H | L | HL | 816.4053 | 945.3114 | 0 | -5% | 10% | 816.4053 | 945.3114 | 0 | 0 | 0
16 Total |  |  | 859.374
17 | Job: 1701 - Cryostat Design-GETTLEFINGER |  | 203.577 | L | M | LM | 162.8616 | 285.0078 | 0 | -10% | 20% | 183.2193 | 244.2924 | 0 | 20.3577 | -40.7154
| Job: 1702 - Base Support Struct Design-DAHLGREN |  | 163.469 | M | L | ML | 147.1221 | 187.9894 | 0 | -0.01% | 20% | 163.4527 | 196.1628 | 0 | 16.3306 | 8.1735
| Job: 1751 - Cryostat Procurement-GETTLEFINGER |  | 316.272 | H | L | HL | 300.4584 | 347.8992 | 0 | -0.01% | 15% | 316.2404 | 363.7128 | 0 | 15.782 | 15.8136
| Job: 1752 - Base Support Proc-DAHLGREN |  | 68.082 | M | L | ML | 61.2738 | 78.2943 | 0 | -0.01% | 5% | 68.0752 | 71.4861 | 0 | 6.8014 | -6.8082
17 Total |  |  | 751.4
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA | Oversight and Supervision | 1660.338 | H | L | HL | 1577.3211 | 1826.3718 | 0 | -10% | 30% | 1494.3042 | 2158.4394 | 0 | -83.0169 | 332.0676
| Job: 1803 - FP Asy Tooling/Constrblty-BROWN | 2.00 - Station 2-Modular Coil Sub- Assembly | 0 | L | L | LL | 0 | 0 | 0 | -0.01% | 25% | 0 | 0 | 0 | 0 | 0
|  | 3.00 - Station 3-Modular Coil to VVSA Assembly | 103.182 | M | L | ML | 92.8638 | 118.6593 | 0 | -0.01% | 25% | 103.1717 | 128.9775 | 0 | 10.3079 | 10.3182
|  | 5.00 - Station 5-Final Field Period Assembly | 82.467 | M | L | ML | 74.2203 | 94.8371 | 0 | -0.01% | 25% | 82.4588 | 103.0837 | 0 | 8.2385 | 8.2467
|  | 6.00 - 6.00-Final Machine Assembly | 199.901 | M | L | ML | 179.9109 | 229.8862 | 0 | -0.01% | 25% | 199.881 | 249.8763 | 0 | 19.9701 | 19.9901
| Job: 1803 - FP Asy Tooling/Constrblty-BROWN Total |  | 385.55
| Job: 1806 - FP Assembly specs and drawings-COLE | - | 84.702
|  | 1.00 - 1.00-VV Prep Station | 10.034
|  | 2.00 - Station 2-Modular Coil Sub- Assembly | 25.658
|  | 3.00 - Station 3-Modular Coil to VVSA Assembly | 38.739
|  | 5.00 - Station 5-Final Field Period Assembly | 59.768
|  | 6.00 - 6.00-Final Machine Assembly | 92.055
| Job: 1806 - FP Assembly specs and drawings-COLE Total |  | 310.956 | M | M | MM | 78.2468 | 115.0688 | 0 | -10% | 50% | 82.8495 | 138.0825 | 0 | 4.6028 | 23.0138
| Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 451.439
|  | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 215.386
|  | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 215.386
| Job: 1815 - Field Period Assy -Station 5-VIOLA Total |  | 882.211 | H | M | HM | 793.9899 | 1014.5426 | 0 | -10% | 50% | 793.9899 | 1323.3165 | 0 | 0 | 308.7738
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General F.P. Assy support | 2681.473 | L | H | LH | 1877.0311 | 4290.3568 | 0 | -0.01% | 40% | 2681.2049 | 3754.0622 | 0 | 804.1738 | -536.2946
|  | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | 95.874 | H | M | HM | 86.2866 | 110.2551 | 0 | -30% | 10% | 67.1118 | 105.4614 | 0 | -19.1748 | -4.7937
|  | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | 133.119 | H | M | HM | 119.8071 | 153.0868 | 0 | -30% | 10% | 93.1833 | 146.4309 | 0 | -26.6238 | -6.6559
|  | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | 186.482 | H | M | HM | 167.8338 | 214.4543 | 0 | -30% | 10% | 130.5374 | 205.1302 | 0 | -37.2964 | -9.3241
|  | S1SP - Station 1-Spool pieces (3) (spacers) | 30.442 | H | M | HM | 27.3978 | 35.0083 | 0 | -30% | 10% | 21.3094 | 33.4862 | 0 | -6.0884 | -1.5221
|  | S2P1 - Station 2-Modular Coil Subassembly-FP#1 | 626.3 | L | H | LH | 438.41 | 1002.08 | 0 | -0.01% | 40% | 626.2374 | 876.82 | 0 | 187.8274 | -125.26
|  | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | 573.107 | L | H | LH | 401.1749 | 916.9712 | 0 | -0.01% | 40% | 573.0497 | 802.3498 | 0 | 171.8748 | -114.6214
|  | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | 558.901 | L | H | LH | 391.2307 | 894.2416 | 0 | -0.01% | 40% | 558.8451 | 782.4614 | 0 | 167.6144 | -111.7802
|  | S2PR - Station 2 Trials & Development | 396.154 | L | H | LH | 277.3078 | 633.8464 | 0 | -0.01% | 40% | 396.1144 | 554.6156 | 0 | 118.8066 | -79.2308
|  | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 373.026 | L | H | LH | 261.1182 | 596.8416 | 0 | -30% | 50% | 261.1182 | 559.539 | 0 | 0 | -37.3026
|  | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 209.78 | L | H | LH | 146.846 | 335.648 | 0 | -30% | 50% | 146.846 | 314.67 | 0 | 0 | -20.978
|  | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 210.109 | L | H | LH | 147.0763 | 336.1744 | 0 | -30% | 50% | 147.0763 | 315.1635 | 0 | 0 | -21.0109
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA Total |  | 6074.767
18 Total |  |  | 9313.822
19 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE |  | 1487.916 | H | L | HL | 1413.5202 | 1636.7076 | 0 | -10% | 20% | 1339.1244 | 1785.4992 | 0 | -74.3958 | 148.7916
19 Total |  |  | 1487.916
Grand Total |  |  | 45226.183 |  |  |  | 40119.6011 | 58792.4923 | 0 |  |  | 42549.4245 | 57321.6228 | 0 | 2429.8234 | -1470.8694
|  |  | 45226.183 |  |  |  | 40119.6011 | 58792.4923 |  |  |  | 42549.4245 | 57321.6228
[7 empty] | -11.29% | 30% |  |  |  | -5.919% | 26.74%
Note on E3: Christopher O. Gruber: Enter L, M or H
Note on F3: Christopher O. Gruber: Enter L, M or H
Note on D3: Christopher O. Gruber: Enter Total Estimated Cost in thousands

## Updated ETC-5-30-07
May 30,2007
Sum of TOTAL
WBS | Job | WBS4 | Total
2 | Job: 2101 - Fueling Systems-BLAMCHARD | - | 63168
| Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | 174410
2 Total |  |  | 237578
3 | Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | 23453
|  | 124V - Flux loop junction boxes and spacer templates | 58268
|  | MD2 - Modular Coil C-wound Loops | 18626
|  | MD3 - Rogowski Coils | 158313
|  | MD4 - TF and PF Co-wound Loops | 23994
| Job: 3101 - Magnetic Diagnostics-STRATTON Total |  | 282654
| Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | 25318
| Job: 3801 - Electron Beam Mapping-STRATTON | - | 250677
| Job: 3901 - Diagnostics sys Integration-STRATTON | - | 132944
3 Total |  |  | 691593
4 | Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | 123701
|  | 412 - 412 - Experimental AC Power Systems | 34881
| Job: 4101 - AC Power-RAMAKRISHNAN Total |  | 158582
| Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | 592095
| Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | 460925
|  | 442 - 442 - Kirk Key Interlocks | 83588
|  | 443 - 443 - Real Time Control Systems | 14772
|  | 444 - 444 - Instrument Systems | 216443
|  | 445 - 445 - Coil Protection Systems | 280161
| Job: 4401 - Control & Protection-RAMAKRISHNAN Total |  | 1055889
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | 211618
|  | 452 - 452 - Electrical Systems Support | 199076
|  | 453 - 453 - System Testing (PTP's) | 267153
| Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN Total |  | 677847
4 Total |  |  | 2484413
5 | Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | 144271
| Job: 5201 - I&C Systems-SICHTA | - | 196596
| Job: 5301 - Data Acquisition-SICHTA | - | 164140
| Job: 5401 - Facility Timing & Synchron.-SICHTA | - | 203111
| Job: 5501 - Real Time Control System-SICHTA | - | 129109
| Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | 221284
| Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | 63117
5 Total |  |  | 1121628
6 | Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | 49628
| Job: 6201 - Cryogenic Systems-DUDEK | 621 - 621 - LN2-LHe Supply System | 106847
|  | 622 - 622 - LN2 Coil Cooling Supply | 85764
|  | 623 - 623 - GN2 Cryostat Cooling System | 422121
| Job: 6201 - Cryogenic Systems-DUDEK Total |  | 614732
| Job: 6301 - Utility Systems-DUDEK | - | 116634
| Job: 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK | - | 548642
6 Total |  |  | 1329636
7 | Job: 7301 - Platform Design & Fab-PERRY | - | 203230
| Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | 1116686
| Job: 7501 - Construction Support Crew-PERRY | - | 1587706
| Job: 7503 - Machine Assembly (station 6)-PERRY | - | 2777799
| Job: 7601 - Tooling Design & Fabrication-PERRY | - | 415690
7 Total |  |  | 6101111
8 | Job: 8101 - Project Management & Control-NEILSON | - | 1938873
|  | RBLX - FY07 Rebaseline Exercise | 4527
| Job: 8101 - Project Management & Control-NEILSON Total |  | 1943400
| Job: 8102 - NCSX MIE Management ORNL-LYON | - | 394620
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | - | 1810263
|  | RBLX - FY07 Rebaseline Exercise | 30228
| Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN Total |  | 1840491
| Job: 8203 - Design Integration-BROWN | - | 1404328
| Job: 8204 - Systems Analysis-BROOKS | - | 1706183
| Job: 8205 - Dimensional Control Coordin-REIERSEN | - | 752840
| Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | 39438
| Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | 134646
| Job: 8501 - Integrated Systems Testing-GENTILE | - | 411630
|  | PROC - Startup Documentation | 346004
| Job: 8501 - Integrated Systems Testing-GENTILE Total |  | 757634
| Job: 8998 - Allocations-STRYKOWSKY | - | 1016404
8 Total |  |  | 9989984
12 | Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | 227094
|  | 124P - VV Personnel Access Port & Lateral sprts | 83786
|  | 124T - Heater Tape for Port Stub | 19650
|  | 124U - T/C and Heater Tape Leads | 36047
|  | 124V - Flux loop junction boxes and spacer templates | 12275
|  | 125 - VV Local I&C | 34401
| Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK Total |  | 413253
12 Total |  |  | 413253
13 | Job: 1302 - PF Design -KALISH | - | 251277
|  | RBLX - FY07 Rebaseline Exercise | 7112
| Job: 1302 - PF Design -KALISH Total |  | 258389
| Job: 1352 - PF Coil Procurement-KALISH | 13P - PF Coil Fabrication | 1606752
| Job: 1353 - CS Structure Procurement-DAHLGREN | 132A - CS Support Structure | 337329
| Job: 1354 - Trim Coil Design &Procurement-KALISH | 133 - Trim Coils | 122664
| Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 134 - TF/PF Loacl I&C | 71991
| Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | 163919
|  | 13Y - TF Fabrication Contract | 834463
|  | RBLX - FY07 Rebaseline Exercise | 1422
| Job: 1361 - TF Fabrication-KALISH Total |  | 999804
13 Total |  |  | 3396929
14 | Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | 329745
| Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | 8912
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | 1557
|  | MCDC - Blanket thermal insulation | 7681
|  | MCDE - Top level assy models/drawings | 5995
|  | MCDF - Analysis and closeout documentation | 54097
|  | RBLX - FY07 Rebaseline Exercise | 1246
|  | TCCO - Type C Design Closeout | 7186
| Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON Total |  | 77762
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON | IHF - Complete Design of MC Interface | 38349
|  | IHG - Tension Tests of Bolted Joint | 72837
|  | IHH - Bolt Shear Test at 77k | 34561
|  | NEWP - Interface Design | 257823
|  | RBLX - FY07 Rebaseline Exercise | 4983
| Job: 1421 - Mod Coil Interface Design-WILLIAMSON Total |  | 408553
| Job: 1429 - MC Interface R&D-GETTELFINGER | COF - Coefficient of Friction (COF) Tests | 37711
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | 16397
|  | BUSH - Bushings | 42143
|  | SHMS - Shims | 170155
|  | STUD - Studs Washers Nuts | 641024
| Job: 1431 - Mod. Coil Interface Hardware-DUDEK Total |  | 869719
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1 - Station 1 Post VPI | 203766
|  | 1A - Station 1a/4 Casting Prep | 244471
|  | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | 579958
|  | 3 - Station 4-Winding Instl Chill Plates Tubing Bag | 646331
|  | 5 - Station 5-VPI | 328485
|  | LABR - LOE Oversight & Supervision | 709164
| Job: 1451 - Mod Coil Winding-CHRZANOWSKI Total |  | 2712175
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLCT - Punchlist- Coil Technicians | 324583
|  | PLTS - Punchlist Tech shop/RESA | 147452
14 Total |  |  | 4916612
15 | Job: 1501 - Coil Structures Design-DAHLGREN | - | 177639
| Job: 1550 - Coil Struct. Procurement -DAHLGREN | - | 1953295
15 Total |  |  | 2130934
16 | Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | 346184
|  | 162 - 162 - Electrical Leads | 471374
|  | 163 - 163 - Coil Protection System | 35587
|  | RBLX - FY07 Rebaseline Exercise | 6229
| Job: 1601 - Coil Services Design-GORANSON Total |  | 859374
16 Total |  |  | 859374
17 | Job: 1701 - Cryostat Design-GETTLEFINGER | - | 203577
| Job: 1702 - Base Support Struct Design-DAHLGREN | - | 163469
| Job: 1751 - Cryostat Procurement-GETTLEFINGER | - | 316272
| Job: 1752 - Base Support Proc-DAHLGREN | 172 - 172 - Base Support Structure | 68082
17 Total |  |  | 751400
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | 1660338
| Job: 1803 - FP Asy Tooling/Constrblty-BROWN | 2.00 - Station 2-Modular Coil Sub- Assembly
|  | 3.00 - Station 3-Modular Coil to VVSA Assembly | 103182
|  | 5.00 - Station 5-Final Field Period Assembly | 82467
|  | 6.00 - 6.00-Final Machine Assembly | 199901
| Job: 1803 - FP Asy Tooling/Constrblty-BROWN Total |  | 385550
| Job: 1806 - FP Assembly specs and drawings-COLE | - | 84702
|  | 1.00 - 1.00-VV Prep Station | 10034
|  | 2.00 - Station 2-Modular Coil Sub- Assembly | 25658
|  | 3.00 - Station 3-Modular Coil to VVSA Assembly | 38739
|  | 5.00 - Station 5-Final Field Period Assembly | 59768
|  | 6.00 - 6.00-Final Machine Assembly | 92055
| Job: 1806 - FP Assembly specs and drawings-COLE Total |  | 310956
| Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | 451439
|  | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | 215386
|  | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | 215386
| Job: 1815 - Field Period Assy -Station 5-VIOLA Total |  | 882211
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General F.P. Assy support | 2681473
|  | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | 95874
|  | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | 133119
|  | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | 186482
|  | S1SP - Station 1-Spool pieces (3) (spacers) | 30442
|  | S2P1 - Station 2-Modular Coil Subassembly-FP#1 | 626300
|  | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | 573107
|  | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | 558901
|  | S2PR - Station 2 Trials & Development | 396154
|  | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | 373026
|  | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | 209780
|  | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | 210109
| Job:1810-Field Period Assy -Station 1 2 3 VIOLA Total |  | 6074767
18 Total |  |  | 9313822
19 | Job: 1901 - Stellarator Core Mngtt&Integr-COLE | - | 1487916
Grand Total ETC |  |  | 45226183

## Schedule Ranges
NCSX Schedule Uncertainty Model
Duration Range
Schedule Activity |  | Base Duration (mos) on Critical Path | Estimate Uncertainty | Low | High | Adjusted High | Schedule Risk Calc | Schedule Duration | Cost Risk Adder
CP and Near CP Activities
Job 1421 - Modular Coil Interface Design |  | 3 | MH | 2.4 | 4.2 | 4.2 | 0 | 0
Job 1431 - Mod. Coil Interface Hardware |  | 3 | MM | 2.55 | 3.75 | 3.75 | 0 | 0
Job 1810 - Field Period Asmbly - Station 1,2,3
| Station 2 - FP#1 | 5.6 | LH | 3.92 | 8.96 | 5.6 | 0 | 0 | 0
| Station 2 - FP#2 | 6.55 | LH | 4.585 | 10.48 | 6.55 | 0 | 0 | 0
| Station 2 - FP#3 | 6.55 | LH | 4.585 | 10.48 | 6.55 | 0 | 0 | 0
| Station 3 - FP#3 | 4.05 | LH | 2.835 | 6.48 | 5.184 | 0 | 0 | 0
Job 1815 - Field Period Asmbly - Station 5
| Sta 5 - Final FP Asmbly - FP#3 | 3.05 | HM | 2.745 | 3.5075 | 3.5075 | 0 | 0
Job 7503 - Machine Assembly (Station 6) |  | 12.2 | LM | 9.76 | 17.08 | 17.08 | 0 | 0
Job 8501 - Integrated System Testing |  | 1 | manual | 0.99 | 2 | 2 | 0 | 0
|  | 45 |  |  |  | 54.4215 |  | 0 | 0
Note: Changed uncertainty level for 8501 since stated it is LOE but dependent on schedule
| Estimated Cost per month for Schedule Stretch | 260 | thousand
Note on C10: Chris Gruber: adjusted for schedule stretch due to accommodating contingency funds within constraint
Note on C11: Chris Gruber: adjusted for schedule stretch due to accommodating contingency funds within constraint
Note on C12: Chris Gruber: adjusted for schedule stretch due to accommodating contingency funds within constraint
Note on C14: Chris Gruber: adjusted for schedule stretch due to accommodating contingency funds within constraint
Note on G9: Chris Gruber: assumes all increase accommodated by 2nd shift with added cost
Note on G10: Chris Gruber: assumes all increase accommodated by 2nd shift with added cost
Note on G11: Chris Gruber: assumes all increase accommodated by 2nd shift with added cost
Note on G12: Chris Gruber: assumes 20% reduction of high end by 2nd shift with added cost
Note on H6: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H7: Chris Gruber: Independent of Estimate Uncertainty
Note on H9: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H10: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H11: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H12: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H14: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H15: Chris Gruber: 90% Correlation with Estimate Probability Profile
Note on H16: Chris Gruber: Independent of Estimate Uncertainty

## Risk Register
NCSX Risk Register
No. | Risk Description | Contributing factors and mitigation plans | Likelihood of Occurrence a |  |  | Basis of estimate | Cost Impact ($k) |  | Schedule Impact (mos) |  | Comments
|  |  |  | Consequences | Risk Rank |  | Low | High | Low | High |  | Name | Risk Calculation |  | Cost | Schedule | Cost Cont | Sched Cont
1 | Inner leg assembly design and requirements are not finalized |  | L | Critical | H | sta 2=$925k plus 1,800k oversight,army=$2.7m and 12 mo. | -818 | 818 | -3.6 | 3.6 |  | 1- Inner Leg Assy | 0.6 | 0 | 0 | 0 | 0 | 0
2 | Additional trim coils may be required to suppress field errors from n>1 modes | Analysis being performed to firm up requirements | U | Marginal | L | 124 fab 19 install x 2 | 214.5 | 286 | 0 | 0 |  | 2- Trim Coils | 0.25 | 0 | 0 | 0 | 0 | 0
3 | Bushing number and design are not finalized |  | L | Marginal | M | +30kx 3 f/bushings $117k installation instl 4 days *18 joints/21d/m | -52 | 446.28 | -0.36972 | 0 | schedule slip mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 3 - Bushings | 0.6 | 0 | 0 | 0 | 0 | 0
4 | TF alignment may take substantially longer than expected once alignment procedure is finalized | TF alignment features not finalized and alignment procedure not yet developed | U | Significant | M | $10k and 6 days per FP | 15 | 60 | 0.42857 | 1.7143 |  | 4 - TF Alignment | 0.25 | 0 | 0 | 0 | 0 | 0
5 | Design of the inboard modular coil interfaces could take substantially longer than anticipated with attendant impact on the critical path | Design of inboard modular coil interfaces within a field period (A-A, A-B, B-C) and between field periods (C-C) not finalized. Design activity is on the critical path. | L | Significant | M | dsn etc=349k | 0 | 349 | 0 | 3 |  | 5 - Inboard Coil Interface Design | 0.6 | 0 | 0 | 0 | 0 | 0
6 | Field period assembly cost and schedule could be significantly impacted if design of the modular coil interfaces changes significantly from the baseline. | Design of inboard modular coil interfaces within a field period (A-A, A-B, B-C) not finalized. Assembly of modular coils is on the critical path. | U | Critical | M | sta 2=$925k plus 1,800k oversight,army=$2.7m and 12 mo. Sta 3 6 add'l mo. At 1.8m | 0 | 2351.6 | 0 | 0 | MC assembly activities on Stations 2 and 3. schedule slip mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 6- Field Period Assy | 0.25 | 0 | 0 | 0 | 0 | 0
7 | Final assembly cost and schedule could be significantly impacted if design of the modular coil interfaces changes significantly from the baseline. | Design of inboard modular coil interfaces between field periods (C-C) not finalized. Assembly of field periods is on the critical path. | U | Marginal | L | 13 days and 62k | 0 | 62 | 0 | 0.61905 | MC assembly activities on Station 6 (Final Assembly) (already assumed 2 shift ops) | 7- Final Assy | 0.25 | 0 | 0 | 0 | 0 | 0
8 | Support structure for final assembly may require modification to meet final assembly requirements | No development trials performed prior to completion of the first field period. Development trials could be performed on first field period without impacting the critical path. | L | Negligible | L |  | 40 | 50 | 0 | 0 |  | 8 - Support Structure | 0.6 | 0 | 0 | 0 | 0 | 0
9 | Coil alignment tolerances may be too tight to achieve in the assumed number of iterations | Development trials on A-A suggest the requirements are achievable but this has not been demonstrated on the other flanges. More recent analysis of alignment requirements suggest they might be relaxed. | U | Marginal | L | 3.5 days x 18 joints @ $11k each | -99 | 486 | -1.5 | 0 | schedule slip mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 9 - Coil Alignment Tolerances | 0.25 | 0 | 0 | 0 | 0 | 0
10 | Weld distortion may be problematic requiring signficantly more time to accomplish welding than assumed | Development trials for weld distortion and design of the welded shims are barely underway. Substantial uncertainties exist. | U | Marginal | L | 13 days x 15 joints @ $37k each | -277.5 | 434.34 | -4.6429 | -0.0042857 | schedule slip mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 10 - Weld Distortion | 0.25 | 0 | 0 | 0 | 0 | 0
11 | VV distortion due to welding may be excessive | No further development activities planned. May require more elaborate welding procedure to minimize distortion. | U | Marginal | L | 15 days @ $180k | 0 | 124.56 | 0 | -0.0028571 | schedule slip mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 11 - VV Distortion | 0.25 | 0 | 0 | 0 | 0 | 0
12 | Resource limitations for metrology, 3D modeling, and "back office" support may constrain progress and impact the schedule | Estimate currently based on 1 iteration for aligning coils. Only 2 laser trackers to monitor 3 field periods requiring leapfrogging which might compromise accuracy. Delays already seen in assembly operations. | U | Significant | M | 54days @$172k | 0 | 172 | 0 | 2.5714 |  | 12- Metrology, 3D and Back Office Support | 0.25 | 0 | 0 | 0 | 0 | 0
13 | The weld technology required to minimize distortion, e.g. MIG welding, may require special accommodations because of lack of trained PPPL personnel and equipment | MIG welding would require bringing in outside welders to assemble field periods with potentially signficant cost and schedule impacts | U | Negligible | L | assume 2 add'l welders trained by 1 PPPL over 4 months | 0 | 51.84 | 0 | 0 | Not on critical path | 13- Weld Technology | 0.25 | 0 | 0 | 0 | 0 | 0
14 | Ports may distort when welded requiring modifications to the planned weld procedure with consequent cost and schedule impacts | Development trials could be performed in advance. Welding of first ports not on critical path. | U | Negligible | L | 10 man-days | 0 | 6.48 | 0 | 0 | Not on critical path | 14 - Port Distortion | 0.25 | 0 | 0 | 0 | 0 | 0
15 | Loss or unavailability of key personnel from the project could substantially impact the schedule. | Baseline schedule predicated on continued availability of key personnel. Mitigation plans should be considered. | L | Critical | H | impacts sta 2 3,5 &6 on oversight&support crews &$151 & 79k/mo. | 834 | 1668 | 1.5 | 3 | schedule slip partially (50%)mitigated by use of 2nd shift (cost impact included@$96k/mo.) | 15 - Key Personnel Availability | 0.6 | 0 | 0 | 0 | 0 | 0
16 | Procuring the aerogel insulation (if it is not commercially available) and developing a satisfactory fill technique could have cost and schedule impacts. | Pourable aerogel insulation for service at 350C is not presently a commercially available product. The NCSX project might have to contract an outfit to burn off the volatiles from a commercially available product if 350C aerogel cannot be bought directly | VL | Negligible | L |  | 0 | 51.84 | 0 | 0 |  | 16 - Aerogel Insulation | 0.9 | 0 | 0 | 0 | 0 | 0
17 | Unanticipated problems with the cryostat and LN2 delivery system may require warming up the stellarator core to effect repair with consequent cost and schedule impacts |  | U | Marginal | L | cryostat fixes @ 229/mo. Plus 79k/mo oversight | 0 | 308 | 0 | 1 | 2 shift ops already assumed | 17 - Cryotat and LN2 System | 0.25 | 0 | 0 | 0 | 0 | 0
18 | Pervasive vacuum leaks appear following welding of the ports | Early detection and repair (which is not in the current baseline) would minimize critical path impacts | U | Significant | M | 160k/mo leakcheck plus 79k/mo oversight | 239 | 478 | 1 | 2 | 2 shift ops already assumed | 18 - Vacuum Leaks | 0.25 | 0 | 0 | 0 | 0 | 0
19 | Funding profile may not match assumptions which in turn could impact cost and schedule |  | U | Significant | M | cost factored into stretchout cost | 0 | 0 | -2 | 2 |  | 19-Funding Profile | 0.25 | 0 | 0 | 0 | 0 | 0
20 | Overhead rates may vary which in turn could impact cost and schedule |  | U | Significant | M | $42m etc | -840 | 840 | 0 | 0 |  | 20 - Pvehead Rates | 0.25 | 0 | 0 | 0 | 0 | 0
21 | Escalation of Copper higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Negligible | L | see separate sheet - assume 5% to 20% higher per year escalation rate | 11.1888 | 80.5572 | 0 | 0 |  | 21- Copper Escalation | 0.9 | 0 | 0 |  | 0
22 | Escalation of Stainless Sheet and Inconel higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Marginal | M | see separate sheet - assume 3% to 20% higher per year escalation rate | 37.0011 | 266.1648 | 0 | 0 |  | 22 - Stainless Escalation | 0.9 | 0 | 0 |  | 0
a VL= Very Likely, (P>90%) L=Likely (90%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%) | [16 empty] | 0 | 0
Note on N3: Chris Gruber: Probability of occurrence modeled as Yes-No distribution
Note on P3: Chris Gruber: Cost impact probability distribution
Note on Q3: Chris Gruber: Schedule Impact Probability Distribution
Note on R3: Chris Gruber: Product of Probability of Occurrence (yes or no) and cost impact probability profile
Note on S3: Chris Gruber: Product of Probability of Occurrence (yes or no) and schedule impact probability profile

## Risk Probability Tables
| Probability of Occurrence |  | Criteria
| Qualitative | Quantitative |  | Use Pr
VU | Very Unlikely | <0.1 | Will not likely occur anytime in the project life cycle, or the probability of the occurrence is judged to be less than 10%. | 0.05
U | Unlikely | >0.1 but <0.4 | Unlikely to occur in the project life cycle , or the probability of the occurrence is judged to be greater than 10% but less than 40%. | 0.25
L | Likely | >0.4 but <0.8 | Will likely occur sometime during the project life cycle of the project or its facilities, or the probability of the occurrence is judged to be greater than 40% but less than 80%. | 0.6
VL | Very Likely | >0.8 | Very likely to occur sometime during the project life cycle or the probability of occurrence is judged to be 80% or greater. | 0.9
* P = Probability of Occurrence
Concept Explanation
For each identified risk, a Probability of Occurrence is defined using the above criteria.
Also for each risk, the consequential impacts are estimated -- as either an absolute value or a range with most likely, low and high values defined
Both cost impacts and schedule impacts should be estimated.
For schedule impact, the value (or range) should reflect impact to the project completion -- that is the impact to the project critical path
Separate models will then be constructed to determine overall cost and schedule probability profiles (using Monte Carlo simulation)
Each risk will represent a variable in the model. The Pr of Occurrence will use the values shown on the right above and
the ranges for cost and schedule impacts.
L | 0.6
U | 0.25
VL | 0.9
VU | 0.05

## Escalation Risk
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 141-038.1 | PF Conductor Delivery |  | 95.3 |  |  |  | 95.3
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 184-037 | External Trim Coil Procurement |  |  | 33.7 |  |  | 33.7
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 64.7 | 17.8 |  | 82.5
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  | 10 |  |  | 10
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  | 45 |  |  | 45
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  | 140 |  |  | 140
|  |  |  | 0 | 95.3 | 293.4 | 17.8 | 0 | 406.5
S - Stainless Steel/Inconnel
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124-130 | VV NB port cover Fabrication |  |  | 58.5 |  |  | 58.5
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | INTRF-001 | PPPL buy SS plate for weld trials | 30 |  |  |  |  | 30
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 77.6 |  |  |  |  | 77.6
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Shim Stock | 57.1 | 3.5 |  |  |  | 60.6
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 30 |  |  |  | 30
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate TF/MCWF mounting Components |  | 371.2 | 88.4 |  |  | 459.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-038 | Fabricate PF Mounting components |  |  | 480.1 | 108.7 |  | 588.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-039 | Fabricate Final TF Assy components Components |  |  | 83.6 |  |  | 83.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-040 | Fabricate Machine/base support interface |  |  | 84.8 |  |  | 84.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 97.5 |  |  |  | 97.5
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 13.9 |  |  |  | 13.9
|  |  |  | 164.7 | 516.1 | 795.4 | 108.7 | 0 | 1584.9
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 47.65 | 146.7 | 8.9 | 0 | 203.25
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 1.4295 | 8.934 | 0.82527 | 0 | 11.1888
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 9.53 | 64.548 | 6.4792 | 0 | 80.5572
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 82.35 | 258.05 | 397.7 | 54.35 | 0 | 792.45
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 7.7415 | 24.2199 | 5.0397 | 0 | 37.0011
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 51.61 | 174.988 | 39.5668 | 0 | 266.1648