## Risk Register
No. | Job (s) | Risk Description | Mitigation Plan | Likelihood of Occurrence a | Consequences | Risk Class | Basis of Estimate | Low CI | High CI | Low SI | High SI
1 | 1806, 8203,8204 | Loss or prolonged unavailability of certain key personnel (Brown, Cole, and Brooks) from the project could substantially impact the schedule. | Baseline schedule predicated on continued availability of key personnel. Bob Ellis has been budgeted to provide support to Tom Brown in Design Integration. Mitigation plans for Cole and Brooks are still not addressed in our plans. | U | Critical | Moderate | impacts sta 2 3,5 &6 on oversight&support crews &$151 & 79k/mo. | 834 | 1668 | 1.5 | 3
2 | 1421 | Modular coil interface design needs to change significantly from the baseline for technical reasons | Task force formed to expedite resolution of feasibility issues | U | Critical | Moderate | Design of the MC interface is on the critical path. Potential impacts include [1] additional design and development (4 engineers for 2-4 months) [2] a change in the cost of field period and final assembly to a change in the design (+/- $300K) and [3] "standing army" costs for an additional 2-4 months | 0 | 800 | 2 | 4
| 1352 | Vendor damages or buiilds non-compliant coil requiring PF coil to be rebuilt. | Extra conductor purchased. Ample float provided in schedule to avoid critical path impacts. | VU | Negligible | Low | No schedule impact, but could extend PPPL Title III efforts by ~ 2 months (~$30K) | 10 | 30 | 0 | 0
3 | 1354 | Additional trim coils may be required to suppress field errors from n>1 modes | Analysis being performed to firm up requirements | U | Marginal | Low | Costs could more than double the present estimate | 150 | 300 | 0 | 0
4 | 1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. | VU | Negligible | Low | Increase PPPL Title III by 1 man-month | 10 | 30 | 0 | 0
5 | 1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound | Continue to use same process used for first twelve coils | U | Significant | Moderate | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 400 | 450 | 0 | 2
6 | 1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired | U | Negligible | Low | ~$10K for equipment plus repair costs | 10 | 30 | 0 | 0
7 | 1810 | Modular coil damaged during assembly requiring significant rework to coil | Coils will be handled during FPA using carefully constructed procedures to minimize likelihood | VU | Negligible | Low | Nominally repaired with a 2-man crew in 2 weeks | 20 | 30 | 0 | 1
8 | 1810 | VV surface component (coolant tube, flux loop, or TC) damaged during FPA requiring significant rework | Not listed on Job Sheet | VU | Negligible | Low | Nominally repaired with a 2-man crew in 1 week | 10 | 20 | 0 | 0.5
9 | 1810 | Unacceptable distortion in field period when welding modular coil shims | Not listed on Job Sheet
10 | 1810 | Field period damaged during loading, transport, and unloading from TFTR TC to NCSX TC | Not listed on Job Sheet
11 | 1810 | Field period does not fit through TC door on transporter | Not listed on Job Sheet
12 | 1810 | Field period weight exceeds crane capacity | Not listed on Job Sheet
13 | 1815 | Excessive distortion during port welding requiring cutting off and re-welding port | Close monitoring during welding will minimize likelihood | U | Negligible | Low | Nominally repaired with a 2-man crew in 2 weeks | 20 | 30 | 0 | 0
| 3101 | Hi Temp rogowski Loop damaged dring installation reaulting in loss of toroidal current measurement capability. | Tripel redundancy - 3 installed, only 1 required. | VU | Negligible | Low | 3 installed - only need 1 | +$0K | +$0K | 0 | 0
14 | 7401, 7501, 7503 | Multiple vacuum leaks appear following welding of the ports | ???. Nor listed on Job Sheet. | VU | Significant | Moderate | 160k/mo leakcheck plus 79k/mo oversight | 240 | 480 | 1 | 2
15 | 7503 | Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion | ???. Nor listed on Job Sheet.
16 | 7503 | Modular coils are shorted across toroidal break between field periods | ???. Nor listed on Job Sheet.
17 | 7503 | Coils are hooked up with incorrect polarity | ???. Nor listed on Job Sheet.
18 | 1701 | Unanticipated problems with cryostat penetrations (icing, excessive condensation) require warming up the stellarator core to effect repair with consequent impacts to critical path activities | ???. Nor listed on Job Sheet. | U | Marginal | Low | Nominally repaired with a 4-man crew in 1 week | 15 | 45 | 0.75 | 1.5
19 | 1701 | Cold mass does not cool down within 96 hours or does not cool down all the way to 77K | ???. Nor listed on Job Sheet.
20 | 1701 | Ground insulation on modular coil fails during initial cooldown | ???. Nor listed on Job Sheet.
21 | 1701 | Ground insulation on TF/PF coil fails during initial cooldown | ???. Nor listed on Job Sheet.
| ??? | GPP projects not completed in time to support proejct needs | ???. Nor listed on Job Sheet.
22 | Many | Escalation of Stainless Sheet and Inconel higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Marginal | Moderate | see separate sheet - assume 3% to 20% higher per year escalation rate | 37.0011 | 266.1648 | 0 | 0
23 | Many | Escalation of Copper higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Negligible | Low | see separate sheet - assume 5% to 20% higher per year escalation rate | 0 | 0 | 0 | 0
Other escalation rates, e.g. labor rates, are higher than budgeted
24 | NA | Funding profile may not match assumptions which in turn could impact cost and schedule |  | U | Significant | Moderate | cost factored into stretchout cost | 0 | 0 | -2 | 2
25 | NA | Overhead rates may vary which in turn could impact cost and schedule |  | U | Significant | Moderate | $42m etc | -840 | 840 | 0 | 0
a VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Sheet1
Risk Level Matrix
Likelihood | Very Likely | VL | Low | Moderate | High | High | High
| Likely | L | Low | Moderate | Moderate | High | High
| Unlikely | U | Low | Low | Moderate | Moderate | High
| Very Unlikely | VU | Low | Low | Low | Moderate | High
| Non-credible | NC | Low | Low | Low | Low | Low
|  |  | Negligible | Marginal | Significant | Critical | Crisis
Consequence
Risk Level Matrix
Likelihood | Very Likely | VL | 1 | 1
| Likely | L
| Unlikely | U | 2 | 2 | 3 | 2
| Very Unlikely | VU | 3 |  | 1
| Non-credible | NC
|  |  | Negligible | Marginal | Significant | Critical | Crisis
Consequence

## Risk Probability Tables
| Probability of Occurrence |  | Criteria
| Qualitative | Quantitative |  | Use Pr
VU | Very Unlikely | <0.1 | Will not likely occur anytime in the project life cycle, or the probability of the occurrence is judged to be less than 10%. | 0.05
U | Unlikely | >0.1 but <0.4 | Unlikely to occur in the project life cycle , or the probability of the occurrence is judged to be greater than 10% but less than 40%. | 0.25
L | Likely | >0.4 but <0.8 | Will likely occur sometime during the project life cycle of the project or its facilities, or the probability of the occurrence is judged to be greater than 40% but less than 80%. | 0.6
VL | Very Likely | >0.8 | Very likely to occur sometime during the project life cycle or the probability of occurrence is judged to be 80% or greater. | 0.9
* P = Probability of Occurrence
Concept Explanation
For each identified risk, a Probability of Occurrence is defined using the above criteria.
Also for each risk, the consequential impacts are estimated -- as either an absolute value or a range with most likely, low and high values defined
Both cost impacts and schedule impacts should be estimated.
For schedule impact, the value (or range) should reflect impact to the project completion -- that is the impact to the project critical path
Separate models will then be constructed to determine overall cost and schedule probability profiles (using Monte Carlo simulation)
Each risk will represent a variable in the model. The Pr of Occurrence will use the values shown on the right above and
the ranges for cost and schedule impacts.
L | 0.6
U | 0.25
VL | 0.9
VU | 0.05

## Escalation Risk
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 141-038.1 | PF Conductor Delivery |  | 95.3 |  |  |  | 95.3
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 184-037 | External Trim Coil Procurement |  |  | 33.7 |  |  | 33.7
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 64.7 | 17.8 |  | 82.5
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  | 10 |  |  | 10
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  | 45 |  |  | 45
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  | 140 |  |  | 140
|  |  |  | 0 | 95.3 | 293.4 | 17.8 | 0 | 406.5
S - Stainless Steel/Inconnel
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124-130 | VV NB port cover Fabrication |  |  | 58.5 |  |  | 58.5
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | INTRF-001 | PPPL buy SS plate for weld trials | 30 |  |  |  |  | 30
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 77.6 |  |  |  |  | 77.6
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Shim Stock | 57.1 | 3.5 |  |  |  | 60.6
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 30 |  |  |  | 30
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate TF/MCWF mounting Components |  | 371.2 | 88.4 |  |  | 459.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-038 | Fabricate PF Mounting components |  |  | 480.1 | 108.7 |  | 588.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-039 | Fabricate Final TF Assy components Components |  |  | 83.6 |  |  | 83.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-040 | Fabricate Machine/base support interface |  |  | 84.8 |  |  | 84.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 97.5 |  |  |  | 97.5
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 13.9 |  |  |  | 13.9
|  |  |  | 164.7 | 516.1 | 795.4 | 108.7 | 0 | 1584.9
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 47.65 | 146.7 | 8.9 | 0 | 203.25
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 1.4295 | 8.934 | 0.82527 | 0 | 11.1888
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 9.53 | 64.548 | 6.4792 | 0 | 80.5572
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 82.35 | 258.05 | 397.7 | 54.35 | 0 | 792.45
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 7.7415 | 24.2199 | 5.0397 | 0 | 37.0011
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 51.61 | 174.988 | 39.5668 | 0 | 266.1648