## Risk Register
NCSX Risk Register
[8 empty] | Cost Impact ($k) |  | Schedule Impact (mos)
No. | Job | Risk Description | Mitigation Plan | Likelihood of Occurrence a | Consequences | Risk Class | Basis of Estimate | Low CI | High CI | Low SI | High SI
1 | 1354 7503 | Additional trim coils may be required to suppress field errors from n>1 modes | Analysis being performed to firm up requirements | U | Marginal | Low | Costs could more than double the present estimate | 200 | 400 | 0 | 0
2 | 1361 | TF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil already procured. Ample float in schedule to avoid critical path impact. | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0
3 | 1352 | PF vendor produces a non-compliant coil requiring fabrication of an additional coil | Conductor for extra coil will be procured in advance and available to wind a new coil if required. Float in schedule appears adequate to avoid critical path impact. | VU | Negligible | Low | Increase PPPL Title III by ~1 man-month | 15 | 35 | 0 | 0
4 | 1421 | Modular coil interface design needs to change significantly from the baseline for unforeseen technical reasons | Task force formed to expedite resolution of feasibility issues. Development activities are underway. | VU | Critical | Moderate | Design of the MC interface is on the critical path. Potential impacts include [1] additional design and development (4 engineers for 1-2 months) plus $100K M&S and [2] a change in the cost of field period and final assembly to a change in the design (+/- $300K). | -100 | 600 | 1 | 2
5 | 1421 | As a result of the development trials for weld distortion, the welding time increases significantly above present allowance | Welding time estimates consistent with time requirements for first R&D article which appeared to have very low distortion. Risk goes away at conclusion of ongoing weld R&D. | U | Significant | Moderate | Nominal welding time may double. Estimate based on $300K/mo for FPA activities. | 0 | 600 | 0 | 2
6 | 1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound | Continue to use same rigorous process used for first 12 coils during which there were no fabrication mihaps requiring re-winding a coil | U | Significant | Moderate | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 400 | 450 | 0 | 2
7 | 1451 | Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired | U | Negligible | Low | ~$10K for equipment plus repair costs | 10 | 30 | 0 | 0
8 | 1810 7503 | "Back office" support for FPA and final assembly becomes a chronic bottleneck, stretching out the time required to complete assembly operations | Additional support budgeted for Brown, Brooks, and Ellis providing "2 deep" back office support. Should be available to mitigate peak demands once training in key skills is completed. | VU | Significant | Low | Estimated impact is <2 months on the critical path. Cost impact covers up to 2 months of FPA/final assembly. | 0 | 600 | 0 | 2
9 | 1810 | Modular coil damaged during assembly requiring significant rework to coil | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood | VU | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks | 10 | 20 | 0 | 0.5
10 | 1810 | VV surface component (coolant tube, flux loop, or TC) damaged during FPA requiring significant rework | Equipment will be handled during FPA using carefully constructed procedures to minimize likelihood | VU | Negligible | Low | Nominally repaired with a 2-man crew within 2 weeks | 10 | 20 | 0 | 0.5
11 | 1810 | Unacceptable distortion in a field period when welding modular coil shims requiring | Likelihood of occurrence is very unlikely as a result of extensive welding R&D and careful monitoring during welding. | VU | Marginal | Low | Cut apart and re-weld two coils back together. Nominally a 2.5-man crew in 12 weeks. | 25 | 35 | 0.75 | 1.25
12 | 1810 | Field period damaged during loading, transport, or unloading from TFTR TC to NCSX TC | Extreme care will be taken when transporting a field period renering this event extremely unlikely | NC | Crisis | Low | Crisis event not covered by contingency
13 | 1815 | Multiple vacuum leaks during initial pumpdown | Welds will be leak checked during FPA when leaks can be addressed without significantly impacting the critical path. Likelihood of many leaks appearing during initial pumpdown is considered extremely unlikely with this mitigation plan. | NC |  |  | Impacts of having a few leaks is covered in estimate uncertainty with present mitigation plan
14 | 7503 | Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Ring tests are performed to reveal low resistance turn-to-turn shorts at RT. | VU | Marginal | Low | Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellrator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2
15 | 7503 | Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Ring tests are performed to reveal low resistance turn-to-turn shorts at RT. | VU | Crisis | High | Crisis event not covered by contingency
16 | 7503 | Insulation on modular coil fails during initial cooldown and testing requiring in situ repair | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. | VU | Marginal | Low | Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellrator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2
17 | 7503 | Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. | VU | Crisis | High | Crisis event not covered by contingency
18 | 7503 | Unanticipated problems with cryostat penetrations (icing, excessive condensation). May require warming up the stellarator core to effect repair with consequent impacts to critical path activities. | Rapid repair materials will be on hand. | U | Marginal | Low | Nominally repaired with a 4-man crew in 1 week with 3 weeks for warmup/cooldown (if required) | 15 | 30 | 0.25 | 1
19 |  | Loss or prolonged unavailability of certain key personnel from the project could substantially impact the schedule. | See mitigation plans for individuals listed below.
| 1901 | Mike Cole (ORNL) | Brad Nelson is been budgeted (15%) on the project. Should Cole become unavailable, Nelson would step in and handle Cole's responsibiltiies until a suitable longer term solution was implemented. | VU | Marginal | Low | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | 75 | 225 | 0.25 | 0.75
| 8203 | Tom Brown (PPPL) | Bob Ellis and an EA/EM engineer have each been budgeted (30% and 40% respectively) along with a designer (50%) to provide support to Tom Brown in Design Integration during peak demands and pick up the slack for Brown if he became unavailable. | VU | Marginal | Low | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | 0 | 150 | 0 | 0.5
| 8204 | Art Brooks (PPPL) | An EA/EM engineer has been budgeted (40%) to provide support to Brooks in Systems Analysis and Technical Assurance during peak demands and pick up the slack for Brooks should he became unavailable. | VU | Marginal | Low | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | 0 | 150 | 0 | 0.5
| 8205 | Bob Ellis (PPPL) | An EA/EM engineer has been budgeted (20%) to provide support to Ellis in Dimensional Control Coordination during peak demands and pick up the slack for Ellis should he become unavailable. | VU | Marginal | Low | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | 0 | 150 | 0 | 0.5
| 1802 7401 | Mike Viola (PPPL) Erik Perry (PPPL) | Viola and Perry will be cross-trained such that each could od the other's job | VU | Marginal | Low | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | 0 | 150 | 0 | 0.5
20 | 1803 7503 | Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion | Functionality of sled will be determined first with concrete blocks and later with first FP. Ample time to make design modifications between arrival of the first and third FPs. | U | Negligible | Low | Nominal cost impact is 1 man-month of engineering design and up to half the fabrication cost of the sled | 25 | 75 | 0 | 0
21 | 7503 | TC floor is not adequately rigid for present metrology plan | Copper sheet and spongy surface removed from TC floor. Fiducials will be placed. Concrete blocks will be placed to see if floor is adequately stiff. | VU | Marginal | Low | Nominal cost impact is 2 man-months of engineering design and $50-150K for local reinforcement of building structures | 50 | 200 | 0 | 0
22 | 1421 7503 | Modular coils are shorted across toroidal break between field periods | Need very low impedence, multiple shorts to get into trouble | NC
23 | 8101 | GPP projects not completed in time to support project needs | Crane/HVAC Lab/DOE overisght Ample float | NC
24 | 8501 | Coils are hooked up with incorrect polarity | Tested during ISTP and fixed | U | Negligible | Low | Covered in estimate uncertainty with present mitigation plan
25 | 8101 | Escalation of Stainless Sheet and Inconel higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Marginal | Moderate | see separate sheet - assume 3% to 20% higher per year escalation rate | 37.0011 | 266.1648 | 0 | 0
26 | 8101 | Escalation of Copper higher than base escalation rates | Funding limits preclude early procurements to avoid escalation impacts | VL | Negligible | Low | see separate sheet - assume 5% to 20% higher per year escalation rate | 11 | 81 | 0 | 0
27 | 8101 | Labor rates may be significantly lower/higher than projected |  | L | Marginal | Moderate | Escalation rate may be anywhere in the range of 2-5% instead of the nominal rate of 3.4% for labor. Schedule impact is due to annual fundign constraints. | -500 | 500 | -0.5 | 0.5
28 | 1810 1815 7503 | Metrology equipment and general purpose tooling/ lifting equipment (e.g.cranes) not available to support the schedule | Maintenance contract mitigates impact of metrology equipment. Additional $200K budgeted for a 3rd laser tracker and/or spare metrology equipment. Should result in improved efficiency. | U | Marginal | Low | Up to 2 week impact on FPA and critical path. FPA cost impact assumed to be $300k/mo. | 0 | 150 | 0 | 0.5
29 | 1352 | No suitable PF coil vendor submits bid. PC coils need to be built in-house. | PF is last major, special procurement. Sources sought received two qualified respondants. Capability to build at PPPL exists if needed. | U | Marginal | Low | Cost impact estimated to be up to $300k (1/3 of fabrication costs) for potentially higher labor rates at PPPL. No impact on critical path expected. | 0 | 300 | 0 | 0
30 | 8101 | Funding profile may not match assumptions which in turn could impact cost and schedule |  | U | Significant | Moderate | Cost impact derived from stretchout | 0 | 0 | -2 | 2
31 | 8101 | Overhead rates may change signficiantly which in turn could impact cost and schedule |  | U | Significant | Moderate | Calculated on basis of $45M ETC | -900 | 900 | -1 | 1
a VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Likelihood
| Probability of Occurrence |  | Criteria
| Qualitative | Quantitative |  | Use Pr
VU | Very Unlikely | <0.1 | Will not likely occur anytime in the project life cycle, or the probability of the occurrence is judged to be less than 10%. | 0.05
U | Unlikely | >0.1 but <0.4 | Unlikely to occur in the project life cycle , or the probability of the occurrence is judged to be greater than 10% but less than 40%. | 0.25
L | Likely | >0.4 but <0.8 | Will likely occur sometime during the project life cycle of the project or its facilities, or the probability of the occurrence is judged to be greater than 40% but less than 80%. | 0.6
VL | Very Likely | >0.8 | Very likely to occur sometime during the project life cycle or the probability of occurrence is judged to be 80% or greater. | 0.9
* P = Probability of Occurrence
Concept Explanation
For each identified risk, a Probability of Occurrence is defined using the above criteria.
Also for each risk, the consequential impacts are estimated -- as either an absolute value or a range with most likely, low and high values defined
Both cost impacts and schedule impacts should be estimated.
For schedule impact, the value (or range) should reflect impact to the project completion -- that is the impact to the project critical path
Separate models will then be constructed to determine overall cost and schedule probability profiles (using Monte Carlo simulation)
Each risk will represent a variable in the model. The Pr of Occurrence will use the values shown on the right above and
the ranges for cost and schedule impacts.

## Risk Level Matrix
Risk Level Matrix
Likelihood | Very Likely | VL | Low | Moderate | High | High | High
| Likely | L | Low | Moderate | Moderate | High | High
| Unlikely | U | Low | Low | Moderate | Moderate | High
| Very Unlikely | VU | Low | Low | Low | Moderate | High
| Non-credible | NC | Low | Low | Low | Low | Low
|  |  | Negligible | Marginal | Significant | Critical | Crisis
Consequence
Risk Level Matrix
Likelihood | Very Likely | VL | 1 | 1
| Likely | L
| Unlikely | U | 2 | 2 | 3 | 2
| Very Unlikely | VU | 3 |  | 1
| Non-credible | NC
|  |  | Negligible | Marginal | Significant | Critical | Crisis
Consequence

## Escalation Risk
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 141-038.1 | PF Conductor Delivery |  | 95.3 |  |  |  | 95.3
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 184-037 | External Trim Coil Procurement |  |  | 33.7 |  |  | 33.7
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 64.7 | 17.8 |  | 82.5
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  | 10 |  |  | 10
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  | 45 |  |  | 45
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  | 140 |  |  | 140
|  |  |  | 0 | 95.3 | 293.4 | 17.8 | 0 | 406.5
S - Stainless Steel/Inconnel
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124-130 | VV NB port cover Fabrication |  |  | 58.5 |  |  | 58.5
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | INTRF-001 | PPPL buy SS plate for weld trials | 30 |  |  |  |  | 30
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 77.6 |  |  |  |  | 77.6
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Shim Stock | 57.1 | 3.5 |  |  |  | 60.6
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 30 |  |  |  | 30
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate TF/MCWF mounting Components |  | 371.2 | 88.4 |  |  | 459.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-038 | Fabricate PF Mounting components |  |  | 480.1 | 108.7 |  | 588.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-039 | Fabricate Final TF Assy components Components |  |  | 83.6 |  |  | 83.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-040 | Fabricate Machine/base support interface |  |  | 84.8 |  |  | 84.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 97.5 |  |  |  | 97.5
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 13.9 |  |  |  | 13.9
|  |  |  | 164.7 | 516.1 | 795.4 | 108.7 | 0 | 1584.9
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 47.65 | 146.7 | 8.9 | 0 | 203.25
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 1.4295 | 8.934 | 0.82527 | 0 | 11.1888
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 9.53 | 64.548 | 6.4792 | 0 | 80.5572
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 82.35 | 258.05 | 397.7 | 54.35 | 0 | 792.45
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 7.7415 | 24.2199 | 5.0397 | 0 | 37.0011
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 51.61 | 174.988 | 39.5668 | 0 | 266.1648