## Table III - Fab & Assy
WBS Number: 185
WBS Title: Assembly of Field Periods
Job Numbers: 1802, 1810, and 1815
Job Title: FPA Oversight & Support (1802)
Job Title: FPA Operations - Stations 1, 2, & 3 (1810)
Job Title: FPA Operations - Station 5 (1815)
Job Manager: Mike Viola
Fabrication and Assembly
Assumptions:
Assumes 5 day workweek 1 shift no overtime
Parallel ops for sta 5 (2 fixtures available)
Parallel ops for sta 5 (2 fixtures available)
Only 1 fixture for station 3 only one shift
Parallel ops for sta 2
| Reflects rls plan rev 6 |  | K$ |  |  |  | Hours
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Estimate based on recent NCSX FPA activities and the amount of oversight and supervision that is required, adjusted by recognition of complexity of work remaining.
Job 1802
Oversight & Supervision
| Metrology Engineering Supervision FY07 raftopolous 50% | 181 | [7 empty] | 431.5 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY08 raftopolous 50% | 362 | [7 empty] | 863 |  |  |  |  | this is LOE adjust consistent with overall schedule
| Metrology Engineering Supervision FY09 raftopolous 50% (6 months???tbd | 181 | [7 empty] | 431.5 |  |  |  |  | assume sta5 finishes March 2009
| PPPL EM LOE FY07 Viola 100% | 181 | [7 empty] | 863 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY08 Viola 100% | 362 | [7 empty] | 1726 |  |  |  |  | this is LOE adjust consistent with overall schedule
| PPPL EM LOE FY09 Viola 100% (6 months???tbd) | 181 | [7 empty] | 863 |  |  |  |  | assume sta5 finishes March 2009
| Title III field period assembly FY07 ORNL suppor cole,goranson,williamson 65% total | 181 | [5 empty] | 561.5 | [6 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
| Title III field period assembly FY08 ORNL suppor cole, goranson,williamson 33%total | 181 | [5 empty] | 562 | [6 empty] | this is LOE adjust consistent with overall schedule awaiting estimate from Mike Cole
| Title III field period assembly FY07 & FY08 Support @ 40hr/month + travel (assume 10 months) - PJ Fogarty |  |  |  |  | 25 |  | 400
| HP Coverage in the TFTR TC LOE FY07@.75 fte | 181 | [6 empty] | 647.25 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY08 @.75 fte | 362 | [6 empty] | 1294.5 | [5 empty] | this is LOE thru stat3 only
| HP Coverage in the TFTR TC LOE FY09 @.75 fte (6 months???tbd) | 181 | [6 empty] | 647.25 | [5 empty] | assume sta5 finishes March 2009
Station 2-Modular Coil Sub- Assembly
Sequence Plan (Brown) - Covered in Job 1803
Systems Analysis (Brooks) - covered in Job 8204
Metrology Plan (Elllis) - Covered in Job 8205
| Procedures written & approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 2
| Pre-job brief completed | 1
Station 2 operational
Station 3-Modular Coil to VVSA Assembly
Sequence Plan (Brown) - Covered in Job 1803
Systems Analysis (Brooks) - covered in Job 8204
Metrology Plan (Elllis) - Covered in Job 8205
| Procedures approved | 10
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 6
| Pre-job brief completed | 6
| Station 3 operational | 1
| Fixtures installed | 6
Station 5-Final Field Period Assembly
Sequence Plan (Brown) - Covered in Job 1803
Systems Analysis (Brooks) - covered in Job 8204
Metrology Plan (Elllis) - Covered in Job 8205
| Procedures approved | 14
| JHA completed | 6
| Training needs identified & released | 6
| ACC review completed | 7
| Pre-job brief completed | 7
| Station 5 operational | 1
Job: 1802 - FP Assy Oversight&Support-VIOLA Total |  |  | 0 | 0 | 0 | 25 | 0 | 1523.5 | 2589 | 5178 | 0 | 0 | 0
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Job: 1810 - Field Period Assembly-VIOLA
Station 1: Based on actual VV #1 costs - almost completed.
Station 2: Based on actual VV #1 costs - almost completed.
Based on experience to accomplish similar tasks (e.g., metrology scans/lock-ins, coil trial fitups, gross checks)
Nose/Bushing related items based on conceptual designs and rough estimates
Assumed nose concept based on application of epoxy & set-up times
Station 3: Setup and Metrology estimates based on conceptual designs tempered with experieince in alignment of multiple components (half field periods and screens proof-of principle tests)
General F.P. Assy support
| LOE Crane support, fixture setupfor TFTR TC. FY07 1.2 fte | 181 | [10 empty] | 1035.6 |  | 2 men 3 day a week .LOE adjust consistent with schedule
| LOE Crane support, fixture setupfor TFTR TC. FY08 1.2 fte | 362 | [10 empty] | 2071.2 |  | 2 men 3 day a week .LOE adjust consistent with schedule
| LOE Crane support, fixture setupfor TFTR TC. FY09 1.2 fte (6 months???tbd) | [13 empty] | assume sta5 finishes March 2009
| LOE Field Supervision for TFTR TC FY07 edwards | 181 | [8 empty] | 863 |  |  |  | this is LOE adjust consistent with overall schedule
| LOE Field Supervision for TFTR TC FY08 edwards | 362 | [8 empty] | 1726 |  |  |  | this is LOE adjust consistent with overall schedule
| LOE Field Supervision for TFTR TC FY09 edwards(6 months???tbd) | 181 | [8 empty] | 863 |  |  |  | assume sta5 finishes March 2009
| LOE Metrology support FY07 1.5 fte engr plus ducco 100% | 181 | [5 empty] | 1294.5 |  |  |  |  | 863 |  | this is LOE adjust consistent with overall schedule
| LOE Metrology support FY08 1.5 fte engr plus ducco 100% | 362 | [5 empty] | 2589 |  |  |  |  | 1726 |  | this is LOE adjust consistent with overall schedule
| LOE Metrology support FY09 1.5 fte engr plus ducco 100% (6 months???tbd) | 181 | [5 empty] | 1294.5 |  |  |  |  | 863 |  | assume sta5 finishes March 2009
| Misc M&S FY07 | 181 | 18 | [11 empty] | 3K/month
| Misc M&S FY08 | 362 | 36 | [11 empty] | 3K/month
| Misc M&S FY09 (6 months???tbd) | 181 | 18 | [11 empty] | assume sta5 finishes March 2009
Station 1-FP #1 VV Prep (hard surface components)
| Layout diagnostic&coolant paths on vessel - Completed | 35
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs for coolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5
| Verify installation of local I&C | 2
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #2 VV Prep (hrd surf cmpnts)
| Misc Hardware - Completed |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12
| Install heater tape on vertical ports - Completed | 7
| Verify installation of heater tapes - Completed | 1
| Attach studs forcoolant lines - Completed | 3
| Wind magnetic diagnostic sensors - Completed | 14
| Install precision magnetic diagnostic sensors - Completed | 3
| Verify installation magnetic diagnostic sensors - Completed | 4
| Install local I&C (incl thermocouples) - Completed | 5 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C - Completed | 2 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1- FP #3 VV Prep (hrd surf cmpnts)
| Misc Hardware |  | 2
| Layout diagnostic&coolant paths on vessel - Completed | 12
| Install heater tape on vertical ports - Completed | 7 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation of heater tapes - Completed | 1 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Attach studs for coolant lines - Completed | 3 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Wind magnetic diagnostic sensors - Completed | 14 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install precision magnetic diagnostic sensors - Completed | 3 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Verify installation magnetic diagnostic sensors - Completed | 4 | [12 empty] | serial tasks alternating between FPA constant 2.5 men
| Install local I&C (incl thermocouples) | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify installation of local I&C | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install cooling/htg lines to vac vsl | 15 | [10 empty] | 300 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Weld cooling/htg risers | 10 | 2 | [9 empty] | 200 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Verify Instl of H/C lines,headers,manifolds | 5 | [10 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Perform final acceptance testing (H/C flow test) | 5 | 4 | [9 empty] | 100 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Trim seal plates | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Loop termination & verification | 18 | [10 empty] | 360 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install Final Internal and External monuments and measure | 4 | [10 empty] | 80 | 2.5
| Final Scan | 4 | [10 empty] | 80 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Install heater tape on removeable ports | 6 | [10 empty] | 120 | 2.5 | serial tasks alternating between FPA constant 2.5 men
| Prepare and transfer completed VV to holding are | 2 | [10 empty] | 40 | 2.5 | serial tasks alternating between FPA constant 2.5 men
Station 1-Spool pieces (3) (spacers)
| Attach diagnostics, studs and coolant lines | 17 | [10 empty] | 340 | 2.5
| install Final Internal and External monuments and measure | 2 | [10 empty] | 40 | 2.5
Station 2 Trials & Setup
| Trial tensioning test on prototype | 2 | 3 | [9 empty] | 40 | 2.5
| Trial bushing and shim test on prototype | 12 | 2 | [9 empty] | 240 | 2.5
| Guidance f/post-VPI proced to include measuremen | 36 | [10 empty] | 0 | 0
| Perform trial x-y-z alignments on A1-A2. | 7 | 2 | [9 empty] | 140 | 2.5
| Perform developmental trials on A1-A2. | 30 | 2 | [9 empty] | 600 | 2.5
| Alignment mechanisms, metro equipt &positioning | 6 | 40 | [9 empty] | 120 | 2.5
| Procure alignment mechanisms, fiducials, lifting | 20 | 25 | [9 empty] | 400 | 2.5
| Develop procedures for torquing bolts | 4 | [10 empty] | 80 | 2.5
| Determine fiducial types&locations | 11 | 2 | [9 empty] | 220 | 2.5
| Procure monuments&related metrology equipment | 15 | 15 | [9 empty] | 300 | 2.5
| Tools&tooling available for FPA operations | [11 empty] | 0 | 2.5
| Hardware rework (1/2 FTE) | 120 | 10 | [9 empty] | 960 | 1
| Install FIRST Holding 20 deg fixture | 4 | 2 | [9 empty] | 80 | 2.5
| Install SECOND Holding 20 deg fixture | 3 | 2 | [9 empty] | 60 | 2.5
| Install THIRD Holding 20 deg fixture | 6 | 2 | [9 empty] | 120 | 2.5
| Install LAST Holding 20 deg fixture | 3 | 2 | [9 empty] | 60 | 2.5
Station 2-Modular Coil Subassembly-FP#1
| Misc Hardware |  | 5
| Test out equipt & procedures | 7 | [10 empty] | 140 | 2.5
| Receive drawings and hardware (shims and bolts) | 7 | [10 empty] | 140 | 2.5
| Remeasure Type A "A" flange | 2.5 | [10 empty] | 50 | 2.5
| Begin A1/B1/C1 | 1 | [10 empty] | 20 | 2.5
| Pre-fit & install alignment tooling A1-A2 | 4 | [10 empty] | 80 | 2.5
| Align A1-A2 | 2 | [10 empty] | 40 | 2.5
| Install studs | 0.5 | [10 empty] | 10 | 2.5
| Install shims | 1 | [10 empty] | 20 | 2.5
| Measure and Drill Bushings | 0.5 | [10 empty] | 10 | 2.5
| Install Bushings | 2 | [10 empty] | 40 | 2.5
| Tension | 1 | 25 | [9 empty] | 40 | 5
| Weld nose | 20 | 15 | [9 empty] | 40 | 2.5
| Verify alignment A1-A2 | 2 | [10 empty] | 40 | 2.5
| De Tension | 1 | [10 empty] | 40 | 5
| Adjust Nose shims | 0 | [10 empty] | 0
| Adjust shims | 1 | [10 empty] | 20 | 2.5
| Adjust Bushings | 1 | [10 empty] | 10 | 2.5
| Re Tension | 1 | [10 empty] | 40 | 5
| Verify alignment A1-A2 | 2 | [10 empty] | 40 | 2.5
| De -Tension | 1 | [10 empty] | 20 | 2.5
| Pre-fit C1-C5 | 7 | [10 empty] | 224 | 4
| Begin 3 pack A1/B1/C1 Install A1 | 3 | [10 empty] | 60 | 2.5
| Fit A1-B1 | 22 | [10 empty] | 490 | 2.8
| Fit B1-C1 | 35 | [10 empty] | 490 | 2.8
| Verify Align Mod-Coils A1/B1/C1 | 5 | [10 empty] | 100 | 2.5
| Pre-fit C2-C3 | 7 | [10 empty] | 224 | 4
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A2-B2 | 22 | [10 empty] | 490 | 2.8
| Fit B2-C2 | 22 | [10 empty] | 490 | 2.8
| Verify Align Mod-Coils A2/B2/C2 | 5 | [10 empty] | 100 | 2.5
Station 2-Modular Coil Subassembly-FP#2
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A3/A4 | 22 | [10 empty] | 490 | 2.8
| Assemble/Align Mod-Coils A3/B3/C3 | 49 | [10 empty] | 1080 | 2.8
| Pre-fit C6-C4 | 7 | [10 empty] | 224 | 4
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Assemble/Align Mod-Coils A4/B4/C4 | 49 | [10 empty] | 1080 | 2.8
Station 2-Modular Coil Subassembly-FP#3
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Fit A5/A6 | 22 | [10 empty] | 490 | 2.8
| Assemble/Align Mod-Coils A5/B5/C5 | 49 | [10 empty] | 1080 | 2.8
| Re-measure Type A"A" flange | 2.5 | [10 empty] | 50 | 2.5
| Assemble/Align Mod-Coils A6/B6/C6 | 49 | [10 empty] | 1080 | 2.8
Station 3-Assemble Mod Coils and VVSA-FP#1
| Misc Hardware |  | 5
| Procure and load test 3 legged actuator System | 4 | 43 | [9 empty] | 96 | 3
| Procure, Fabricate and load test 3 legged actuator Lift Fixture | 8 | 6 | [9 empty] | 128 | 2
| Begin Assembly of First Field Period Assy | 2 | [10 empty] | 40 | 2.5
| Fab new legs | 4 | [10 empty] | 64 | 2
| Install station 3 platforms (8 required) | 4 | 10 | [9 empty] | 112 | 3.5
| Pre-installation set-up (Steps 1.x) | 7 | [10 empty] | 180 | 3.21
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Test out station 3 equipment and procedures | 4 | 10 | [9 empty] | 80 | 2.5
Assemble/Disassemble abc1-abc2 (stage 3 fixture)
| VV to MC turning fixt base; metr check | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV&locate sens | 2 | [10 empty] | 40 | 2.5
| Mount MC on crane; perform metr checks | 4 | 8 | [9 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to sprt sys and recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 40 | [10 empty] | 800 | 2.5
| Perform final metrology position check | 2 | [10 empty] | 40 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 5 | [10 empty] | 100 | 2.5
| Prepare Field Period for shipment | 5 | [10 empty] | 100 | 2.5
| Transfer completed assy to C-site test cell | 5 | [10 empty] | 200 | 5
Station 3-Assemble Mod Coils and VVSA-FP#2
| Assemble/Disassemble abc -abc4 (stage 3 fixture) | 4
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Mount VV to MC turning fixt base; metr check (Steps 5x) | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV & locate sens (Stes 6.01) | 1 | [10 empty] | 20 | 2.5
| Mount MC on crane; perform metr checks | 4 | [10 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to supt sys and recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 35 | [10 empty] | 700 | 2.5
| Perform final metrology position check | 3 | [10 empty] | 60 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 2 | [10 empty] | 40 | 2.5
| Prepare Field Period for shipment | 2 | [10 empty] | 64 | 4
| Transfer completed assy to C-site test cell | 1 | [10 empty] | 48 | 6
Station 3-Assemble Mod Coils and VVSA-FP#3
| Assemble/Disassemble abc -abc6 (Stage 3 fixture) | 3
| Pre-assemblies left MCHP (Steps 2.x) | 7 | [10 empty] | 140 | 2.5
| Pre-assembliess right MHCP (Steps 3.x) | 7 | [10 empty] | 130 | 2.5
| Install and align station 3 screens (Steps 4.x) | 5 | 2 | [9 empty] | 100 | 2.5
| Mount VV to MC turning fixt base; metr check (Steps 5x) | 3 | [10 empty] | 60 | 2.5
| Attach local protective strips to VV & locate sens (Stes 6.01) | 1 | [10 empty] | 20 | 2.5
| Mount MC on crane; perform metr checks | 4 | [10 empty] | 80 | 2.5
| Rotate right MC to stand-off position&chk | 3 | [10 empty] | 60 | 2.5
| Transfer load to supt sysand recheck position | 3 | [10 empty] | 60 | 2.5
| Move MC turning fixt; mount MC on crane | 3 | [10 empty] | 60 | 2.5
| Rotate left MC to stand-off position and check p | 3 | [10 empty] | 60 | 2.5
| Move left & right MC to final position & measure | 2 | [10 empty] | 40 | 2.5
| Bolt together at flange interface. | 35 | [10 empty] | 700 | 2.5
| Perform final metrology position check | 3 | [10 empty] | 60 | 2.5
| Remove temp interference strips&sensors | 1 | [10 empty] | 20 | 2.5
| Secure VV to MC's using temporary supports. | 2 | [10 empty] | 40 | 2.5
| Prepare Field Period for shipment | 2 | [10 empty] | 64 | 4
| Transfer completed assy to C-site test cell | 1 | [10 empty] | 48 | 6
Job: 1810 - Field Period Assembly-VIOLA |  |  | 336 | 0 | 0 | 0 | 0 | 5178 | 0 | 0 | 3452 | 0 | 30314.8
| TASK DESCRIPTION | Work days | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM/DSN | SHTB | EMEM | EMSM | EMSB | EMTB | CREW | Basis of Estimate
Based on quotes from PPPL Tech Shop based on similar tasks, tempered (adjusted) for complexity of having to do all welds from inside of the vessel.
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA
Station 5- Final FP Assy -FP#1 (in NCSX TC)
| metrology network | 10 | 7 | [9 empty] | 160
| Bolt on 2 Port Extensions needed for first Plasma diagnostics | 1 | [10 empty] | 16 | 2 | 10" ports provided by WBS 38
| MTM NCR Hardware repurchase (bolt kits & cover plates) |  | 42
| Weld Wire & weld supples |  | 15
| Testout Sta 5 equipt & procedures | 5 | [10 empty] | 160 | 4
| Check 3 sled interfaces adjust holes | 12 | [10 empty] | 384 | 4
| Fixtures installed - final metrology | 6 | [10 empty] | 192 | 4
| Install on support platform | 15 | 12 | [9 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 8 | [10 empty] | 160 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#2 (in NCSX TC)
| Install on support platform | 15 | [10 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 6 | [10 empty] | 120 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Station 5- Final FP Assy -FP#3 (in NCSX TC)
| Install on support platform | 15 | [10 empty] | 600 | 5
| Mount MC/VV assembly to support frame a | 2 | [10 empty] | 40 | 2.5
| Position and weld all ports to VV*2 shift* | 30 | [10 empty] | 600 | 2.5
| Inspect Welds | 4 | [10 empty] | 80 | 2.5
| Assemble left TF Coil Assembly check position | 8 | [10 empty] | 256 | 4
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Assemble right TF Coil Assembly chk position | 8 | [10 empty] | 256 | 4
| Attach TF coils to MC's | 4 | [10 empty] | 80 | 2.5
| Align TF Coils | 6 | [10 empty] | 120 | 2.5
| Change platforms | 1 | [10 empty] | 20 | 2.5
| Position, tack-weld only two large horizontal diag ports (port 4's) | 8 | [10 empty] | 160 | 2.5
Assemble external trim coils (in wbs75)
Close up VV, leak check
| Adjust final support base interfaces | 8 | [10 empty] | 160 | 2.5
| Final metrology outside & inside | 10 | [10 empty] | 200 | 2.5
| Last field period assembled | 1 | [10 empty] | 20 | 2.5
| Lift onto Station 6 assembly structure | 1 | [10 empty] | 20 | 2.5
Job:1810 - Field Period Assembly-VIOLA Total | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Job: 1815 - Field Period Assembly Station 5 (in NCSX TC)-VIOLA |  |  | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8808
HP Techs EMEM???
Is this in Job 1805?
What is this?
Is this in Job 1805?

## Table III - FabAssy & Instl
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
In-house Fabrication and Assembly and Installation
Job 7501 - Construction Support Crew | [11 empty] | Basis of Estimate
|  | K$ | Hours | [5 empty] | Duration in Shifts | Persons per Shift | Assumptions | Note: final designs not yet available - estimates based on conceptual information from others
Description of Task | ACT | M&S | EAEM | Metrology | EMEM | EMSM | EMTB | ORNL
LOE Construction Support Crew during machine assy | 7501-05 |  |  |  |  | 3128.375 | 8342.3333 |  | 220 | 2.75 | crane/fork lift operator, rigger, tool crib (75%) 29 month duration | NSTX assembly
ORNL Title III Support of Machine Assembly
Fabricate assembly structure |  | 80 |  |  | 96 | 240 | 960 |  | 20 | 6 | Design by WBS 1803 | Fabrications for TFTR and NSTX
Exercise assembly structure with FPA-1 before start of assembly |  |  |  | 320 | 80 | 320 | 640 |  | 40 |  | Review requested 8 weeks of trial runs/metrology | TFTR and NSTX
Total Job 7501 |  | 80 | 0 | 320 | 176 | 3688.375 | 9942.3333
Job 7503 - Construction Support Crew | [11 empty] | Basis of Estimate
|  | K$ | Hours | [5 empty] | Duration in Shifts | Persons per Shift | Assumptions | Note: final designs not yet available - estimates based on conceptual information from others
Description of Task | ACT | M&S | EAEM | Metrology | EMEM | EMSM | EMTB
Install Permanent Base Plates/Columns | 7503-020 |  | 60 |  |  | 120 | 480 |  | 10 | 6 |  | TFTR and NSTX assembly
Install temp assembly structure |  |  |  |  | 72 | 180 | 720 |  | 15 | 6 |  | TFTR and NSTX assembly
Install Lower PF 4,5&6 into prelim position | 7503-060 |  |  |  |  | 16 | 32 |  | 1 | 4 |  | TFTR and NSTX assembly
Install 3 Spool Pieces on fixt & test movement | 7503-070 |  | 40 | 80 |  | 80 | 320 |  | 10 | 4 |  | TFTR and NSTX assembly
FPA-1 Installed on temp assembly sleds | 7503-080 | [10 empty] | TFTR and NSTX assembly
FPA-2 Installed on temp assembly sleds | 7503-110 | [10 empty] | TFTR and NSTX assembly
FPA-3 Installed on temp assembly sleds | 7503-150 | [10 empty] | TFTR and NSTX assembly
Test movement of FPAs & position checks. | 7503-120 |  | 20 | 40 |  | 40 | 160 |  | 5 | 4 |  | TFTR and NSTX assembly
MC Shims |  | 36 | 60 |  | 86 | 216 | 864 |  | 18 | 6 | shims provided by others; M&S for final sizing | TFTR and NSTX assembly
Install inboard and outboard shims | [11 empty] | TFTR and NSTX assembly
Move all FPAs together, check fitup, tack shims | [11 empty] | TFTR and NSTX assembly
Weld inboard shims on mating flanges | [11 empty] | TFTR and NSTX assembly
Install end TF coils |  |  |  | 48 |  | 48 | 192 |  | 6 | 4 |  | TFTR and NSTX assembly
Install spacer supports and spacers | [5 empty] | 16 | 64 |  | 2 | 4 |  | TFTR and NSTX assembly
Move FPAs & spacers together & check fitup | [5 empty] | 48 | 192 |  | 6 | 4 |  | TFTR and NSTX assembly
Remove spacers and machine to fit | [6 empty] | 64 |  | 4 | 2 |  | TFTR and NSTX assembly
Re-install spacers | [5 empty] | 16 | 64 |  | 2 | 4 |  | TFTR and NSTX assembly
Position all FPA's / Spool Pieces @ MC Interface | 7503-160 |  | 24 | 48 |  | 48 | 192 |  | 6 | 4 |  | TFTR and NSTX assembly
Install local Platforms around FPA-1 | 7503-090 |  | 0 |  |  | 32 | 128 |  | 4 | 4 |  | TFTR and NSTX assembly
Install local Platforms around FPA-2 | 7503-130 |  | 0 |  |  | 32 | 128 |  | 4 | 4 |  | TFTR and NSTX assembly
Install local Platforms around FPA-3 | 7503-190 |  | 0 |  |  | 32 | 128 |  | 4 | 4 |  | TFTR and NSTX assembly
MC Interfaces: measure holes and mark bushings for eccentric drilling | [5 empty] | 24 | 96 |  | 3 | 4 | Field Period Assembly will fab and install all bushings except at three MC interfaces … at each of these 3 interfaces only 32 bushings will be fabricated during final assembly: 32 x 3 = 96 … 1 mh to measure and mark one bushing | TFTR and NSTX assembly
MC Interfaces: drill eccentric custom holes in bushings |  | 6.048 |  |  |  | 24 | 96 |  | 3 | 4 | 96 bushings x 1/8 day to set up and drill each bushing with a one man crew, four crews; M&S for consumeable tools at $63 per bushing | TFTR and NSTX assembly
Measure vessel gaps to determine spool piece dimensions |  |  | 288 | 288 |  |  |  |  | 18 | 2 |  | TFTR and NSTX assembly
Initial machining of spool pieces (complete one side) |  | 45 |  |  | 12 |  |  |  | 45 |  | Spool pieces must go outside for machining | TFTR and NSTX assembly
Final machining of spool pieces |  | 45 |  |  | 12 |  |  |  | 45 |  | Spool pieces must go outside for machining | TFTR and NSTX assembly
MC Interfaces: bolt together |  |  |  |  | 29 | 72 | 288 |  | 36 | 6 | all materials provided by others | TFTR and NSTX assembly
Raise permanent supports to take machine loads |  |  |  | 180 | 72 | 180 | 720 |  | 15 | 6 |  | TFTR and NSTX assembly
Remove temporary assembly structure | [5 empty] | 24 | 96 |  | 2 | 6 |  | TFTR and NSTX assembly
Install/Level FPA's and Spool Piece supports | 7503-030 |  | 120 | 240 |  | 240 | 960 |  | 30 | 4 |  | TFTR and NSTX assembly
FPA Metrology Checks to Assure Alignment | 7503-170 |  | 40 | 40 |  |  | 40 |  | 5 | 1 |  | TFTR and NSTX assembly
Mate-up and weld all VV-to-Spool interfaces | 7503-200 |  |  | 180 |  | 240 | 1440 |  | 30 | 3 | Weld time doubled to account for expected significant flange mismatch .. Can only use one welder/pedalman/safety watch at a time … assume two shifts | TFTR and NSTX assembly
Weld on port 4's |  |  |  | 60 |  | 180 | 720 |  | 30 | 3 | 6 ports | TFTR and NSTX assembly
Install e-beam mapping equipment |  |  |  |  | 40 | 80 | 320 |  | 10 | 4 | EWDA | TFTR and NSTX assembly
Install vacuum pumping system | 7503-240 |  |  |  |  | 40 | 160 |  | 5 | 4 |  | TFTR and NSTX assembly
Pumpdown & leak check VV | 7503-260 |  |  |  |  | 120 | 480 |  | 15 | 4 |  | TFTR and NSTX operations
Fit-up all TF coils | 7503-210 |  | 40 | 200 |  | 200 | 800 |  | 25 | 4 |  | TFTR and NSTX assembly
Install TF alignment and traction ring | [11 empty] | TFTR and NSTX assembly
Pull TF coils radially inward & verify nose fir-up | [11 empty] | TFTR and NSTX assembly
Lock TF coils at four support locations | [11 empty] | TFTR and NSTX assembly
Install MC structure insulation boots | 7503-240.1 |  |  |  |  | 80 | 320 |  | 10 | 4 | EWDA | TFTR and NSTX assembly
Seal gaps in MC shims, cooling tubes, etc for insul pour | [5 empty] | 160 | 640 |  | 20 | 4 |  | TFTR and NSTX assembly
Fill MC/VVSA annulus with pourable Aerogel insulation | 7503-240.2 |  |  |  |  | 16 | 64 |  | 2 | 4 |  | TFTR and NSTX assembly
Install trim coils | 7503-290A |  | 16 |  |  | 32 | 128 |  | 4 | 4 |  | TFTR and NSTX assembly
Install LN2 manifolds | [5 empty] | 80 | 320 |  | 10 | 4 | Fabrication by WBS 161; instl EWDA | TFTR and NSTX assembly
Complete Elect Pwr connections | 7503-320 |  |  |  |  | 160 | 960 |  | 30 | 4 | Provided by WBS 162; instl EWDA | TFTR and NSTX assembly
Install in-cryostat cabling for electric power to coils | [11 empty] | TFTR and NSTX assembly
Connect cabling and I&C to MC and TF coils | [11 empty] | TFTR and NSTX assembly
Complete mag diag & machine I&C | 7503-321 |  |  |  |  | 160 | 320 |  | 10 | 4 | Provided by WBS ?; instl EWDA | TFTR and NSTX assembly
Install PF Solenoid and PF 1a U/L into position | 7503-290 |  | 16 | 32 |  | 32 | 128 |  | 4 | 4 | All I&C in place on solenoid and PF 1a U/L mounted on support structure prior to arrival in Test Cell | TFTR and NSTX assembly
Align guide mechanism for solenoid installation | [11 empty] | TFTR and NSTX assembly
Install solenoid support structure | [11 empty] | TFTR and NSTX assembly
Install solenoid assembly | [11 empty] | TFTR and NSTX assembly
Connect cabling, LN2 and I&C to solenoid | [5 empty] | 8 | 32 |  | 1 | 4 |  | TFTR and NSTX assembly
Install PF4L | [5 empty] | 8 | 32 |  | 1 | 4 |  | TFTR and NSTX assembly
Connect cabling, LN2 and I&C to PF4L | [5 empty] | 8 | 32 |  | 1 | 4 |  | TFTR and NSTX assembly
Adjust spring compression in solenoid support structure | [5 empty] | 8 | 32 |  | 1 | 4 |  | TFTR and NSTX assembly
Raise lower PF 5&6 coils into final position | 7503-270 |  | 24 |  |  | 48 | 192 |  | 6 | 4 |  | TFTR and NSTX assembly
Install Upper PF4, 5 & 6 coils | 7503-280 |  | 24 |  |  | 48 | 192 |  | 6 | 4 |  | TFTR and NSTX assembly
Install Cryostat Base, vapor barrier & port boots | 7503-340 |  |  |  |  | 80 | 320 |  | 10 | 4 |  | TFTR and NSTX assembly
Install elec pwr, LN2, & instr feedthrus thru cryo base | [5 empty] | 40 | 160 |  | 5 | 4 | EWDA | TFTR and NSTX assembly
Integrated electrical testing |  |  |  |  | 80 | 80 | 320 |  | 10 | 4 |  | TFTR and NSTX operations
Install transition box, cabling and connect to power supplies | [5 empty] | 80 | 320 |  | 10 | 4 | EWDA | TFTR and NSTX assembly
Complete LN2 connections from coils to manifolds | 7503-310 |  |  |  |  | 80 | 320 |  | 10 | 4 |  | TFTR and NSTX assembly
Connect coil and VV instrumentation | [5 empty] | 80 | 320 |  | 10 | 4 | EWDA | TFTR and NSTX assembly
Connect 150C bakeout | [5 empty] | 40 | 160 |  | 5 | 4 | EWDA | NSTX operations
Prepare for and perform warm coil testing | [10 empty] | covered in other WBS
Install cryostat cooling system and instrumentation | [5 empty] | 320 | 1280 |  | 20 | 8 | EWDA | TFTR and NSTX assembly
Install Cryostat | [11 empty] | TFTR and NSTX assembly
Install Cryostat upper section and port boots | 7503-350 |  |  |  |  | 80 | 320 |  | 10 | 4 |  | TFTR and NSTX assembly
Install Midplane Cryostat sections and port boots | 7503-360 |  |  |  |  | 120 | 480 |  | 15 | 4 |  | TFTR and NSTX assembly
Install Cryostat Circulation Duct | 7503-370 |  |  |  |  | 40 | 160 |  | 5 | 4 | Cryo cooling system instl in WBS 623 | TFTR and NSTX assembly
PTP and Cooldown | 730.8200 |  |  |  | 80 | 80 | 480 |  |  |  |  | TFTR and NSTX operations
Total Job 7503 |  | 132.048 | 772 | 1436 | 483 | 4316 | 17976