## Sheet1
Station No. | start date | end date | days | weeks |  | 1st period | 2nd period | 3thd period |  | ENGR | Designer | Total hrs
station 2 | 2007-10-01 | 2009-03-01 | 517 | 73.8571 | 2954.2857 | 590.8571 | 393.9048 | 196.9524 | 1181.7143 | 590.8571 | 590.8571 | 1181.7143
station 3 | 2008-02-01 | 2009-07-01 | 516 | 73.7143 | 2948.5714 | 491.4286 | 294.8571 | 98.2857 | 884.5714 | 442.2857 | 442.2857 | 884.5714
Total Hours
station 5 | 2008-04-01 | 2009-09-01 | 518 | 74 | 2960 | 493.3333 | 296 | 98.6667 | 888 | 444 | 444 | 888 | Station 2 to 5 (FPA - Job 1802) | 2954.2857
station 6 | 2009-06-01 | 2010-10-01 | 487 | 69.5714 | 2782.8571 | 742.0952 | 556.5714 | 371.0476 | 1669.7143 | 1669.7143 | 834.8571 | 2504.5714 | Station 6 (Fnl Mach Assy - Job 7503) | 2504.5714
[6 empty] | Station 2 |  | Coverage |  |  | Title III Support Travel
|  |  | 701 | 100.1429 | 4005.7143 | 1st period | 60% | 60% Engr/Dsn |  | Job 1802 | Job 7503
[10 empty] | 4500 |  | FY2007
[6 empty] | 2nd period | 40% | 40% Engr/Dsn |  | 9000 |  | FY2008
[10 empty] | 4500 | 1500 | FY2009
[6 empty] | 3thd period | 20% | 20% Engr/Dsn |  |  | 6000 | FY2010
[11 empty] | 4500 | FY2011
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
590.8571
[6 empty] | Station 3 |  | Coverage
[6 empty] | 1st period | 50% | 50% Engr/Dsn
[6 empty] | 2nd period | 30% | 30% Engr/Dsn
[6 empty] | 3thd period | 10% | 10% Engr/Dsn
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
[6 empty] | Station 5 |  | Coverage
[6 empty] | 1st period | 50% | 50% Engr/Dsn
[6 empty] | 2nd period | 30% | 30% Engr/Dsn
[6 empty] | 3thd period | 10% | 10% Engr/Dsn
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
[6 empty] | Station 6 |  | Coverage
[6 empty] | 1st period | 80% | 80% Engr/Dsn
[6 empty] | 2nd period | 60% | 60% Engr/Dsn
[6 empty] | 3thd period | 40% | 40% Engr/Dsn
[6 empty] | ENGR | 100% | Average
[6 empty] | Designer | 50% | Average
Assume each period is 1/3 of the number of weeks