## P3
1 | WBS2 | JJJJ | WBS4 | Maturity | Complexity | TOTAL ETC | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | FY2010 | FY2011
2 | 12 | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124P - VV Personnel Access Port & Lateral sprts | H | L | 83786 | FY2010: 83786
3 |  | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 125 - VV Local I&C | H | L | 35264 | FY2008: 35264
4 |  | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 122 - Thermal Insulation | H | L | 227094 | FY2008: 32700; FY2010: 194394
5 |  | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124T - Heater Tape for Port Stub | H | L | 20143 | FY2008: 20143
6 |  | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124U - T/C and Heater Tape Leads | H | L | 36621 | FY2007: 36621
7 |  | 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124V - Flux loop junction boxes and spacer templates | H | L | 12275 | FY2007: 12275
|  | Sum 1204 |  |  |  | 415183
8 |  | 1250 - Job: 1250 - Vacuum Vessel Fabrication**CLOSED** | - | H | L | -161695 | FY2007: -161695
9 | 13 | 1302 - Job: 1302 - PF Design -KALISH | RBLX - FY07 Rebaseline Exercise | L | L | 4623 | FY2007: 4623
10 |  | 1302 - Job: 1302 - PF Design -KALISH | - | L | L | 255053 | FY2007: 4063; FY2008: 250990
|  | Sum 1302 |  |  |  | 259676
11 |  | 1352 - Job: 1352 - PF Coil Procurement-KALISH | 13P - PF Coil Fabrication | L | L | 1614665 | FY2008: 536654; FY2009: 1049640; FY2010: 28371
12 |  | 1353 - Job: 1353 - CS Structure Procurement-DAHLGREN | 132A - CS Support Structure | H | L | 337329 | FY2009: 78258; FY2010: 259071
13 |  | 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 133 - Trim Coils | L | L | 122664 | FY2009: 45160; FY2010: 77504
14 |  | 1355 - Job: 1355 - WBS 13 I&C Proc and Coil Assy-KALISH | 134 - TF/PF Loacl I&C | M | L | 72143 | FY2008: 29807; FY2009: 40774; FY2010: 1562
15 |  | 1361 - Job: 1361 - TF Fabrication-KALISH | 130 - TF Title III and Fabrication Oversight | H | M | 164246 | FY2007: 98362; FY2008: 65884
16 |  | 1361 - Job: 1361 - TF Fabrication-KALISH | 13Y - TF Fabrication Contract | H | M | 838004 | FY2007: 354060; FY2008: 483944
17 |  | 1361 - Job: 1361 - TF Fabrication-KALISH | RBLX - FY07 Rebaseline Exercise | H | M | 1422 | FY2007: 1422
18 |  | 1361 - Job: 1361 - TF Fabrication-KALISH | - | H | M | -38281 | FY2007: -38281
|  | Sum 1361 |  |  |  | 965391
19 | 14 | 1404 - Job: 1404 - MCWF R&D 1st Prod Casting**CLOSED** | - |  |  | -35940 | FY2007: -35940
20 |  | 1408 - Job: 1408 - MC Winding Supplies-CHRZANOWSKI | - | L | M | 330148 | FY2007: 184763; FY2008: 145385
21 |  | 1411 - Job: 1411 - MCWF Fabr. S005242-HEITZENROEDER | - | H | L | 8912 | FY2007: 8912
22 |  | 1416 - Job: 1416 - Mod Coil Type AB Fnl Dsn-WILLIAMSON | MCDB - Clamp hardware modifications | L | M | 7786 | FY2007: 7786
23 |  |  | MCDC - Blanket thermal insulation | L | M | 26559 | FY2007: 26559
24 |  |  | MCDE - Top level assy models/drawings | L | M | 75664 | FY2007: 51558; FY2008: 24106
25 |  |  | MCDF - Analysis and closeout documentation | L | M | 121493 | FY2008: 121493
26 |  |  | TCCO - Type C Design Closeout | L | M | 7430 | FY2008: 7430
|  | Sum 1416 |  |  |  | 238932
27 |  | 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | 142A - Outboard Interface | L | M | 12458 | FY2007: 12458
28 |  |  | 142B - Outboard Interface-Bolted Joint Tests-Tension | L | M | 73840 | FY2007: 73840
29 |  |  | 142C - Outboard Interface-Bolted Joint Tests-Shear | L | M | 53144 | FY2007: 52753; FY2008: 390
30 |  |  | 142D - Outboard Interface-Friction | L | M | 37711 | FY2007: 37711
31 |  |  | 142E - Inboard Interface-Design | L | M | 136885 | FY2007: 136885
32 |  |  | 142F - Inboard Interface-AB/BC/AA | L | M | 31072 | FY2007: 31072
33 |  |  | 142G - Inboard Interface-CC | L | M | 127690 | FY2007: 127690
34 |  |  | 142H - Welded Joint Tests-Procedure | L | M | 131251 | FY2007: 131251
35 |  |  | 142I - Welded Joint Tests-Tests | L | M | 73828 | FY2007: 73828
36 |  |  | 142J - Overall MC Interface | L | M | 314885 | FY2007: 284351; FY2008: 30534
|  | Sum 1421 |  |  |  | 992764
37 |  | 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | BLAD - Bladders | M | M | 16397 | FY2007: 16397
38 |  |  | BUSH - Bushings | M | M | 53337 | FY2007: 39404; FY2008: 13933
39 |  |  | SHMS - Shims | M | M | 173346 | FY2007: 105129; FY2008: 68217
40 |  |  | STUD - Studs Washers Nuts | M | M | 716574 | FY2007: 242542; FY2008: 474032
|  | Sum 1431 |  |  |  | 959654
41 |  | 1451 - Job: 1451 - Mod Coil Winding-CHRZANOWSKI | 1A - Station 1a/4 Casting Prep | H | H | 244471 | FY2007: 244471
42 |  |  | 2 - Station 2-Winding Instl Chill Plates Tubing Bag | H | H | 579958 | FY2007: 363812; FY2008: 216147
43 |  |  | 3 - Station 4-Winding Instl Chill Plates Tubing Bag | H | H | 646331 | FY2007: 354655; FY2008: 291676
44 |  |  | 5 - Station 5-VPI | H | H | 328485 | FY2007: 137279; FY2008: 191205
45 |  |  | 1 - Station 1 Post VPI | H | H | 203766 | FY2007: 99655; FY2008: 104110
46 |  |  | LABR - LOE Oversight & Supervision | H | H | 709164 | FY2007: 300686; FY2008: 408478
|  | Sum 1451 |  |  |  | 2712175
47 |  | 1459 - Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI | PLTS - Punchlist Tech shop/RESA | M | L | 419672 | FY2007: 160478; FY2008: 259194
48 |  |  | PLCT - Punchlist- Coil Technicians | M | L | 325879 | FY2007: 79397; FY2008: 246483
|  | Sum 1459 |  |  |  | 745551
49 | 15 | 1501 - Job: 1501 - Coil Structures Design-DAHLGREN | - | M | L | 184751 | FY2007: 184607; FY2008: 144
50 |  | 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | - | M | L | 1016255 | FY2008: 339333; FY2009: 631327; FY2010: 45595
51 | 16 | 1601 - Job: 1601 - Coil Services Design-GORANSON | RBLX - FY07 Rebaseline Exercise |  |  | 6229 | FY2007: 6229
52 |  | 1601 - Job: 1601 - Coil Services Design-GORANSON | 161 - 161 - LN2 Distribution | H | L | 355748 | FY2008: 80834; FY2009: 193863; FY2010: 81051
53 |  | 1601 - Job: 1601 - Coil Services Design-GORANSON | 162 - 162 - Electrical Leads | H | L | 485790 | FY2008: 42166; FY2009: 253485; FY2010: 190140
54 |  | 1601 - Job: 1601 - Coil Services Design-GORANSON | 163 - 163 - Coil Protection System | H | L | 38150 | FY2009: 38150
|  | Sum 1601/1602/1603 |  |  |  | 885917
55 | 17 | 1701 - Job: 1701 - Cryostat Design-GETTLEFINGER | - | L | M | 207229 | FY2009: 199546; FY2010: 7683
56 |  | 1702 - Job: 1702 - Base Support Struct Design-DAHLGREN | - | M | L | 163469 | FY2008: 163469
57 |  | 1751 - Job: 1751 - Cryostat Procurement-GETTLEFINGER | - | H | L | 324852 | FY2010: 324852
58 |  | 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 172 - 172 - Base Support Structure | M | L | 71462 | FY2008: 4694; FY2009: 66768
59 | 18 | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | A - Oversight and Supervision | H | M | 1979813 | FY2007: 329056; FY2008: 977158; FY2009: 670275; FY2010: 3324
60 |  | 1802 - Job: 1802 - FP Assy Oversight&Support-VIOLA | - | H | M | 15000 | FY2007: 15000
|  | Sum 1802 |  |  |  | 1994813
61 |  | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 2.00 - Station 2-Modular Coil Sub- Assembly | L | L | 0
62 |  | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 3.00 - Station 3-Modular Coil to VVSA Assembly | M | L | 112938 | FY2007: 99307; FY2008: 13631
63 |  | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 5.00 - Station 5-Final Field Period Assembly | M | L | 186797 | FY2007: 33974; FY2008: 152824
64 |  | 1803 - Job: 1803/1805- FPA Tooling/Constr-BROWN/DUDEK | 6.00 - 6.00-Final Machine Assembly | L | M | 215967 | FY2008: 102139; FY2009: 113828
|  | Sum 1803/1805 |  |  |  | 515702
65 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 1.00 - 1.00-VV Prep Station | M | M | 10405 | FY2009: 10405
66 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 2.00 - Station 2-Modular Coil Sub- Assembly | M | M | 25658 | FY2007: 25658
67 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 3.00 - Station 3-Modular Coil to VVSA Assembly | M | M | 38766 | FY2007: 17426; FY2008: 21340
68 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 5.00 - Station 5-Final Field Period Assembly | M | M | 59768 | FY2008: 59768
69 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | 6.00 - 6.00-Final Machine Assembly | M | M | 94125 | FY2008: 51769; FY2009: 42356
70 |  | 1806 - Job: 1806 - FP Assembly specs and drawings-COLE | - | M | M | 85479 | FY2007: 21071; FY2008: 49697; FY2009: 14710
|  | Sum 1806 |  |  |  | 314201
71 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S0P0 - General F.P. Assy support | H | M | 2727199 | FY2007: 417936; FY2008: 1229885; FY2009: 1046918; FY2010: 32460
72 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P1 - Station 1-VV Prep (hard surface components) FP#1 | H | M | 111486 | FY2007: 50602; FY2008: 60884
73 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P2 - Station 1- VV Prep (hrd surf cmpntsFP#2 | H | M | 141302 | FY2007: 13289; FY2008: 128013
74 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1P3 - Station 1- VV Prep (hrd surf cmpntsFP#3 | H | M | 225259 | FY2007: 18998; FY2008: 72040; FY2009: 134221
75 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S1SP - Station 1-Spool pieces (3) (spacers) | H | M | 31335 | FY2009: 31335
76 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PR - Station 2 Trials & Development | L | H | 458069 | FY2007: 405640; FY2008: 52429
77 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PX - Setup | L | H | 74499 | FY2007: 53670; FY2008: 20829
78 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PM - Pre-Measuring and fitup checks | L | H | 224874 | FY2007: 95096; FY2008: 129778
79 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P1 - Station 2-MC Sub Assy A1-B1-C1 | L | H | 137791 | FY2007: 44909; FY2008: 92882
80 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2PZ - Station 2 MC Sub Assy A2-B2-C2 | L | H | 76906 | FY2008: 76906
81 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P2 - Station 2-Modular Coil Subassembly-FP#2 | L | H | 217499 | FY2008: 217499
82 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S2P3 - Station 2-Modular Coil Subassembly-FP#3 | L | H | 223149 | FY2008: 25478; FY2009: 197671
83 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P0 - Station 3 Setup/Preparations/General | L | H | 128836 | FY2008: 128836
84 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P1 - Station 3-Assemble Mod Coils and VVSA-FP#1 | L | H | 143315 | FY2008: 143315
85 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P2 - Station 3-Assemble Mod Coils and VVSA-FP#2 | L | H | 145618 | FY2008: 64808; FY2009: 80811
86 |  | 1810 - Job:1810-Field Period Assy -Station 1 2 3 VIOLA | S3P3 - Station 3-Assemble Mod Coils and VVSA-FP#3 | L | H | 141075 | FY2009: 141075
|  | Sum 1810 |  |  |  | 5208212
87 |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P0 - Setup/Preparations/General | L | M | 238876 | FY2008: 238876
88 |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P1 - Station 5- Final FP Assy -FP#1 (in NCSX TC) | L | M | 360380 | FY2008: 83805; FY2009: 276575
89 |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P2 - Station 5- Final FP Assy -FP#2 (in NCSX TC) | L | M | 363888 | FY2009: 331536; FY2010: 32352
90 |  | 1815 - Job: 1815 - Field Period Assy -Station 5-VIOLA | S4P3 - Station 5- Final FP Assy -FP#3 (in NCSX TC) | L | M | 364644 | FY2009: 309295; FY2010: 55349
|  | Sum 1815 |  |  |  | 1327788
91 | 19 | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 191 - 191 - Stellarator Core Management & Oversight | H | L | 860314 | FY2007: 69094; FY2008: 210857; FY2009: 223747; FY2010: 230570; FY2011: 126047
92 |  | 1901 - Job: 1901 - Stellarator Core Mngtt&Integr-COLE | 192 - 192 - Stellarator Core Integration & Analysis | H | L | 725465 | FY2007: 72622; FY2008: 176059; FY2009: 185681; FY2010: 192910; FY2011: 98193
|  | Sum 1901 |  |  |  | 1585779
93 | 21 | 2101 - Job: 2101 - Fueling Systems-BLANCHARD | - | L | L | 63168 | FY2010: 63168
94 | 22 | 2201 - Job: 2201 - Vacuum Pumping Systems-BLANCHARD | - | M | L | 174773 | FY2009: 105738; FY2010: 69035
95 | 31 | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD3 - Rogowski Coils | H | L | 101119 | FY2007: 16221; FY2008: 84898
96 |  | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | MD4 - TF and PF Co-wound Loops | H | L | 71824 | FY2007: 68864; FY2008: 2959
97 |  | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124U - T/C and Heater Tape Leads | H | L | 48277 | FY2007: 44257; FY2008: 4020
98 |  | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | 124V - Flux loop junction boxes and spacer templates | H | L | 57948 | FY2007: 57948
99 |  | 3101 - Job: 3101 - Magnetic Diagnostics-STRATTON | VLPB - Voltage Loops & Protective Boxes | H | L | 14292 | FY2008: 14292
|  | Sum 3101 |  |  |  | 293460
100 | 36 | 3601 - Job: 3601 - Edge Divertor Diagnostics-STRATTON | - | H | L | 26135 | FY2010: 26135
101 | 38 | 3801 - Job: 3801 - Electron Beam Mapping-STRATTON | - | M | M | 255177 | FY2009: 103182; FY2010: 151995
102 | 39 | 3901 - Job: 3901 - Diagnostics sys Integration-STRATTON | - | H | L | 132944 | FY2007: 11593; FY2008: 29228; FY2009: 30085; FY2010: 62038
103 | 41 | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | - | H | L | -104100 | FY2007: -104100
104 |  | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411 - 411 - Auxiliary AC Power Systems | H | L | 123693 | FY2009: 49623; FY2010: 74070
105 |  | 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 412 - 412 - Experimental AC Power Systems | H | L | 34846 | FY2009: 8207; FY2010: 26639
|  | Sum 4101 |  |  |  | 54439
106 | 43 | 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431 - 431 - C-Site DC Systems | H | L | 602831 | FY2008: 10991; FY2009: 273787; FY2010: 318052
107 | 44 | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 441 - 441 - Electrical Interlocks | M | L | 463078 | FY2009: 202408; FY2010: 260670
108 |  | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 442 - 442 - Kirk Key Interlocks | M | L | 85437 | FY2010: 85437
109 |  | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 443 - 443 - Real Time Control Systems | M | L | 14772 | FY2010: 14772
110 |  | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 444 - 444 - Instrument Systems | M | L | 219849 | FY2009: 44412; FY2010: 175438
111 |  | 4401 - Job: 4401 - Control & Protection-RAMAKRISHNAN | 445 - 445 - Coil Protection Systems | M | L | 282554 | FY2009: 79429; FY2010: 203125
|  | Sum 4401 |  |  |  | 1065690
112 | 45 | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 451 - 451 - System Design & Interfaces | H | L | 215142 | FY2009: 214748; FY2010: 395
113 |  | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 452 - 452 - Electrical Systems Support | H | L | 199076 | FY2009: 105373; FY2010: 93703
114 |  | 4501 - Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 453 - 453 - System Testing (PTP's) | H | L | 270550 | FY2009: 35472; FY2010: 130757; FY2011: 104322
|  | Sum 4501 |  |  |  | 684768
115 | 51 | 5101 - Job: 5101 - Network and Fiber Infrastruct-SICHTA | - | M | L | 144271 | FY2009: 7328; FY2010: 136942
116 | 52 | 5201 - Job: 5201 - I&C Systems-SICHTA | - | M | L | 198607 | FY2009: 30670; FY2010: 167936
117 | 53 | 5301 - Job: 5301 - Data Acquisition-SICHTA | - | M | L | 165118 | FY2009: 22774; FY2010: 142344
118 | 54 | 5401 - Job: 5401 - Facility Timing & Synchron.-SICHTA | - | M | M | 205716 | FY2009: 4387; FY2010: 197883; FY2011: 3446
119 | 55 | 5501 - Job: 5501 - Real Time Control System-SICHTA | - | M | L | 129109 | FY2009: 16740; FY2010: 112370
120 | 56 | 5601 - Job: 5601 - Central Safety &Interlock Sys-SICHTA | - | L | M | 223144 | FY2009: 7055; FY2010: 216089
121 | 58 | 5801 - Job: 5801 - Central I&C Integr& Oversight-SICHTA | - | H | L | 69144 | FY2007: 7116; FY2008: 24174; FY2009: 18611; FY2010: 19243
122 | 61 | 6101 - Job: 6101 - Water Systems-DUDEK | 613 - 613 - Vacuum Pumping System | L | L | 49628 | FY2009: 49628
123 | 62 | 6201 - Job: 6201 - Cryogenic Systems-DUDEK | 621 - 621 - LN2-LHe Supply System | L | M | 87585 | FY2009: 19501; FY2010: 68084
124 |  | 6201 - Job: 6201 - Cryogenic Systems-DUDEK | 622 - 622 - LN2 Coil Cooling Supply | L | M | 88514 | FY2009: 21969; FY2010: 66545
125 |  | 6201 - Job: 6201 - Cryogenic Systems-DUDEK | 623 - 623 - GN2 Cryostat Cooling System | L | M | 487372 | FY2009: 155031; FY2010: 331767; FY2011: 574
|  | Sum 6201 |  |  |  | 663471
126 | 63 | 6301 - Job: 6301 - Utility Systems-DUDEK | - | L | L | 116634 | FY2009: 116634
127 | 64 | 6401 - Job: 6401 - PFC/VV Htng/Cooling(bakeout)- DUDEK | - | L | M | 548642 | FY2009: 229579; FY2010: 319063
128 | 73 | 7301 - Job: 7301 - Platform Design & Fab-PERRY | - | L | L | 204492 | FY2007: 2485; FY2009: 202007
129 | 74 | 7401 - Job: 7401 - TC Prep & Mach Assy Planning-PERRY | - | L | M | 1429863 | FY2007: -308300; FY2008: 22746; FY2009: 481530; FY2010: 927371; FY2011: 306517
130 | 75 | 7501 - Job: 7501 - Construction Support Crew-PERRY | - | L | M | 1436581 | FY2009: 241070; FY2010: 887133; FY2011: 308378
131 |  | 7503 - Job: 7503 - Machine Assembly (station 6)-PERRY | - | L | M | 4645955 | FY2009: 1472809; FY2010: 2405983; FY2011: 767162
132 | 76 | 7601 - Job: 7601 - Tooling Design & Fabrication-PERRY | - | L | L | 414042 | FY2009: 149912; FY2010: 264130
133 | 81 | 8101 - Job: 8101 - Project Management & Control-NEILSON | RBLX - FY07 Rebaseline Exercise | H | L | 4527 | FY2007: 4527
134 |  | 8101 - Job: 8101 - Project Management & Control-NEILSON | - | H | L | 3529375 | FY2007: 314353; FY2008: 895411; FY2009: 1014940; FY2010: 962045; FY2011: 342626
135 |  | 8102 - Job: 8102 - NCSX MIE Management ORNL-LYON | - | H | L | 496740 | FY2007: 60420; FY2008: 158720; FY2009: 158720; FY2010: 96622; FY2011: 22258
|  | Sum 8101/8102 |  |  |  | 4030642
136 | 82 | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | RBLX - FY07 Rebaseline Exercise | H | L | 30228 | FY2007: 30228
137 |  | 8202 - Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | - | H | L | 2428994 | FY2007: 288274; FY2008: 642476; FY2009: 640093; FY2010: 637522; FY2011: 220630
|  | Sum 8202 |  |  |  | 2459222
138 |  | 8203 - Job: 8203 - Design Integration-BROWN | - | M | M | 1361515 | FY2007: 149141; FY2008: 351746; FY2009: 350339; FY2010: 348933; FY2011: 161356
139 |  | 8204 - Job: 8204 - Systems Analysis-BROOKS | - | M | M | 1329945 | FY2007: 345987; FY2008: 283072; FY2009: 281940; FY2010: 280807; FY2011: 138139
140 |  | 8205 - Job: 8205 - Dimensional Control Coordin-REIERSEN | - | L | H | 598301 | FY2007: 111110; FY2008: 278888; FY2009: 136829; FY2010: 55501; FY2011: 15972
141 |  | 8210 - Job: 8210 - FY07 Rebaseling tasks | RBLX - FY07 Rebaseline Exercise | H | L | 19201 | FY2007: 19201
142 |  | 8215 - Job: 8215 Plant Design | RBLX - FY07 Rebaseline Exercise | H | L | 134641 | FY2007: 24296; FY2008: 33874; FY2009: 34530; FY2010: 35947; FY2011: 5994
143 | 85 | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | - | H | L | 418829 | FY2011: 418829
144 | 85 | 8501 - Job: 8501 - Integrated Systems Testing-GENTILE | PROC - Startup Documentation | H | L | 346004 | FY2009: 275780; FY2010: 70223
|  | Sum 8501 |  |  |  | 764833
145 | 89 | 8998 - Job: 8998 - Allocations-STRYKOWSKY | - | H | L | 1478404 | FY2007: 146988; FY2008: 384384; FY2009: 406232; FY2010: 430800; FY2011: 110000
[5 empty] | ETC= | 49552488 | 0 | 0 | 0 | 0 | 6925625 | 12492223 | 14206512 | 12777686 | 3150443
[5 empty] | Cost thru 4/30/07= | 67305752 | FY2003: 5941920; FY2004: 14314350; FY2005: 18131610; FY2006: 19072808; FY2007: 9845060
[5 empty] | EAC= | 116858240 | 5941920 | 14314350 | 18131610 | 19072808 | 16770685 | 12492223 | 14206512 | 12777686 | 3150443
[5 empty] | Contingency (approx) | 15093000 | FY2008: 3400000; FY2009: 4200000; FY2010: 4200000; FY2011: 3293000
[5 empty] | TEC= | 131951240 | 5941920 | 14314350 | 18131610 | 19072808 | 16770685 | 15892223 | 18406512 | 16977686 | 6443443
[5 empty] | Funding= |  | FY2007: 16771000; FY2008: 15900000; FY2009: 18200000; FY2010: 18900000; FY2011: 19500000
30.46%
Note: standing army ("hotel") cost reduced from $260k/mo. To $169k/mo.
|  |  | Planneds finish= |  |  | 2011-02-23
|  |  | CD-4= |  |  | 2011-12-23
|  |  | Schedule Contingency= |  |  | 10 mo.
Note on E1: Christopher O. Gruber: Enter L, M or H
Note on F1: Christopher O. Gruber: Enter L, M or H