## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 163
WBS Title: Coil Protection Systems
Job Number: 1601-163
Job Title: Coil Protection Systems Interfaces
Job Manager: Paul Goranson
Description:
This WBS element consists of the interface design of the coil electrical leads inside the cryostat which then connect the coil protection systems outside the cryostat.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07)): SEE JOB 1601-161
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 163
WBS Title: Coil Protection Systems
Job Number: 1601-163
Job Title: Coil Protection Systems Interfaces
Job Manager: Paul Goranson
Description:
This effort covers all Title I, II, and III engineering for the Coil Protection System. No hardware is anticipated for this job, only design interface with WBS 4 and 5.
HOURS
Task ID | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL DSN | ORNOL RM | EMEM | EMSM | EMSB | EMTB | EAEM | EASM | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate
Title I an II Design
Pro-E models (avg) | 8 | hrs/model | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
assy dwgs | 24 | hrs/dwg | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
Detail drawings | 16 | hrs/dwg | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
installation dwg | 16 | hrs/dwg | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
cooling schematic | 0 | hrs/dwg | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
electrical schematic | 8 | hrs/dwg | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
I&C schematic | 20 | hrs/dwg | 4 | 80 | 0 | 80 | [14 empty] | See Worksheet below - based on recent experience at MDL
stress analysis | 0 | hrs/calc | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
thermal analysis | 24 | hrs/calc | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
special analysis (electromagnetics) | 40 | hrs/calc | 2 | 80 | 40 | [6 empty] | 40 | [8 empty] | See Worksheet below - based on recent experience at MDL
Procuremnt Specifications | 16 | hrs/spec | 0 | 0 | 0 | [15 empty] | See Worksheet below - based on recent experience at MDL
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 | 40 | [15 empty] | See Worksheet below - based on recent experience at MDL
meetings/reporting/presentations | 10% | % of tot hrs |  | 20 | 20 | [15 empty] | See Worksheet below - based on recent experience at MDL
Subtotal Title I & II Design |  |  |  | 220 | 100 | 80 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Title III
vendor inspection & oversight | 0 | hrs per | 1 | 0
Disposition of deviation requests and non-conformances | 0 | hrs/wk | 20 | 0 | [16 empty] | Based on recent experience on NCSX
In-House fab/assy oversight & inspection | 0 | hrs/wk | 4 | 0
As-built drawings | 0 | hrs/dwg | 0 | 0 | [16 empty] | Based on recent experience on NCSX
Installation oversight & inspection | 0 | hrs/wk | 4 | 0
Subtotal Title III Design |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notes and worksheets
Pro-E models
assy dwgs
Detail drawings
installation dwg
cooling schematic
electrical schematic
I&C schematic |  |  | 4 | [17 empty] | minimum of one schematic for each signal type
stress analysis
thermal analysis
special analysis |  |  | 2 | [17 empty] | analysis of potential fault conditions based on reaction times of various systems specification of correct current, voltage, strain, and temperature waveforms to be compared with actual
procurement specifications
preliminary and final design reviews |  |  | 1
meetings/reporting/presentations

## Table II - M&S
WBS Number: 163
WBS Title: Coil Protection Systems
Job Number: 1601-163
Job Title: Coil Protection Systems Interfaces
Job Manager: Paul Goranson
Description:
No materials or subcontracts are anticipated for this WBS element
Why do all of these formulas refer back to B87 => seems like it should progress with coil

## Table III Fab & Assy
WBS Number: 163
WBS Title: Coil Protection Systems
Job Number: 1601-163
Job Title: Coil Protection Systems Interfaces
Job Manager: Paul Goranson
Fabrication and Assembly
Description:
No local fab or assembly is anticipated for the Coil leads. Installation is part of WBS 7.

## Table IV - Conting & Risk
WBS Number: 163
WBS Title: Coil Protection Systems
Job Number: 1601-163
Job Title: Coil Protection Systems Interfaces
Job Manager: Paul Goranson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity | X |  |  |  | Design well established based on previous devices
-5%/+10%
| Design Complexity |  |  | X |  | Standard Components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)