## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702)
Job Title: Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Description:
This WBS element consists of the design and fabrication of the base support structure. The base support structure consists of the base column assemblies, interconnecting beams and column base hardware.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07)):
Job 1702: $163,469
Job 1752: $71,462
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [16 empty] | Basis of Estimate
|  | FY07$K |  |  |  |  | HOURS
Task ID |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EADD | EMSM | EMSB | EMTB | EAD* | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
Based on prior engineering experiences; e.g. S-1, PLT, PDX, PBX-m
TITLE I AND TITLE II DESIGN COMPLETED
| Base Support layout & design | [7 empty] | 420
| Design engrg. & analysis | [11 empty] | 320
| PDR prep | [7 empty] | 12 |  |  |  | 12
| Disposition PDR chits | [11 empty] | 16
| FDR prep | [7 empty] | 16 |  |  |  | 16
| Prepare SOW/RFQ | [11 empty] | 12
| Disposition FDR chits | [7 empty] | 32 |  |  |  | 24
Total Title I & II | [8 empty] | 480 |  |  |  | 400
Title III Design
Vendor Oversight, Inspection | [12 empty] | 20 | [10 empty] | Engineering judgement based on recent NCSX experience
Disposition of deviation requests and non-conformances | [12 empty] | 16 | [10 empty] | Engineering judgement based on recent NCSX experience
Coordination of Procurement Actions | [12 empty] | 8 | [10 empty] | Engineering judgement based on recent NCSX experience
Subtotal Title III Design |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Materials and Subcontracts (M&S) |  |  |  |  | Basis of Estimate
Description:
The base supoort structure is the main gravity load carrying structure (~250,000lbs) for the entire machine. It must provide the gravity load path from the machine and distribute these loads to the test cel floor. It must also be capable of withstanding horizontal seismic accelerations of 0.13g and vertical accelerations of 0.07g.
Purchased parts: | (ft.) | lbs./ft. | $/lb. | cost
4 - W12 x 26 x 24' - 316L stainless steel | 96 | 26 | 7.5 | 18720 | Verbal quote StainlessStructurals - recent (early April 2007) - $/lb
4 - W8 x 15 x 24' - 316L stainless steel | 96 | 15 | 7.5 | 10800 | Verbal quote StainlessStructurals - recent (early April 2007) - $/lb
3/4" - 316L plate 36" x 48" base hub plate | 4 | 95 | 7.5 | 2850 | Quote , metal suppliers online - See Table V
3/4" - 316L plate 36" x 48" top & bottom base column bases | 4 | 95 | 7.5 | 2850 | Quote , metal suppliers online - See Table V
Weld rod & roto-bores |  |  |  | 3000 | PPPL Shop estimate - see Table V - adjusted by WBS Manager
12 - Inconel 718 hex bolts 1-8 x 2.5" @ $55 ea. |  |  |  | 660 | Quote B&G fabricators - See Table V
12 - Inconel 718 hex nuts 1-8 @ $38 ea. |  |  |  | 456 | Quote B&G fabricators - See Table V
24 - 316 SS flat washers 1.03" ID @$4.26 ea. |  |  |  | 102.24 | Catalog item McMaster-Carr - see Table V
Total Materials |  |  |  | 39438.24
Labor - PPPL: | hrs.
Welding (4hrs @ 48 places) | 192 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager
Welding (4hrs @ 24 places) | 96 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager
Cut & Drill plates | 75 |  |  |  | PPPL Shop estimate - see Table V - adjusted by WBS Manager
Job Totals: | 363

## Table III - FabAssy & Instl
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
In-house Fabrication and Assembly and Installation
Included in Table II

## Table IV - Conting & Risk
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
Job 1702 |  |  |  |  | -10%/+15%
| Design Maturity |  | X |  |  | Design is near PDR, but nothing exotic
| Design Complexity |  |  | X |  | Standard parts and components
Job 1752 |  |  |  |  | -10%/+15%
| Design Maturity |  | X |  |  | Design is near PDR, but nothing exotic
| Design Complexity |  |  | X |  | Standard parts and components
Other Comments: | [5 empty] | Possibility that vendor will not deliver on time, however, significant float (~4 months exist off critical path) => other vendors could be identified.
There is a finite likelihood of material costs increasing, but already assumed an escalation of ~5%/year for Inconel, HOWEVER, recent history indicatespossibility of a much higher escalation (Table V)
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
Jobs 1702 and 1752 - NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 172
WBS Title: Base Support Structures
Job Numbers: 1702 and 1752
Job Title: Base Support Structure Design (1702) and Base Support Structure Procurements (1752)
Job Manager: Fred Dahlgren
PPPL Engineering/Tech Shop Estimate | Metal Suppliers Internet Quote
B&G Quote
Material Escalation Information