## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 19
WBS Title: Stellarator Core Manafgement and Integration
Job Number: 1901
Job Title: Stellarator Core Manafgement and Integration
Job Manager: Mike Cole
Description:
WBS 191 (Stellarator Core Management) - This effort covers general management and oversight for the Stellarator Core. It is assumed to be half time for the duration of the project. This is a Level of Effort task. WBS 192 (Stellarator Core Integration and Global Analysis) - This effort covers design integration activities for the Stellarator Core, including global Pro-E models and drawings for the Stellarator Core, Pro-Intralink database maintenance of all drawings and CAD models, analyses common to all of WBS 1, and design criteria documents. This is a level of effort task.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $1,585,779
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date

## Table I - Dsn Labor
WBS Number: 19
WBS Title: Stellarator Core Manafgement and Integration
Job Number: 1901
Job Title: Stellarator Core Manafgement and Integration
Job Manager: Mike Cole
Description:
WBS 191- This effort covers general management and oversight for the Stellarator Core. It is assumed to be half time for the duration of the project.
HOURS
Task ID |  | 2007 | 2008 thru 2010 | 2011 | Basis of Estimate
Description:
WBS 191 (Stellarator Core Management) - This effort covers general management and oversight for the Stellarator Core. It is assumed to be half time for the duration of the project. This is a Level of Effort task.
Hours/year
Labor - Composite of ORNL Engineer / Designer |  | 488 | 1170 | dependent upon schedule | Brad at 15% and Mike at 50%
K$
Travel |  | 3000 | 6000 | 6000
WBS 192 (Stellarator Core Integration and Global Analysis) - This effort covers design integration activities for the Stellarator Core, including global Pro-E models and drawings for the Stellarator Core, Pro-Intralink database maintenance of all drawings and CAD models, analyses common to all of WBS 1, and design criteria documents. This is a level of effort task.
Hours/year
Labor - Composite of ORNL Engineer / Designer |  | 638 | 1530 | dependent upon schedule | Assumed 0.3 my/yr for a design integration designer and 0.55 my/yr for an engineer. Based on an ORNL manyear of 1800 hours.
K$
Travel |  | 3000 | 3000 | 3000 | Assumed 2 trips/per of the designer and engineer
Title III is shown in WBS 73 reference 2505hrs
see spreadsheet title 3 estimate for fpa and machine assy
Brad at 15% Mike at 40%

## Table II - M&S
WBS Number: 19
WBS Title: Stellarator Core Manafgement and Integration
Job Number: 1901
Job Title: Stellarator Core Manafgement and Integration
Job Manager: Mike Cole
Materials and Subcontracts (M&S) | [5 empty] | Basis of Estimate
Description:
WBS 191 - Management and Integration - no M&S
WBS 192 - Stellarator Core Integration and Global Analysis
Worksheet for FY2007 to 2009
| no. | cost ea/yr | yrs | % to NCSX | total
Software
Pro-E licenses | 6 | 3330 | 4 | 60% | 47952 | Based on actual FY 2007 maint costs
ANSYS maintenance | 1 | 8743 | 4 | 60% | 20983.2 | Based on FY 2003 maint costs
IPA maint. | 1 | 2005 | 4 | 60% | 4812 | Based on FY 2003 maint costs
Rhino | 1 | 500 | 4 | 60% | 1200 | Based on FY 2003 maint costs
Corel Draw | 1 | 600 | 4 | 60% | 1440 | Based on FY 2003 maint costs
misc software | 1 | 1500 | 4 | 60% | 3600 | Based on historical costs
subtotal, software |  |  |  |  | 79987.2
Hardware
Workstations | 6 | 2500 | 4 | 60% | 36000 | based on replacement every two years
Printer / Plotter maint. | 2 | 1200 | 4 | 60% | 5760 | based on historical maint. Costs
subtotal, hardware |  |  |  |  | 41760
Total Purchased Software/Hardware |  | 20378 | Per Year |  | 121747.2

## Table III - FabAssy & Instl
WBS Number: 19
WBS Title: Stellarator Core Manafgement and Integration
Job Number: 1901
Job Title: Stellarator Core Manafgement and Integration
Job Manager: Mike Cole
In-house Fabrication and Assembly and Installation
Description: N/A

## Table IV - Conting & Risk
WBS Number: 19
WBS Title: Stellarator Core Manafgement and Integration
Job Number: 1901
Job Title: Stellarator Core Manafgement and Integration
Job Manager: Mike Cole
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | LOE - estimates based on recent experiences on NCSX
-10%/+20%
| Design Complexity |  |  | X |  | LOE - estimates based on recent experiences on NCSX
| Other Comments: |  |  |  |  | Work highly dependent of MC winding and FPA activities - as they are delayed/improved, this job follows.
Residual Risks
Risk |  |  |  |  | Likelihood of Occurring (%) | Mitigation Stgrategies | Consequence if Occurs
[7 empty] | Cost | Schedule
NONE