## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
Description:
This WBS element consists of diagnostics required to characterize the plasma edge and divertor regions. Quantities measured include the hydrogen recycling, the edge neutral pressure, the edge temperature and density profiles, the divertor radiated power, the divertor target temperature, and edge and divertor flows. This information is important in the understanding of edge transport and plasma wall interactions. A variety of diagnostic techniques will be used. This WBS is responsible for the vacuum interface, including windows, shutters, valves or electrical feedthrus. Responsibility also includes sensors, mounting structures and sensor cabling near the vacuum vessel. Sensor electronics and racks are also included. Other WBS units are responsible for field cabling and junction boxes, rack terminal blocks, rack AC power and grounding, and data acquisition hardware.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $26,135
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
Description: Visible TV camera wide angle view along one field period to show plasma shape. Will borrow camera from NSTX. Location will be one of the blanked-off neutral beam ports. Need to install an angled tube and 8” Conflat flange on NB port. Need to design and fabricate holder for camera. Will use same camera and window for e-beam mapping (WBS 38).
|  | $ | Labor Hours | [6 empty] | Basis of Estimate
Task Description |  | M&S | EMEM | EMSM | EMTB | EEEM | EETB | EADM | RM2
Design System - angled port design for line-of-sight | [7 empty] | 80 |  | Based on similar designs for NSTX (much more complicated on NSTX)
Fabricate angled view port |  |  |  |  | 8 |  | 16 |  |  | Based on similar designs for NSTX - modified for NCSX design - estimate from Construction Manager
Fabricate Camera Mount |  |  |  |  | 40 |  |  |  |  | Based on similar designs for NSTX
Install System |  |  |  |  | 40 |  |  |  |  | Based on similar designs for NSTX
Engineering Oversight |  |  | 40 | [6 empty] | Based on similar designs for NSTX
Materials
| Window | 2500 | [7 empty] | Based on catalogue price from vendor - See Table V
| Misc Material/parts | 1000 | [7 empty] | Based on experiences on NSTX
TOTAL |  | 3500 | 40 | 0 | 88 | 0 | 16 | 80 | 0

## Table II - M&S
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Standard design based on previous PPPL devices
-5%/+10%
| Design Complexity |  |  | X |  | Very simple design used before
| Other Comments:- |  |  |  |  | Time for leak checking welds not included in this estimate
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 36
WBS Title: Edge & Divertor Diagnostic Systems
Job Number: 3601
Job Title: Edge & Divertor Diagnostic Systems
Job Manager: Brent Stratton
M&S Backup
Window Quote