## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
Description:
This WBS element consists of all EB mapping equipment required to accomplish the NCSX mission as defined in the General Requirements. This equipment will be required in the field-line mapping phase of operations and thus is included in the NCSX Fabrication Project.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $255,177
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
Description: E-beam mapping will be done with an electron gun and movable fluorescent wand borrowed from Auburn University. Will use same visible TV camera as in WBS 36. Need two port extensions for 10” diameter ports. Need data acquisition system to record wand position, electron gun bias voltage and emission current. Need control capability for wand, electron gun bias voltage and emission current..
|  | $ |  | Labor Hours | [7 empty] | Basis of Estimate
Task Description |  | M&S | Travel | EMEM | EMSM | EMTB | EEEM | EETB | EADM | ECEM | RM2
Design System
| Design interface components - adapting flange sizes |  |  | 120 | [7 empty] | Engineering judgement - however standard design used before
| Physics-based modeling, work with Auburn personnel |  | 3000 | [7 empty] | 480 | Engineering judgement - however standard design used before
| Pepare drawings (~6 drawings) | [7 empty] | 80 |  |  | Based on conceptual design and PPPL design experience
| Design software for control & data acquisition for H/W | [8 empty] | 300 |  | Engineering judgement - however standard design used before
Fabricate System (Including welding)
| Fabricating & Welding Spool Pieces |  |  |  |  | 16 |  | 16 |  |  |  | Engineering judgement - however standard design used before
| Fabricating other parts |  |  |  |  | 80 | [5 empty] | Engineering judgement - however standard design used before
Install System | [5 empty] | 240 | [5 empty] | Engineering judgement - however standard design used before
Engineering Oversight |  |  |  | 40
Materials
| Port Extensions Material/Parts | 4000 | [9 empty] | Based on estimate provided by PPPL Construction Manager - see Table V
| Data Acquisition Materials/Parts | 10000 | [9 empty] | Based on estimate provided by PPPL Computer Division - see Table V
| Rack | 28600 | [9 empty] | Based on estimate provided by PPPL Electrical Engineer - see Table V
TOTAL |  | 42600 | 3000 | 160 | 0 | 336 | 0 | 16 | 80 | 300 | 480

## Table II - M&S
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Similar designs done elswhere, but NCSX specific design still conceptual
-15%/+25%
| Design Complexity |  | X |  |  | Standard components, but interfaces could be somewhat complex
| Other Comments: |  |  |  |  | Leak checking not included in this estimate
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Risk
WBS Number: 38
WBS Title: Electron Beam Mapping
Job Number: 3801
Job Title: Electron Beam Mapping Systems
Job Manager: Brent Stratton
Backup Information
Data Acquistion Hardware