## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 52
WBS Title: Central I&C Systems
Job Number: 5201
Job Title: Central I&C Systems
Job Manager: Paul Sichta
Description:
The central process control system will provide supervisory control and a common user interface to all engineering subsystems and high-energy systems. It will provide the synchronization between two or more operating machines at PPPL using shared power conversion resources. It will support current and historical trending, alarm logging, mimic displays, machine state archival, and process control and monitoring functions for NCSX. It will be designed using the Experimental Physics and Industrial Control System (EPICS)
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $198,607
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 52
WBS Title: Central I&C Systems
Job Number: 5201
Job Title: Central I&C Systems
Job Manager: Paul Sichta
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort.
FY07$K
Activity ID | Activity Description | 41MS | 43MS/CC | 48MS | 37STK | 35 Trvl | ECEM | ECTB | EMTB | EASB | EEEM | EETB | Basis of Estimate
Originally manhours estimate based on NSTX experience. However, this estimate has been updated to reflect experience of experieince on other similar networking installation projects.
52-10 | Preliminary Design | [5 empty] | 40
52-20 | Final Design | [5 empty] | 40
52-30 | Procurement | 18 | 17 |  | 3 |  | 20
52-40 | EPICS Programming - Base | [5 empty] | 80
52-50 | EPICS Programming - VDCT db editor | [5 empty] | 40
52-60 | IOC Programming - MDSplus data & events | [5 empty] | 120
52-70 | OPC - EPICS/PLC Interface |  | 2 |  |  | 2 | 160
52-80 | Appl. Program | [5 empty] | 80
52-90 | Programming - misc. | [5 empty] | 100
52-100 | Installation | [5 empty] | 40 | 100 | 240 | 120
52-110 | Test | [5 empty] | 40
| Subtotal Job 5201 | 18 | 19 | 0 | 3 | 2 | 720 | 100 | 240 | 120 | 0 | 0
| M&S Details: | K$ | Basis of M&S Estimate
| Travel/training | 2 | Based on recent NSTX experience and other lab infrastructure projects
| NTC web cam (4) | 3 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| PC - appl. TBD (2) | 6 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| Linux soft IOC (2) | 3 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| OPC client & server HW/SW/TRNG (for T/C) | 10 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| EPICS server (use NSTX) |  | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| EPICS gateway | 8 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| misc | 10 | Based on recent purchased of parts for NSTX and other lab infrastructure projects
| Total M&S | 42

## Table II - M&S
WBS Number: 52
WBS Title: Central I&C Systems
Job Number: 5201
Job Title: Central I&C Systems
Job Manager: Paul Sichta
Weldments & Assy H/w
Materials and Subcontracts (M&S) |  | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 52
WBS Title: Central I&C Systems
Job Number: 5201
Job Title: Central I&C Systems
Job Manager: Paul Sichta
In-house Fabrication and Assembly and Installation
See Table I

## Table IV - Conting & Risk
WBS Number: 52
WBS Title: Central I&C Systems
Job Number: 5201
Job Title: Central I&C Systems
Job Manager: Paul Sichta
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although PDR, some more design needed to finalize.
-10%/+15%
| Design Complexity |  |  | X |  | Duplication of NSTX architecture
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)