## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
Description:
The Utility Systems (WBS 63) are required to provide service manifolds around the NCSX stellarator for compressed air, vacuum pump venting and gaseous nitrogen. Utility Systems are comprised of three (3) service manifolds around the NCSX vacuum vessel: one for vacuum venting; one for GN2 service; and one for compressed air. The WBS element only consists of the effort to provide the design, fabrication and installation of a manifold system around the NCSX stellarator for compressed air, vacuum pump venting and gaseous nitrogen.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $116,634
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
|  | FY07$K |  |  |  |  | HOURS
|  | 1.308 | 1000 | 1716 | 1716 | 1716 | 168.7 | 168.7 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33
TASK DESCRIPTION |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNLEM | ORNLDSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | Basis of Estimae
Design
| Preliminary Design | [7 empty] | 60 |  |  |  |  | 80 |  |  |  |  | Engineering judgement based on NSTX experience.
PDR
| Final design | [7 empty] | 20 |  |  |  |  | 80 |  |  |  |  | Engineering judgement based on NSTX experience.
FDR
Procrurement & Fabrication/Installation
Procurement lead time and award
| Vent System Procurements | 22207 | [6 empty] | 40 |  |  | 322 | [6 empty] | See Material Take Offs in Table V
| Air System Procurements | 2191 | [16 empty] | See Material Take Offs in Table V
PTP Testing | [8 empty] | 8 |  |  | 40 | [6 empty] | Engineering judgement based on NSTX experience.
| TOTALS | 24398 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 0 | 0 | 362 | 0 | 160 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
Materials and Subcontracts (M&S) | Basis of Estimate
M&S in Table I

## Table III - FabAssy & Instl
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
In-house Fabrication and Assembly and Installation
Fabrication & Installation in Table I

## Table IV - Conting & Risk
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Design not complicated, but still in a conceptual stage.
-10%/+15%
| Design Complexity |  |  | X |  | Standard piping -- off-the-shelf components
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V -Basis of Estimate
WBS Number: 63
WBS Title: Utility Systems
Job Number: 6301
Job Title: Utility Systems
Job Manager: Larry Dudek
Backup Data
Vent Systems Material Takeoffs
Air Systems Material Takeoffs