## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 74
WBS Title: Machine Assembly Planning & Oversight
Job Numbers: 7401 and 7451
Job Title: Machine Assembly Planning & Oversight (7401)
Job Title: ORNL Support of Redesigns (7451)
Job Manager: Erik Perry (7401) and Mike Cole (7451)
Description:
This WBS element includes those activities associated with planning the assembly and installation, of the NCSX device. It includes the Construction Management coordination between WBS elements whose activities directly involve the assembly of the NCSX components in the NCSX test cell and basement. It also includes participation in design reviews by the Construction Manager to assure the constructability of the NCSX facility.
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $1,429,863
Approvals:
____________________________________ ___________________
Job Manager Date
| ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________ | ____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 74
WBS Title: Machine Assembly Planning & Oversight
Job Numbers: 7401 and 7451
Job Title: Machine Assembly Planning & Oversight (7401)
Job Title: ORNL Support of Redesigns (7451)
Job Manager: Erik Perry (7401) and Mike Cole (7451)
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [16 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EAEM Dsn | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
None - this is an assembly operation

## Table II - M&S
WBS Number: 74
WBS Title: Machine Assembly Planning & Oversight
Job Numbers: 7401 and 7451
Job Title: Machine Assembly Planning & Oversight (7401)
Job Title: ORNL Support of Redesigns (7451)
Job Manager: Erik Perry (7401) and Mike Cole (7451)
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
None - this is an assembly operation

## Table III - FabAssy & Instl
WBS Number: 74
WBS Title: Machine Assembly Planning & Oversight
Job Numbers: 7401 and 7451
Job Title: Machine Assembly Planning & Oversight (7401)
Job Title: ORNL Support of Redesigns (7451)
Job Manager: Erik Perry (7401) and Mike Cole (7451)
In-house Fabrication and Assembly and Installation
Job 7401 - Machine Assembly Planning & Oversight | [11 empty] | Basis of Estimate
|  | K$ | Hours | [5 empty] | Duration in Shifts | Persons per Shift | Assumptions | The plan estimate is based on the time required for the preparation of the existing assembly plan. The LOE oversight is based on the actual costs for the NSTX assembly oversight and the TFTR D&D Project oversight.
Description of Task | ACT | M&S | EAEM | Metrology | ORNL EM | EMEM | EMSM | EMTB
LOE FY07 prior to assembly starting | 714.020 |  |  |  |  | 120 | 90
Update Final Assembly Plan | [5 empty] | 160 | [5 empty] | Based on time to do existing plan
LOE during assembly (thru first plasma) 1.0 fte each EM and SM | 714.030 |  |  |  |  | 1.0 fte | 1.0 fte |  |  |  |  | LOE based on TFTR & NSTX Assembly. (1.0 fte only is required on 2nd shift if used)
Test Cell 110v outlets | 7502-001 | [5 empty] | 48 |  |  |  | GPP Funded
Test Cell 208v outlets | 7502-002 | [5 empty] | 24 |  |  |  | GPP Funded
Subtotal Job 7401 |  | 0 | 0 | 0 |  | 280 | 162 | 0
Job 7451 - ORNL Support of Redesigns | [11 empty] | Basis of Estimate
|  | K$ | Hours | [5 empty] | Duration in Shifts | Persons per Shift | Assumptions | The plan estimate is based on the time required for the preparation of the existing assembly plan. The LOE oversight is based on the actual costs for the NSTX assembly oversight and the TFTR D&D Project oversight.
Description of Task | ACT | M&S | EAEM | Metrology | ORNL EM | EMEM | EMSM | EMTB
ORNL support of re-designs | 714.020 | 12 |  |  | 2505 | [6 empty] | Reiersen / ORNL requirement
Subtotal Job 7451 |  | 12 | 0 | 0 | 2505 | 0 | 0 | 0

## Table IV - Conting & Risk
WBS Number: 74
WBS Title: Machine Assembly Planning & Oversight
Job Numbers: 7401 and 7451
Job Title: Machine Assembly Planning & Oversight (7401)
Job Title: ORNL Support of Redesigns (7451)
Job Manager: Erik Perry (7401) and Mike Cole (7451)
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range |  | Comments/Other Considerations
Job 7401
| Design Maturity |  |  | X |  | Linked with Job 7503 => Estimated without detailed drawings. Significant uncertainty that current concept will stay the same - see Residual Risks below.
-20%/+40%
| Design Complexity |  | X |  |  | Linked to Job 7503 => Experienced in assembly fusion devices, but tolerances exceed anything done before.
Job 7451
| Design Maturity |  |  | X |  | Linked with Job 7503 => Estimated without detailed drawings. Significant uncertainty that current concept will stay the same - see Residual Risks below.
-20%/+40%
| Design Complexity |  | X |  |  | Linked to Job 7503 => Experienced in assembly fusion devices, but tolerances exceed anything done before.
| Other Comments: |  |  |  |  | This job is LOE - as WBS 75 increases in duration this job will increase in duration the same amount.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
7401 | Loss or prolonged unavailability of certain key personnel (Viola or Perry) from the project could substantially impact the schedule. |  |  |  | VU | Viola and Perry will be cross-trained such that each could od the other's job |  | Estimated impact is <1 months on the critical path. Cost estimates cover 0-1 months of near term FPA assembly (in addition to the standing army costs addressed under schedule impact). | +$240K | +$480K | +1.00 | +2.00
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)