## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
Description:
This WBS element consists of those activities associated with the final assembly of the stellarator core in the NCSX Test Cell
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07):
Job 7501: $1,436,581
Job 7503: $4,645,955
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
Description:
None - this is an assembly operation

## Table II - M&S
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
This is an assembly operation - M&S included in Table III

## Table III - FabAssy & Instl
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
In-house Fabrication and Assembly and Installation
Job 7501 - Construction Support Crew | [12 empty] | Basis of Estimate
|  | K$ |  | Hours |  |  |  |  | Duration in Shifts | Persons per Shift |  | Assumptions | Note: final designs not yet available - estimates based on conceptual information from others
Description of Task | ACT | M&S | Travel | EAEM | Metrology | EMEM | EMSM | EMTB
LOE Construction Support Crew during machine assy | 7501-05 | [5 empty] | .75 fte | 2.0 fte |  | 2.75 |  | crane/fork lift operator 1.0 fte, rigger 1.0 fte, tool crib .75 fte (applies to 2 nd shifht also if used) | NSTX assembly
Total Job 7501 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Job 7503 - Construction Support Crew | [12 empty] | Basis of Estimate
|  | K$ |  | Hours |  |  |  |  | Duration in Shifts | Persons per Shift |  | Assumptions | Note: final designs not yet available - estimates based on conceptual information from others
Description of Task | ACT | M&S |  | EAEM | Metrology | EMEM | EMSM | EMTB
Assembly of Components for Others
Fabricate assembly structure |  | 80 |  |  |  | 96 | 240 | 960 | 20 | 6 | 1376 | Design by WBS 1803
Fabricate structure to go between assembly sleds & FPAs |  | 80 |  |  |  | 96 | 240 | 960 |  |  | 1376 | EWDA - same magnitude as assembly sleds is assumed
Assemble 3 FPA support stands | [5 empty] | 48 | 120 | 480 | 15 | 4 | 648
Assemble 3 VV spool piece support stands | [5 empty] | 32 | 80 | 320 | 10 | 4 | 432
Assemble machine base structure | [5 empty] | 32 | 80 | 320 | 10 | 4 | 432
Assemble 3 FPA installation carts | [5 empty] | 32 | 80 | 320 | 10 | 4 | 432
Fabricate 3 laser support poles |  | 24 | [5 empty] | 480 | 30 | 2 | 504
Fabricate 3 concrete blocks for testing of assembly structure with metrology |  | 18 |  |  |  | 20 |  | 192 | 12 | 2 | 230 | Req'd for concrete block on assembly structure test - T. Brown requirement
Exercise assembly structure with concrete block and metrology before start of assembly | [5 empty] | 80 | 320 | 640 | 40 |  | 1040 | T. Brown requirement
Install test cell metrology site monuments and check them |  |  |  |  | 640 | 64 | 160 |  | 20 | 4 | 864 | T. Brown requirement - re-doing what is done for station 5 work
Test test cell floor deflections with concrete block placed at FPA support positions |  |  |  |  | 120 | 48 | 120 | 480 | 15 | 4 | 768 | T. Brown requirement
Exercise assembly structure with FPA-1 before start of assembly |  | 0 |  |  | 320 | 80 | 320 | 640 | 40 |  | 1360 | Review requested 8 weeks of trial runs/metrology
Machine Assembly | [10 empty] | 0
Install Permanent Base Plates/Columns | 7503-020 |  |  | 60 |  |  | 120 | 480 | 10 | 6 | 660 |  | TFTR and NSTX assembly
Install temp assembly structure | [5 empty] | 72 | 180 | 720 | 15 | 6 | 972 |  | TFTR and NSTX assembly
Install Lower PF 4,5&6 into prelim position | 7503-060 | [5 empty] | 16 | 32 | 1 | 4 | 48 |  | TFTR and NSTX assembly
Install 3 Spool Pieces on fixt & test movement | 7503-070 |  |  | 40 | 80 |  | 80 | 320 | 10 | 4 | 520 |  | TFTR and NSTX assembly
FPA-1 Installed on temp assembly sleds | 7503-080 | [9 empty] | 0 |  | TFTR and NSTX assembly
FPA-2 Installed on temp assembly sleds | 7503-110 | [9 empty] | 0 |  | TFTR and NSTX assembly
FPA-3 Installed on temp assembly sleds | 7503-150 | [9 empty] | 0 |  | TFTR and NSTX assembly
FPA-1 installation and assembly test |  |  |  |  | 320 | 80 | 320 | 640 | 20 |  | 1360 | T. Brown requirement
FPA-2 installation and assembly test |  |  |  |  | 320 | 80 | 320 | 640 | 20 |  | 1360 | T. Brown requirement
FPA-3 installation and assembly test |  |  |  |  | 320 | 80 | 320 | 640 | 20 |  | 1360 | T. Brown requirement
Test movement of FPAs & position checks. | 7503-120 |  |  | 20 | 40 |  | 40 | 160 | 5 | 4 | 260 |  | TFTR and NSTX assembly
MC Shims |  | 36 |  | 60 | 32 | 86 | 216 | 864 | 18 | 6 | 1294 | shims provided by others; M&S for final sizing | TFTR and NSTX assembly
Install inboard and outboard shims | [10 empty] | 0 |  | TFTR and NSTX assembly
Move all FPAs together, check fitup, tack shims | [10 empty] | 0 |  | TFTR and NSTX assembly
Weld inboard shims on mating flanges | [10 empty] | 0 |  | TFTR and NSTX assembly
Install end TF coils |  |  |  |  | 48 |  | 48 | 192 | 6 | 4 | 288 |  | TFTR and NSTX assembly
Install spacer supports and spacers | [6 empty] | 16 | 64 | 2 | 4 | 80 |  | TFTR and NSTX assembly
Move FPAs & spacers together & check fitup |  |  |  |  | 32 |  | 48 | 192 | 6 | 4 | 272 |  | TFTR and NSTX assembly
Remove spacers and machine to fit | [7 empty] | 64 | 4 | 2 | 64 |  | TFTR and NSTX assembly
Re-install spacers | [6 empty] | 16 | 64 | 2 | 4 | 80 |  | TFTR and NSTX assembly
Position all FPA's / Spool Pieces @ MC Interface | 7503-160 |  |  | 24 | 48 |  | 48 | 192 | 6 | 4 | 312 |  | TFTR and NSTX assembly
Install local Platforms around FPA-1 | 7503-090 |  |  | 0 |  |  | 32 | 128 | 4 | 4 | 160 |  | TFTR and NSTX assembly
Install local Platforms around FPA-2 | 7503-130 |  |  | 0 |  |  | 32 | 128 | 4 | 4 | 160 |  | TFTR and NSTX assembly
Install local Platforms around FPA-3 | 7503-190 |  |  | 0 |  |  | 32 | 128 | 4 | 4 | 160 |  | TFTR and NSTX assembly
MC Interfaces: measure holes and mark bushings for eccentric drilling | [6 empty] | 24 | 96 | 3 | 4 | 120 | Field Period Assembly will fab and install all bushings except at three MC interfaces … at each of these 3 interfaces only 32 bushings will be fabricated during final assembly: 32 x 3 = 96 … 1 mh to measure and mark one bushing | TFTR and NSTX assembly
MC Interfaces: drill eccentric custom holes in bushings |  | 6.048 |  |  |  |  | 24 | 96 | 3 | 4 | 126.048 | 96 bushings x 1/8 day to set up and drill each bushing with a one man crew, four crews; M&S for consumeable tools at $63 per bushing | TFTR and NSTX assembly
Measure vessel gaps to determine spool piece dimensions |  |  |  | 288 | 288 |  |  |  | 18 | 2 | 576 |  | TFTR and NSTX assembly
Spool piece installation test |  |  |  |  | 320 | 80 | 320 | 640 | 20 |  | 1360 | T. Brown requirement
Initial machining of spool pieces (complete one side) |  | 45 |  |  |  | 12 |  |  | 45 |  | 57 | Spool pieces must go outside for machining | TFTR and NSTX assembly
Final machining of spool pieces |  | 45 |  |  |  | 12 |  |  | 45 |  | 57 | Spool pieces must go outside for machining | TFTR and NSTX assembly
MC Interfaces: bolt together | [5 empty] | 29 | 72 | 288 | 36 | 6 | 389 | all materials provided by others | TFTR and NSTX assembly
Retorque all super-nuts after 30 days | [5 empty] | 58 | 144 | 576 | 12 | 6 | 778 | Viola requirement
Raise permanent supports to take machine loads |  |  |  |  | 180 | 72 | 180 | 720 | 15 | 6 | 1152 |  | TFTR and NSTX assembly
Remove temporary assembly structure | [6 empty] | 24 | 96 | 2 | 6 | 120 |  | TFTR and NSTX assembly
Install/Level FPA's and Spool Piece supports | 7503-030 |  |  | 120 | 240 |  | 240 | 960 | 30 | 4 | 1560 |  | TFTR and NSTX assembly
FPA Metrology Checks to Assure Alignment | 7503-170 |  |  | 40 | 40 |  |  | 40 | 5 | 1 | 120 |  | TFTR and NSTX assembly
Mate-up and weld all VV-to-Spool interfaces | 7503-200 |  |  |  | 180 |  | 240 | 1440 | 30 | 3 | 1860 | Weld time doubled to account for expected significant flange mismatch .. Can only use one welder/pedalman/safety watch at a time … assume two shifts | TFTR and NSTX assembly
Weld on port 4's |  |  |  |  | 60 |  | 180 | 720 | 30 | 3 | 960 | 6 ports | TFTR and NSTX assembly
Install e-beam mapping equipment | [5 empty] | 40 | 80 | 320 | 10 | 4 | 440 | EWDA | TFTR and NSTX assembly
Install vacuum pumping system | 7503-240 | [5 empty] | 40 | 160 | 5 | 4 | 200 |  | TFTR and NSTX assembly
Pumpdown & leak check VV | 7503-260 | [5 empty] | 120 | 480 | 15 | 4 | 600 |  | TFTR and NSTX operations
Fit-up all TF coils | 7503-210 |  |  | 40 | 200 |  | 200 | 800 | 25 | 4 | 1240 |  | TFTR and NSTX assembly
Install TF alignment and traction ring | [10 empty] | 0 |  | TFTR and NSTX assembly
Pull TF coils radially inward & verify nose fir-up | [10 empty] | 0 |  | TFTR and NSTX assembly
Lock TF coils at four support locations | [10 empty] | 0 |  | TFTR and NSTX assembly
Install MC structure insulation boots | 7503-240.1 | [5 empty] | 80 | 320 | 10 | 4 | 400 | EWDA | TFTR and NSTX assembly
Seal gaps in MC shims, cooling tubes, etc for insul pour | [6 empty] | 160 | 640 | 20 | 4 | 800 |  | TFTR and NSTX assembly
Fill MC/VVSA annulus with pourable Aerogel insulation | 7503-240.2 | [5 empty] | 16 | 64 | 2 | 4 | 80 |  | TFTR and NSTX assembly
Install LN2 manifolds | [6 empty] | 80 | 320 | 10 | 4 | 400 | Fabrication by WBS 161; instl EWDA | TFTR and NSTX assembly
Complete Elect Pwr connections | 7503-320 | [5 empty] | 160 | 960 | 30 | 4 | 1120 | Provided by WBS 162; instl EWDA | TFTR and NSTX assembly
Install in-cryostat cabling for electric power to coils | [10 empty] | 0 |  | TFTR and NSTX assembly
Connect cabling and I&C to MC and TF coils | [10 empty] | 0 |  | TFTR and NSTX assembly
Complete mag diag & machine I&C | 7503-321 | [5 empty] | 160 | 320 | 10 | 4 | 480 | Provided by WBS ?; instl EWDA | TFTR and NSTX assembly
Install PF Solenoid and PF 1a U/L into position | 7503-290 |  |  | 16 | 32 |  | 32 | 128 | 4 | 4 | 208 | All I&C in place on solenoid and PF 1a U/L mounted on support structure prior to arrival in Test Cell | TFTR and NSTX assembly
Align guide mechanism for solenoid installation | [10 empty] | 0 |  | TFTR and NSTX assembly
Install solenoid support structure | [10 empty] | 0 |  | TFTR and NSTX assembly
Install solenoid assembly | [10 empty] | 0 |  | TFTR and NSTX assembly
Connect cabling, LN2 and I&C to solenoid | [6 empty] | 8 | 32 | 1 | 4 | 40 |  | TFTR and NSTX assembly
Install PF4L | [6 empty] | 8 | 32 | 1 | 4 | 40 |  | TFTR and NSTX assembly
Connect cabling, LN2 and I&C to PF4L | [6 empty] | 8 | 32 | 1 | 4 | 40 |  | TFTR and NSTX assembly
Adjust spring compression in solenoid support structure | [6 empty] | 8 | 32 | 1 | 4 | 40 |  | TFTR and NSTX assembly
Raise lower PF 5&6 coils into final position | 7503-270 |  |  | 24 |  |  | 48 | 192 | 6 | 4 | 264 |  | TFTR and NSTX assembly
Install Upper PF4, 5 & 6 coils | 7503-280 |  |  | 24 |  |  | 48 | 192 | 6 | 4 | 264 |  | TFTR and NSTX assembly
Install Cryostat Base, vapor barrier & port boots | 7503-340 | [5 empty] | 80 | 320 | 10 | 4 | 400 |  | TFTR and NSTX assembly
Install elec pwr, LN2, & instr feedthrus thru cryo base | [6 empty] | 40 | 160 | 5 | 4 | 200 | EWDA | TFTR and NSTX assembly
Integrated electrical testing | [5 empty] | 80 | 80 | 320 | 10 | 4 | 480 |  | TFTR and NSTX operations
Install transition box, cabling and connect to power supplies | [6 empty] | 80 | 320 | 10 | 4 | 400 | EWDA | TFTR and NSTX assembly
Complete LN2 connections from coils to manifolds | 7503-310 | [5 empty] | 80 | 320 | 10 | 4 | 400 |  | TFTR and NSTX assembly
Connect coil and VV instrumentation | [6 empty] | 80 | 320 | 10 | 4 | 400 | EWDA | TFTR and NSTX assembly
Connect 150C bakeout | [6 empty] | 40 | 160 | 5 | 4 | 200 | EWDA | NSTX operations
Prepare for and perform warm coil testing | [10 empty] | 0 | covered in other WBS
Install cryostat cooling system and instrumentation | [6 empty] | 320 | 1280 | 20 | 8 | 1600 | EWDA | TFTR and NSTX assembly
Install Cryostat | [10 empty] | 0 |  | TFTR and NSTX assembly
Install Cryostat upper section and port boots | 7503-350 | [5 empty] | 80 | 320 | 10 | 4 | 400 |  | TFTR and NSTX assembly
Install Midplane Cryostat sections and port boots | 7503-360 | [5 empty] | 120 | 480 | 15 | 4 | 600 |  | TFTR and NSTX assembly
Install Cryostat Circulation Duct | 7503-370 | [5 empty] | 40 | 160 | 5 | 4 | 200 | Cryo cooling system instl in WBS 623 | TFTR and NSTX assembly
PTP and Cooldown | 730.8200 |  |  |  |  | 80 | 80 | 480 |  |  | 640 |  | TFTR and NSTX operations
Total Job 7503 |  | 334.048 | 0 | 756 | 3860 | 1489 | 7468 | 26776
40683.048

## Table IV - Conting & Risk
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
Job 7501 |  |  |  |  | -20%/+40%
| Design Maturity |  |  | X |  | Estimated without detailed drawings. Significant uncertainty that current concept will stay the same - see Residual Risks below.
| Design Complexity |  | X |  |  | Follows tasks in Job 7503 - but most are LOE activities
Job 7503 |  |  |  |  | -20%/+40%
| Design Maturity |  |  | X |  | Estimated without detailed drawings. Significant uncertainty that current concept will stay the same - see Residual Risks below.
| Design Complexity |  | X |  |  | Experienced in assembly fusion devices, but tolerances exceed anything done before.
| Other Comments: |  |  |  |  | Major source of uncertainty is in the machine assembly concepts which are still evolving. See Residual Risks below.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
7501 - NONE
7503 | Additional trim coils may be required to suppress field errors from n>1 modes |  |  |  | U | Analysis being performed to firm up requirements | Costs could more than double the present estimate | 200 | 400 | 0 | 0
| "Back office" support for FPA and final assembly becomes a chronic bottleneck, stretching out the time required to complete assembly operations |  |  |  | VU | Additional support budgeted for Brown, Brooks, and Ellis providing "2 deep" back office support. Should be available to mitigate peak demands once training in key skills is completed. | Estimated impact is <2 months on the critical path. Cost impact covers up to 2 months of FPA/final assembly. | 0 | 600 | 0 | 2
| Insulation on TF/PF coil fails during initial cooldown and testing requiring in situ repair |  |  |  | VU | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Ring tests are performed to reveal low resistance turn-to-turn shorts at RT. | Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellrator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2
| Insulation on TF/PF coil fails during initial cooldown and testing requiring dismantling stellarator core |  |  |  | VU | Ist of each kind will be tested at cryogenic temperature at elevated (50% higher) voltage for faults to ground. All coils will be tested at RT at elevated (50% higher) voltage for faults to ground. Ring tests are performed to reveal low resistance turn-to-turn shorts at RT. | Crisis event not covered by contingency
| Insulation on modular coil fails during initial cooldown and testing requiring in situ repair |  |  |  | VU | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. | Repair in situ is assumed recovery scenario taking 2-3 months. 1 month to warmup and cooldown the stellrator core. 3 techs/1 engr for duration of active repair )1-2 months). | 50 | 150 | 1 | 2
| Insulation on modular coil fails during initial cooldown and testing requiring stellarator core disassembly |  |  |  | VU | C1 tested at full current at cryogenic temeprature. All modular coils will be tested at RT at elevated (50% higher) voltage for faults to ground. | Crisis event not covered by contingency
| Unanticipated problems with cryostat penetrations (icing, excessive condensation). May require warming up the stellarator core to effect repair with consequent impacts to critical path activities. |  |  |  | U | Rapid repair materials will be on hand. | Nominally repaired with a 4-man crew in 1 week with 3 weeks for warmup/cooldown (if required) | 15 | 30 | 0.25 | 1
| Assembly sled for final assembly is not adequately stiff or does not provide repeatable motion |  |  |  | U | Functionality of sled will be determined first with concrete blocks and later with first FP. Ample time to make design modifications between arrival of the first and third FPs. | Nominal cost impact is 1 man-month of engineering design and up to half the fabrication cost of the sled | 25 | 75 | 0 | 0
| TC floor is not adequately rigid for present metrology plan |  |  |  | VU | Copper sheet and spongy surface removed from TC floor. Fiducials will be placed. Concrete blocks will be placed to see if floor is adequately stiff. | Nominal cost impact is 2 man-months of engineering design and $50-150K for local reinforcement of building structures | 50 | 200 | 0 | 0
| Modular coils are shorted across toroidal break between field periods |  |  |  | NC | Need very low impedence, multiple shorts to get into trouble
| Metrology equipment and general purpose tooling/ lifting equipment (e.g.cranes) not available to support the schedule |  |  |  | U | Maintenance contract mitigates impact of metrology equipment. Additional $200K budgeted for a 3rd laser tracker and/or spare metrology equipment. Should result in improved efficiency. | Up to 2 week impact on FPA and critical path. FPA cost impact assumed to be $300k/mo. | 0 | 150 | 0 | 0.5
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 75
WBS Title: Machine Assembly Operations
Job Numbers: 7501 and 7503
Job Title: Construction Crew Support (7501)
Job Title: Machine Assembly Operations (7503)
Job Manager: Erik Perry
ORNL Updated Title III Engineering (6/8/2007)
Station No. | start date | end date | days | weeks |  | 1st period | 2nd period | 3thd period |  | ENGR | Designer | Total hrs
station 2 | 2007-10-01 | 2009-03-01 | 517 | 73.8571 | 2954.2857 | 590.8571 | 393.9048 | 196.9524 | 1181.7143 | 590.8571 | 590.8571 | 1181.7143
station 3 | 2008-02-01 | 2009-07-01 | 516 | 73.7143 | 2948.5714 | 491.4286 | 294.8571 | 98.2857 | 884.5714 | 442.2857 | 442.2857 | 884.5714
Total Hours
station 5 | 2008-04-01 | 2009-09-01 | 518 | 74 | 2960 | 493.3333 | 296 | 98.6667 | 888 | 444 | 444 | 888 | Station 2 to 5 (FPA - Job 1802) | 2954.2857
station 6 | 2009-06-01 | 2010-10-01 | 487 | 69.5714 | 2782.8571 | 742.0952 | 556.5714 | 371.0476 | 1669.7143 | 1669.7143 | 834.8571 | 2504.5714 | Station 6 (Fnl Mach Assy - Job 7503) | 2504.5714
[6 empty] | Station 2 |  | Coverage |  |  | Title III Support Travel
|  |  | 701 | 100.1429 | 4005.7143 | 1st period | 60% | 60% Engr/Dsn |  | Job 1802 | Job 7503
[10 empty] | 4500 |  | FY2007
[6 empty] | 2nd period | 40% | 40% Engr/Dsn |  | 9000 |  | FY2008
[10 empty] | 4500 | 1500 | FY2009
[6 empty] | 3thd period | 20% | 20% Engr/Dsn |  |  | 6000 | FY2010
[11 empty] | 4500 | FY2011
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
[6 empty] | Station 3 |  | Coverage
[6 empty] | 0 | 50% | 50% Engr/Dsn
[6 empty] | 590.8571 | 30% | 30% Engr/Dsn
[6 empty] | 491.4286 | 10% | 10% Engr/Dsn
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
[6 empty] | Station 5 |  | Coverage
[6 empty] | 0 | 50% | 50% Engr/Dsn
[6 empty] | 590.8571 | 30% | 30% Engr/Dsn
[6 empty] | 491.4286 | 10% | 10% Engr/Dsn
[6 empty] | ENGR | 50% | Average
[6 empty] | Designer | 50% | Average
[6 empty] | Station 6 |  | Coverage
[6 empty] | 0 | 80% | 80% Engr/Dsn
[6 empty] | 590.8571 | 60% | 60% Engr/Dsn
[6 empty] | 491.4286 | 40% | 40% Engr/Dsn
[6 empty] | ENGR | 100% | Average
[6 empty] | Designer | 50% | Average
Assume each period is 1/3 of the number of weeks