## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 85
WBS Title: Integrated Systems Testing
Job Number: 8501
Job Title: Integrated Systems Testing
Job Manager: Charlie Gentile
Description:
This WBS (85) covers the planning, document preparation, and execution of the NCSX integrated system testing and startup activities, culminating in First Plasma
Schedule:
See Attached
ETC Cost: (loaded in as-spent dollars from 5/1/07): $764,833
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 85
WBS Title: Integrated Systems Testing
Job Number: 8501
Job Title: Integrated Systems Testing
Job Manager: Charlie Gentile
FY07$K
|  |  |  | 1308 | 1000 | 1716 | 1716 | 1716 | 156.5 | 128.59 | 108.44 | 78.33 | 180.79 | 116.7 | 168.88 | 138.6 | 138.6 | 78.33 | 144.88 | 93.69 | 70.98 | 162.83 | Basis of Estimate
Task ID |  | TASK DESCRIPTION |  | 41 MS | 48 MS | 37 STK | 35 TRVL | 31 OT | EM EM | EM SM | EM SB | EM TB | EA EM | EA SB | EE EM | EE SM | EE SB | EE TB | EC EM | EC SB | EC TB | RM2 | These estimates are based on a CD-4 Startup Plan (dated April 2007) - The purpose of this Startup Plan is to identify those tasks, documents, actions, and reviews required for meeting the requirements of Critical Decision 4 (CD-4), NCSX First Plasma.
Documentation
|  | 1.0 fte Engineer | 28.5 | [5 empty] | 1140 | [13 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 fte Senior L&S | 28.5 | [6 empty] | 1140 | [12 empty] | Based on TFTR & NSTX experience & existing S/U documentation
Startup
|  | 1.0 Test director/physict in charge (PIC) @100% | 10 | [18 empty] | 400 | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 Chief Operations Engineer (COE) @85% | 10 | [5 empty] | 340 | [13 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 Project Engineer (wayne already at 75% in wbs82 | 10 | [9 empty] | 100 | [9 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 2.0 Machine technicians @ 85% | 10 | [7 empty] | 680 | [11 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 FCPC Tech @75% | 10 | [12 empty] | 300 | [6 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 Cryo sysw tech @75% | 10 | [8 empty] | 300 | [10 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 AC power Engr @75% | 10 | [11 empty] | 300 | [7 empty] | Based on TFTR & NSTX experience & existing S/U documentation
|  | 1.0 Computer Engr @75% | 10 | [15 empty] | 300
31
|  |  |  | 0 | 0 | 0 | 0 | 0 | 1480 | 1140 | 680 | 300 | 100 | 0 | 300 | 300 | 0 | 0 | 300 | 0 | 0 | 400
CD-4

## Table II - M&S
WBS Number: 85
WBS Title: Integrated Systems Testing
Job Number: 8501
Job Title: Integrated Systems Testing
Job Manager: Charlie Gentile
Description:
None - all labor.
Why do all of these formulas refer back to B87 => seems like it should progress with coil

## Table III Fab & Assy
WBS Number: 85
WBS Title: Integrated Systems Testing
Job Number: 8501
Job Title: Integrated Systems Testing
Job Manager: Charlie Gentile
Fabrication and Assembly

## Table IV - Conting & Risk
WBS Number: 85
WBS Title: Integrated Systems Testing
Job Number: 8501
Job Title: Integrated Systems Testing
Job Manager: Charlie Gentile
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | LOE effort dependent on length of schedule
-5%/+10%
| Design Complexity |  |  | X |  | No special assignments
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
8501 | Coils are hooked up with incorrect polarity |  |  |  | U | Tested during ISTP and fixed | Covered in estimate uncertainty with present mitigation plan
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)