## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Description:
Job 1408 consists of all the procured components for the modular coil windings, and includes the cable conductor, kapton and glass insulation, epoxy, coil clamps, cooling lines, lead blocks, fillers, etc. Job 1451 consists of all the labor required to wind conductor, vacuum bag, vacuum impregnate with epoxy, connect cooling lines, and inspect the modular coils. This WBS element consists of all punch list items need to finalize the fabrication of each modular coil.
Schedule:
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [16 empty] | Basis of Estimate
|  | FY07$K |  |  |  |  | HOURS
Task ID | Comments | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
No Design Work Associated with This Job

## Table II - M&S
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Materials and Supplies
All M&S included in Table III

## Table III Fab & Assy
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Fabrication and Assembly
Conditions and Basis for Estimate
1) All estimates are based on work performed from May 1, 2007 through the end of modular coil fabrication program
2) Estimates are based on actual in-field times as well as consultation with metrology personnel and technicians
3) M&S based upon actual contracts and monthly M&S supporting winding activities on first nine coils - see specifics in M&S below
|  | EAEM | EAEM | EMSM | EMEM
TASK DESCRIPTION |  | Chrz. | Raft. | Meighan | Languish
|  | hours | hours | hours | hours
Engineering and Oversight |  | 70% | 40% | 70% | 40%
LOE | 9450-1***-1451 | 120 hr/month | 70 hr/month through completion of winding | 120 hr/month | 70 hr/month
nominal hours for 14mo. Production |  | 1680 | 980 | 1680 | 980
Casting Preparation |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours]
RESA Building Activities
Unload & unbox winding form | 9450-1***-1459 | 0.5 | 0 | 0 | 0 | 12 | 5 | 60 | B5 & B6; A5 & A6; C6
Inspect casting [surfaces, magnetic permeability] | 9450-1***-1451 | 0.5 | 1 | 9 | 4.5 | 0 | 5 | 22.5 | B5 & B6; A5 & A6; C6
Winding form modifications [grinding, welding, deburring, etc.] | 9450-1***-1459 | 3 | 0 | 0 | 0 | 48 | 5 | 240 | B5 & B6; A5 & A6; C6
Station 1a/4 Activities
Position & mount WF to support ring | 9450-1***-1451 | 2 | 3 | 9 | 54 | 32 | 6 | 516 | B4 thru B6; A5 thru A6; C6
Install coil in station 4 turning fixture | 9450-1***-1451 | 1 | 3 | 9 | 27 | 16 | 6 | 258 | B4 thru B6; A5 thru A6; C6
Install weights and balance casting and ring assembly | 9450-1***-1451 | 1 | 2 | 10 | 20 | 0 | 6 | 120 | B4 thru B6; A5 thru A6; C6
Weld monuments, stud adapters & lead nuts | 9450-1***-1451 | 2.5 | 1 | 9 | 22.5 | 16 | 7 | 269.5 | B3 thru B6; A5 thru A6; C6
Measure casting wings using metrology equipment | 9450-1***-1451 | 2 | 2 | 8 | 32 | 0 | 5 | 160 | B5 thru B6; A5 thru A6; C6
Install studs for winding clamps | 9450-1***-1451 | 2 | 3 | 9 | 54 | 0 | 7 | 378 | B3 thru B6; A5 thru A6; C6
Electrical test poloidal break | 9450-1***-1451 | 0.5 | 1 | 9 | 4.5 | 0 | 7 | 31.5 | B3 thru B6; A5 thru A6; C6
Clean casting [Inspect and clean all holes] | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 7 | 126 | B3 thru B6; A5 thru A6; C6
Install Kapton edging and mold release winding surface | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 7 | 252 | B3 thru B6; A5 thru A6; C6
Fitup Lead blocks and terminals [Remove lead blocks] | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 7 | 126 | B3 thru B6; A5 thru A6; C6
Cladding final clean & Kapton [Parallel activity] | 9450-1***-1451 | 7 | 1 | 9 | 63 | 0 | 6 | 378 | B4 thru B6; A5 thru A6; C6
Install inner cladding plates and cooling Tubes | 9450-1***-1451 | 5 | 3 | 9 | 135 | 0 | 7 | 945 | B3 thru B6; A5 thru A6; C6
|  | 27 |  |  | 488.5 | 124
[8 empty] | 3882.5 | TOTALS hours
Coil Winding Station 2 and 3 |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] |  | Revised
Prep for Winding
Prepare coil for transfer | 9450-1***-1451 | 0.5 | 2 | 9 | 9 | 0 | 7 | 63 | B3 thru B6; A5 thru A6; C6
Install winding form in turning fixture | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 7 | 280 | B3 thru B6; A5 thru A6; C6
Install upper Tee for coil clamps | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 7 | 252 | B3 thru B6; A5 thru A6; C6
Install/set winding clamps side bars A & B | 9450-1***-1451 | 4 | 3 | 9 | 108 | 0 | 7 | 756 | B3 thru B6; A5 thru A6; C6
Prep groundwrap insulation [Parallel activity] | 9450-1***-1451 | 6 | 1 | 9 | 54 | 0 | 7 | 378 | B3 thru B6; A5 thru A6; C6
Re-install G-11 lead blocks- sides A & B | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 8 | 144 | B3 thru B6; A4 thru A6; C6
Position inner GW insulation onto winding form (sides A & B) | 9450-1***-1451 | 7 | 2 | 9 | 126 | 0 | 8 | 1008 | B3 thru B6; A4 thru A6; C6
Position lacing strips sides A & B | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 8 | 288 | B3 thru B6; A4 thru A6; C6
Wind Side "A"
Braze & secure 1st. coil lead set [inc. brazing] | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 8 | 288 | B3 thru B6; A4 thru A6; C6
Position leads & Wind side A | 9450-1***-1451 | 12 | 2.5 | 10 | 300 | 0 | 8 | 2400 | B3 thru B6; A4 thru A6; C6
Reposition coil from side A to side B | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 8 | 320 | B3 thru B6; A4 thru A6; C6
Wind Side "B"
Braze & secure 1st. coil lead set [inc. brazing] | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 8 | 288 | B3 thru B6; A4 thru A6; C6
Position leads & Wind side B | 9450-1***-1451 | 12 | 2.5 | 10 | 300 | 0 | 8 | 2400 | B3 thru B6; A4 thru A6; C6
Final coil winding activities
Measure, reposition & re-measure coil bundle [sides A & B] | 9450-1***-1451 | 8 | 3 | 9 | 216 | 0 | 8 | 1728 | B3 thru B6; A4 thru A6; C6
Secure Lacing | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 8 | 288 | B3 thru B6; A4 thru A6; C6
Complete groundwrap installation | 9450-1***-1451 | 6 | 2 | 9 | 108 | 0 | 8 | 864 | B3 thru B6; A4 thru A6; C6
Unanticipated Delays/Rework Activities
Tasks TBD | 9450-1***-1451 | 3 | 3 | 9 | 81 | 0 | 8 | 648
|  | 35.75 |  |  | 1548 | 32 |  | 12393 | TOTALS hours
1580
Final Coil prep & Mold Application [Stations 2 & 3] |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining | Revised
Final Coil Prep
Clean chill plates [Parallel activity] | 9450-1***-1451 | 4 | 1 | 9 | 36 | 0 | 8 | 288 | Coils A4-A6; B3-B6 and C6
Install chill plates & Tubing | 9450-1***-1451 | 12 | 2.5 | 9 | 270 | 0 | 8 | 2160 | Coils A4-A6; B3-B6 and C6
Cut, braze, silverplate and position 2nd. coil lead set [side A] | 9450-1***-1451 | 3 | 2 | 9 | 54 | 0 | 8 | 432 | Coils A4-A6; B3-B6 and C6
Cut, braze, silverplate and position 2nd. Coil lead set [side B] | 9450-1***-1451 | 3 | 2 | 9 | 54 | 0 | 8 | 432 | Coils A4-A6; B3-B6 and C6
Soft solder and clean all lead joints | 9450-1***-1451 | 2 | 1 | 9 | 18 | 0 | 8 | 144 | Coils A4-A6; B3-B6 and C6
Install outer co-wound Diagnostic loops | 9450-1***-1451 | 2 | 2 | 9 | 36 | 0 | 8 | 288 | Coils A4-A6; B3-B6 and C6
Measure position of co-wound diagnostic loops | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 8 | 144 | Coils A4-A6; B3-B6 and C6
Perform pre-VPI elect. & pressure tests
Pressure test cryo lines | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 8 | 144 | Coils A4-A6; B3-B6 and C6
Perform preliminary [pre-vpi] electrical tests | 9450-1***-1451 | 0.5 | 2 | 10 | 10 | 0 | 8 | 80 | Coils A4-A6; B3-B6 and C6
Install bag mold around modular coil
Prep sprue sub-assemblies [Parallel activity] | 9450-1***-1451 | 1 | 1 | 9 | 9 | 0 | 8 | 72 | Coils A4-A6; B3-B6 and C6
Prep lead sprue sub-assemblies [Parallel activity] | 9450-1***-1451 | 0.5 | 1 | 9 | 4.5 | 0 | 8 | 36 | Coils A4-A6; B3-B6 and C6
Install G-11 final clamp pads & sprue bases | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 8 | 144 | Coils A4-A6; B3-B6 and C6
Finalize and secure G-11 lead box | 9450-1***-1451 | 1 | 1 | 9 | 9 | 0 | 8 | 72 | Coils A4-A6; B3-B6 and C6
Install glass roving and sheet over chill plates | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 8 | 144 | Coils A4-A6; B3-B6 and C6
Install silicone bag & sprues | 9450-1***-1451 | 5 | 2 | 9 | 90 | 0 | 8 | 720 | Coils A4-A6; B3-B6 and C6
Vacuum pumpdown/ RTV overcoat & leak repair | 9450-1***-1451 | 2 | 3 | 9 | 54 | 0 | 9 | 486 | Coils A4-A6; B2-B6 and C6
Install epoxy shell | 9450-1***-1451 | 2.5 | 3 | 9 | 67.5 | 0 | 9 | 607.5 | Coils A4-A6; B2-B6 and C6
|  | 21.25 |  |  | 784 | 0 |  | 6393.5 | TOTALS hours
VPI Activities (Station 5) |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Final VPI Prep
Prepare MC for transfer | 9450-1***-1451 | 0.5 | 2 | 9 | 9 | 0 | 9 | 81 | Coils A4-A6; B2-B6 and C6
Transfer modular coil to Autoclave | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 9 | 360 | Coils A4-A6; B2-B6 and C6
Prepare MC for VPI [Connect fill lines & TC; leak check] | 9450-1***-1451 | 3 | 3 | 8 | 72 | 0 | 9 | 648 | Coils A4-A6; B2-B6 and C6
Vacuum pumpdown & preheat mold and autoclave | 9450-1***-1451 | 2 | 3 | 10 | 60 | 0 | 9 | 540 | Coils A4-A6; B2-B6 and C6
VPI modular coil
Epoxy mix and fill coil | 9450-1***-1451 | 1 | 4 | 12 | 48 | 0 | 9 | 432 | Coils A4-A6; B2-B6 and C6
Temperature rampup and Cure | 9450-1***-1451 | 3 | 2 | 12 | 72 | 0 | 9 | 648 | Coils A4-A6; B2-B6 and C6
Temperature rampup and Post cure | 9450-1***-1451 | 2 | 2 | 12 | 48 | 0 | 10 | 480 | Coils A4-A6; B1-B6 and C6
Temperature rampdown | 9450-1***-1451 | 1 | 1 | 10 | 10 | 0 | 10 | 100 | Coils A4-A6; B1-B6 and C6
Cleanup & ready autoclave for coil removal | 9450-1***-1451 | 2 | 3 | 10 | 60 | 0 | 10 | 600 | Coils A4-A6; B1-B6 and C6
Rebuild manifolds and prep autoclave for next VPI | 9450-1***-1451 | 5 | 3 | 10 | 150 | 0 | 10 | 1500 | Coils A4-A6; B1-B6 and C6
|  | 20.5 |  |  | 553 | 16 |  | 5389 | TOTALS hours
569
Post VPI Activities (Station 1) |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Prepare coil for transfer | 9450-1***-1451 | 0.5 | 2 | 9 | 9 | 0 | 10 | 90 | Coils A4-A6; B1-B6 and C6
Transfer modular coil from Autoclave to Station #1 | 9450-1***-1451 | 1 | 3 | 8 | 24 | 16 | 10 | 400 | Coils A4-A6; B1-B6 and C6
Remove studs, structural shell & sprues | 9450-1***-1451 | 8 | 2 | 9 | 144 | 0 | 11 | 1584 | Coils A3-A6; B1-B6 and C6
Install final coil clamps | 9450-1***-1451 | 3 | 2 | 9 | 54 | 0 | 11 | 594 | Coils A3-A6; B1-B6 and C6
Perform (room temperature) electrical & Pressure Tests | 9450-1***-1451 | 1 | 2 | 9 | 18 | 0 | 11 | 198 | Coils A3-A6; B1-B6 and C6
Remove coil from ring assembly | 9450-1***-1451 | 1 | 3 | 10 | 30 | 16 | 11 | 506 | Coils A3-A6; B1-B6 and C6
|  | 14.5 |  |  | 279 | 32 |  | 3372 | TOTALS hours
311
Punch List Items |  | Total | No. of | Coil Tech | Coil Tech | Tech Shop | No. of | Total
| Job Number | Shifts | Coil tech | [hours per | [hours per | Support | coils | Manhrs | COILS
TASK DESCRIPTION |  |  | per shift | shift] | coil] | [hours] | remaining
Mount diagnostic boxes | 9450-1***-1459 | 0.5 | 2 | 9 | 9 | 0 | 18 | 162 | All coils
Route and secure diagnostic wires to box | 9450-1***-1459 | 0.5 | 2 | 9 | 9 | 0 | 18 | 162 | All coils
Install final clamps [coils previously finished] | 9450-1***-1459 | 3 | 2 | 9 | 54 | 0 | 6 | 324 | Coils A1; C1 thru C5
Finalize cooling tubes | 9450-1***-1459 | 1 | 2 | 9 | 18 | 0 | 18 | 324 | All coils
Install Rogowski coils | 9450-1***-1459 | 2 | 2 | 9 | 36 | 0 | 2 | 72 | Coils A3 and A4
Test thermocouples & strain gages [15 min/unit] | 9450-1***-1459 | 0 | 0 | 0 | 0 | 134 | 1 | 134 | [134 strain gauges/ 600 TC]
Install strain gauges and thermocouples [2 hrs./SG or TC] | 9450-1***-1459 | 0 | 1 | 0 | 41 | 0 | 18 | 738 | [134 strain gauges/ 600 TC]
Measure final coil clamp surfaces | 9450-1***-1459 | 1.5 | 2 | 9 | 27 | 0 | 18 | 486 | All coils
Install Thermal Insulation over coil | 9450-1***-1459 | 3 | 2 | 9 | 54 | 0 | 18 | 972 | All coils
Replace co-wound loop on C4 | 9450-1***-1459 | 1 | 2 | 9 | 18 | 0 | 1 | 18 | Coil C4
Install additional flange holes [12 per type "C" winding form] | 9450-1***-1459 | 0 | 0 | 0 | 0 | 192 | 6 | 1152 | [16 hr/hole]
Measure as built coils as required | 9450-1***-1459 | 2 | 2 | 9 | 36 | 0 | 18 | 648
Ground Poloidal Break Hardware | 9450-1***-1459 | 0 | 0 | 0 | 0 | 2 | 18 | 36 | All coils
Ground lead jumper studs | 9450-1***-1459 | 0.2 | 1 | 8 | 1.6 | 0 | 18 | 28.8 | All coils
Grind flange pockets for hardware | 9450-1***-1459 | 0 | 0 | 0 | 0 | 440 | 1 | 440 | [60] holes@ 2hr ea.&[20] holes @ 16hr ea.
Grind winding form wings/clearances | 9450-1***-1459 | 0 | 0 | 0 | 0 | 24 | 18 | 432 | All coils
insert repair | [5 empty] | 200 |  | 200 | A1(2 holes) B2(8 holes)
[8 empty] | 6328.8 | TOTALS hours
|  |  | Coil Tech | Coil Tech | Tech Shop | No. of | TOTAL | M&S
MATERIAL & SUPPLIES | Job Number |  | [hours per | [hours per | Support | coils | Tech | w/o G&A | COILS
|  |  | shift] | coil] | [hours] | remaining | Hours
Coil Supplies
1) Insulation | 9450-1***-1408 |  |  | 0 | 0 | 9 |  | 8000
2) Epoxy- CTD-101 [$4500.00 per coil @ assume 9 injections] | 9450-1***-1408 |  |  | 0 | 0 | 9 |  | 45000 | Coils A4-A6; B2-B6 and C6
3) Miscellaneous and safety supplies [@ $7000/month] | 9450-1***-1408 |  |  | 0 | 0 | 9 |  | 63000
4) Strain gages and thermocouples | 9450-1***-1459 | [6 empty] | 60000 | TC.$30each x600 =$18k; SG $290 each x 62=$18k FB SG $277eachx72=$20k;misc $4k
5) Cutting hardware for flange bolts | 9450-1***-1459 | [6 empty] | 3000
VPI Supplies
1) Epoxy/glass for mold shell [Hysol] | 9450-1***-1408 |  |  | 0 | 0 | 9 | * | 13000
2) VPI clean manifold contract [$1100.00 per VPI] | 9450-1***-1408 |  |  | 0 | 0 | 9 |  | 10000
Tech Shop Support-
Miscellaneous activities- TBD | 9450-1***-1408 |  |  | 0 | 80 | 8 | 640 |  | Coils A4-A6; B3-B6 and C6
9450-1***-1459
[8 empty] | 202000 | TOTALS
| $/ Gallon | Gal/coil | per coil | No. coils
Hysol 2039 Resin | 82 | 4.5 | 369 | 9 | 3321
Hysol 3561 Hardener | 211 | 1.5 | 316.5 | 9 | 2848.5
| $/Box | Bx/coil | per coil | No. coils
Glass | 350 | 2 | 700 | 9 | 6300
|  |  |  | * | 12469.5

## Table IV - Conting & Risk
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
Job 1408 |  |  |  |  | -15%/+25%
| Design Maturity |  |  | X |  | Unknowns of equipment reliability
| Design Complexity |  |  | X |  | Mostly off-the-shelf items
Job 1451 |  |  |  |  | -15%/+25%
| Design Maturity | X |  |  |  | Known and proven procedures and processes
| Design Complexity | X |  |  |  | Have built 12 coils and have proven processes even with tight metrology and tolerances.
Job 1459 |  |  |  |  | -10%/+15%
| Design Maturity |  | X |  |  | Still uncertainty on number of field changes (e.g., number of holes, etc.)
| Design Complexity |  |  | X |  | Standard field work.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
1408 - NONE
1451 | Damage or loss of modular coil during VPI or testing requiring the conductor to be stripped off and re-wound |  |  |  | U | Continue to use same rigorous process used for first 12 coils during which there were no fabrication mihaps requiring re-winding a coil | ~$35K in materials; ~$380K in labor. 7.5 months to do work with the potential for a 2 month impact on the critical path. | 400 | 450 | 0 | 2
| Failure of major piece of winding equipment (e.g., motor, gear box, etc.) resulting in extended downtime in a winding station |  |  |  | U | Use three remaining winding stations to continue MC fabrication while fourth station is being repaired | ~$10K for equipment plus repair costs | 10 | 30 | 0 | 0
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)
Assumptions Cost: Would need ~$4.5K of Expoxy + ~$3K of insulation + $1.5K of shell + ~$5K of other misc components/materials + cost of new lead blocks of ~$15K => round off to ~$35K. Labor ~$380K assuming ~4.5 months to rework and redo coil. Schedule: To redo the coil: Need 138 shifts x 3 men/shift x 8 hours/shift => 3 months + To rework of ~65 shifts x 3 men/shift x 8 hours/shift => 1.5 months. Need an additional ~3 months to order lead blocks if needed. Anticipate ~3 months to re-order and obtain new lead blocks. If Type B coil is the one to fail, could add 1-2 months to critcal path at an added "standing army" cost of ~$260K/months or ~$520K.

## Table V - Basis of Estimate
WBS Number: 142
WBS Title: Windings and Assembly
Job Numbers: 1408, 1451, & 1459
Job Title: Modular Coil Winding Supplies (1408)
Job Title: Modular Coil Winding Operations (1451)
Job Title: Modular Coil Punch List Items (1459)
Job Manager: Jim Chrzanowski
RES | RESOURCE | TOTAL | 2007-01-08 | 2007-01-15 | 2007-01-22 | 2007-01-29 | 2007-02-05 | 2007-02-12 | 2007-02-19 | 2007-02-26 | 2007-03-05 | 2007-03-12 | 2007-03-19 | 2007-03-26 | 2007-04-02 | 2007-04-09 | 2007-04-16 | 2007-04-23 | 2007-04-30 | 2007-05-07 | 2007-05-14 | 2007-05-21 | 2007-05-28 | 2007-06-04 | 2007-06-11 | 2007-06-18 | 2007-06-25 | 2007-07-02 | 2007-07-09 | 2007-07-16 | 2007-07-23 | 2007-07-30 | 2007-08-06 | 2007-08-13 | 2007-08-20 | 2007-08-27 | 2007-09-03 | 2007-09-10 | 2007-09-17 | 2007-09-24 | 2007-10-01 | 2007-10-08 | 2007-10-15 | 2007-10-22 | 2007-10-29 | 2007-11-05 | 2007-11-12 | 2007-11-19 | 2007-11-26 | 2007-12-03 | 2007-12-10 | 2007-12-17 | 2007-12-24 | 2007-12-31 | 2008-01-07 | 2008-01-14 | 2008-01-21 | 2008-01-28 | 2008-02-04 | 2008-02-11 | 2008-02-18 | 2008-02-25 | 2008-03-03 | 2008-03-10 | 2008-03-17
| EM//TB | 29305 | [7 empty] | 461.8 | 822.8 | 945.9 | 708.9 | 700.4 | 639.8 | 545.8 | 542.4 | 528.9 | 568.2 | 836.1 | 750.4 | 621.9 | 566.3 | 947.3 | 800.8 | 675.7 | 646.2 | 492.5 | 545.8 | 545.8 | 554.7 | 700.4 | 614.7 | 486.2 | 623.8 | 793 | 504.1 | 523 | 493.5 | 449 | 393.2 | 393.2 | 494 | 700.4 | 571.9 | 486.2 | 692.6 | 774.4 | 356.6 | 523 | 493.5 | 449 |  | 235.9 | 393.2 | 371.1 | 485.4 | 442.6 | 271.2 | 297 | 381.6 | 221.5 | 93 | 93 | 55.8
| EMT/SB | 350.2 | [7 empty] | 4.9 | 8.1 | 12.3 | 10.6 | 12 | 13.2 | 10.8 | 10.6 | 9.7 | 9.5 | 11.9 | 12.1 | 12.4 | 10.6 | 15.2 | 14.1 | 14.6 | 13.7 | 10.2 | 10.8 | 10.8 | 8.6 | 3.3 | 3.5 | 3.8 | 5.1 | 6 | 3.7 | 4.9 | 4 | 2.7 | 1.1 | 1.1 | 1.3 | 3.3 | 3.6 | 3.8 | 5.8 | 5.5 | 2.8 | 4.9 | 4 | 2.7 |  | 0.7 | 1.1 | 0.4 | 2.2 | 2.3 | 2.7 | 3.1 | 4.4 | 2.4 | 2.7 | 2.7 | 1.6
| EMT/TB | 1050 | [7 empty] | 14.6 | 24.4 | 37 | 31.9 | 36.1 | 39.6 | 32.4 | 31.8 | 29.2 | 28.5 | 35.8 | 36.4 | 37.2 | 31.7 | 45.6 | 42.3 | 43.7 | 41.1 | 30.7 | 32.4 | 32.4 | 25.9 | 10 | 10.5 | 11.3 | 15.3 | 18.1 | 11.2 | 14.7 | 12 | 8.1 | 3.3 | 3.3 | 4 | 10 | 10.8 | 11.3 | 17.3 | 16.5 | 8.5 | 14.7 | 12 | 8.1 |  | 2 | 3.3 | 1.3 | 6.7 | 6.9 | 8 | 9.3 | 13.1 | 7.2 | 8 | 8 | 4.8
 | time axis 2007-01-08 to 2008-03-17
| 29305.4 | Winding crew (reestimate)(5 day work wk) | [7 empty] | 461.8 | 822.8 | 945.9 | 708.9 | 700.4 | 639.8 | 545.8 | 542.4 | 528.9 | 568.2 | 836.1 | 750.4 | 621.9 | 566.3 | 947.3 | 800.8 | 675.7 | 646.2 | 492.5 | 545.8 | 545.8 | 554.7 | 700.4 | 614.7 | 486.2 | 623.8 | 793 | 504.1 | 523 | 493.5 | 449 | 393.2 | 393.2 | 494 | 700.4 | 571.9 | 486.2 | 692.6 | 774.4 | 356.6 | 523 | 493.5 | 449 | 0 | 235.9 | 393.2 | 371.1 | 485.4 | 442.6 | 271.2 | 297 | 381.6 | 221.5 | 93 | 93 | 55.8
| 1400.2 | Tech shop support (reestimate) | [7 empty] | 19.5 | 32.5 | 49.3 | 42.5 | 48.1 | 52.8 | 43.2 | 42.4 | 38.9 | 38 | 47.7 | 48.5 | 49.6 | 42.3 | 60.8 | 56.4 | 58.3 | 54.8 | 40.9 | 43.2 | 43.2 | 34.5 | 13.3 | 14 | 15.1 | 20.4 | 24.1 | 14.9 | 19.6 | 16 | 10.8 | 4.4 | 4.4 | 5.3 | 13.3 | 14.4 | 15.1 | 23.1 | 22 | 11.3 | 19.6 | 16 | 10.8 | 0 | 2.7 | 4.4 | 1.7 | 8.9 | 9.2 | 10.7 | 12.4 | 17.5 | 9.6 | 10.7 | 10.7 | 6.4
| 2470.5 | Winding crew (actual) | 2007-01-08: 823.5; 2007-01-15: 823.5; 2007-01-22: 823.5; 2007-01-29: 823.5; 2007-02-05: 823.5; 2007-02-12: 823.5; 2007-02-19: 823.5; 2007-02-26: 823.5; 2007-03-05: 823.5; 2007-03-12: 823.5
| 138 | Tech shop support (actual) | 2007-01-08: 46; 2007-01-15: 46; 2007-01-22: 46; 2007-01-29: 46; 2007-02-05: 46; 2007-02-12: 46; 2007-02-19: 46; 2007-02-26: 46; 2007-03-05: 46; 2007-03-12: 46
| 2187 | 18 people m-f avg 45hrs workwk x .9 | 2007-01-08: 729; 2007-01-15: 729; 2007-01-22: 729; 2007-01-29: 729; 2007-02-05: 729; 2007-02-12: 729; 2007-02-19: 729; 2007-02-26: 729; 2007-03-05: 729; 2007-03-12: 729
| 29238.2 | Winding crew (reestimate)(6 day work wk) | [7 empty] | 545.2 | 973 | 1020 | 850.7 | 786.2 | 655 | 648.2 | 627.3 | 1003 | 874.8 | 746.3 | 952.7 | 1054 | 810.8 | 766.6 | 710.8 | 655 | 770.5 | 700.4 | 669.1 | 583.4 | 840.1 | 841.8 | 620.2 | 583.4 | 509 | 471.8 | 508.7 | 840.5 | 626.3 | 583.4 | 890.3 | 799 | 612.9 | 583.4 | 490.4 | 471.8 | 538.2 | 539.6 | 216.9 | 325.4 | 417.3 | 283 |  | 74.4 | 111.6 | 55.8
|  |  | 823.5 | 823.5 | 823.5 | 823.5 | 823.5 | 823.5 | 823.5 | 823.5 | 823.5 | 823.5
|  |  | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46 | 46
|  |  | 835 | 835 | 871 | 871 | 795 | 796 | 756 | 756 | 860 | 860
|  |  | 84 | 84 | 15 | 15 | 2 | 2 | 52 | 52 | 77 | 77
Winding estimate manpower cross check (job 1451 only)
Mod Coil Test Flange Assuming A-B joints with 18 inch centers => 6 holes per joint vs. assumed 2-3 estimated by Task Force.