## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Description:
Job 1421 consists of the effort to design the modular coil interfaces, including R&D.
Schedule:
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor 1421
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Description:
Title I, II and III Engineering for design of the modular coil interfaces.
NOTE: Title III for these components is included in Job 1802 |  | FY07$K
Task ID |  | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | Basis of Estimate
see Table V - Basis of Estimate
Outboard Interface Design | [15 empty] | see Table V - Basis of Estimate
IH4-020 | Prepare outboard shim dwgs and release | [5 empty] | 60 | [8 empty] | see Table V - Basis of Estimate
INTRF-045 | FDR outboard shims | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
| Resolve CHITs and issue shim drawings | [5 empty] | 60
see Table V - Basis of Estimate
Bolted Joint Tests | [15 empty] | see Table V - Basis of Estimate
Tension Tests of Bolted Joint | [15 empty] | see Table V - Basis of Estimate
1421-3067 | Procure 2 studs f/joint test.Use existing part | [6 empty] | 8 | [7 empty] | see Table V - Basis of Estimate
1421-3075 | Setup test fixture &perform JHA & pre-job brief | [6 empty] | 8
1421-3077 | Meas joint deflect vs preload & loss of preload | [6 empty] | 24 | [7 empty] | see Table V - Basis of Estimate
1421-3079 | Measure joint deflec & preload v. temp @80K | [6 empty] | 24 | [7 empty] | see Table V - Basis of Estimate
1421-3084 | Measure joint deflection&preload v. cooldown cyc | [6 empty] | 24 | [7 empty] | see Table V - Basis of Estimate
1421-3087 | Perform pullout tests for tapped holes | [6 empty] | 24
1421-3081 | Meas joint deflect & preload v. time (days) at R | [6 empty] | 160 | [7 empty] | see Table V - Basis of Estimate
1421-3090 | Document&conduct review of test results | [6 empty] | 40 | [7 empty] | see Table V - Basis of Estimate
see Table V - Basis of Estimate
Bolt Shear Test at 77k | [15 empty] | see Table V - Basis of Estimate
1421-3112B | Procure/fab parts for test&initial assembly | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
1421-3115B | Assemble & test | [5 empty] | 320 | [8 empty] | see Table V - Basis of Estimate
1421-3119B | Document test results | [5 empty] | 80 | [8 empty] | see Table V - Basis of Estimate
see Table V - Basis of Estimate
Inboard Interface Design | [15 empty] | see Table V - Basis of Estimate
IH1-001 | Coil to coil analysis | [5 empty] | 520 | [8 empty] | see Table V - Basis of Estimate
1421-3125 | Determine geometry&location of high COF shims&pl | [5 empty] | 80
1421-3127 | Structural analyses to performance rqmts for bol | [5 empty] | 240 | [8 empty] | see Table V - Basis of Estimate
1421-3132 | PDR to review requirements, design,&development | [5 empty] | 40
see Table V - Basis of Estimate
AB/BC/AA welded joints | [15 empty] | see Table V - Basis of Estimate
| Prepare winding form mods for weld clamping bolts | [5 empty] | 300 | [8 empty] | see Table V - Basis of Estimate
INTRF-050 | Complete Shim fabrication drawings (ORNL) | [5 empty] | 240 | [8 empty] | see Table V - Basis of Estimate
| Release information for procurement of shim material | [5 empty] | 24
INTRF-055 | FDR AB/BC/AA inboard shims | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
see Table V - Basis of Estimate
CC bolted joint | [15 empty] | see Table V - Basis of Estimate
IH1-000 | ESTABLISH CONCEPT | [5 empty] | 680 | [8 empty] | see Table V - Basis of Estimate
IH1-0000 | PEER REVIEW OF JOINT CONCEPT | [5 empty] | 80 | [8 empty] | see Table V - Basis of Estimate
| Add bolt holes to C winding form for CC interface | [5 empty] | 140 | [8 empty] | see Table V - Basis of Estimate
| Bolt Reach and Access study (mockup) | [5 empty] | 200 | [8 empty] | see Table V - Basis of Estimate
| Prepare CC shim drawiings and release | [5 empty] | 360 | [8 empty] | see Table V - Basis of Estimate
| FDR CC inboard shims | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
Welded Joint Tests
Procedure
INTRF-035 | PPPL Determine shim material | [6 empty] | 40 | [7 empty] | see Table V - Basis of Estimate
INTRF-001 | PPPL buy SS plate for weld trials | [6 empty] | 8 | [7 empty] | see Table V - Basis of Estimate
INTRF-005 | Weld distortion trials at PPPL on SS plate | [6 empty] | 40 | [7 empty] | see Table V - Basis of Estimate
INTRF-025 | ORNL build pywood mockup of flange | [5 empty] | 140 | [8 empty] | see Table V - Basis of Estimate
INTRF-030 | ORNL verify weld access, develop alternate welding methods | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
INTRF-010 | Develop Weld Geometry Procedure | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
Test
INTRF-015 | Weld trials on two MCWF's at PPPL | [6 empty] | 80 | [7 empty] | see Table V - Basis of Estimate
INTRF-020 | Document results and update weld procedure | [6 empty] | 120 | [7 empty] | see Table V - Basis of Estimate
Overall interface
INTRF-040 | Analysis of tensil loads (ORNL) | [5 empty] | 320 | [8 empty] | see Table V - Basis of Estimate
1421-3134 | Develop specs & dwgs for station 2 &3 assy | [5 empty] | 300 | [8 empty] | see Table V - Basis of Estimate
1421-3136 | Conduct MC interface FDR incl job 1416 | [5 empty] | 40 | [8 empty] | see Table V - Basis of Estimate
1421-3138 | Resolve issues, release assembly drawings | [5 empty] | 240 | [8 empty] | see Table V - Basis of Estimate. Specs in Job 1806
FY07 Rebaseline exercise
ECP53RBX05 | FY07 Rebaseline Exercise | [5 empty] | 256
Travel
| trips for ORNL personnel to PPPL |  |  |  | 9 | [10 empty] | 6 trips at $1500 avg
| trips for PPPL personnel to UT MDL |  |  |  | 3 | [10 empty] | 2 trips at $1500 avg
| SUBTOTAL |  |  |  | 12 |  | 4960 | 600
unlisted, known labor hours
| scheduled and unscheduled meetings/reporting/presentations (@ 25%) | [5 empty] | 1210 | 150 | [7 empty] | see Table V - Basis of Estimate
| TOTAL |  |  |  | 12 |  | 6170 | 750

## Table II - M&S
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Materials and Supplies
M&S-k$
1421-3067 | Procure 2 studs f/joint test.Use existing part |  | 1 | Based on stud quotation
1421-3112B | Test fixture for fatique testing |  | 10 | Based on fabrication estimate for hardware, see detail below
IH1-001 | Coil to coil analysis |  | 36 | Based engineering judgement for subcontract, see details below
INTRF-001 | PPPL buy SS plate for weld trials |  | 31.05 | Based on $15/lb SS plate, see detail below
INTRF-005 | Weld distortion trials at PPPL on SS plate |  | 1 | engr judgement for consumables
INTRF-025 | ORNL build plywood mockup of flange |  | 30 | Based on est costs for subcontract, see detail below
INTRF-030 | ORNL verify weld access, develop alternate welding methods |  | 20 | Based engineering judgement for subcontract, see details below
| ORNL verify CC bolt reach access |  | 19 | Based engineering judgement for subcontract, see details below
INTRF-015 | Weld trials on two MCWF's at PPPL |  | 1 | engr judgement for consumables
| TOTAL |  | 149.05
Details
Test fixture for fatique testing
| SST plate, G11 bushings and insulators material |  |  | 6
| LN2 can, bellows, support struts, G10 rods |  |  | 3.6 | see detail bill of matls below
9.6
Analysis subcontract
| 12 weeks x 50% time | 240 | hours | 36
stainless steel plate
| 1.5"x 4' x 8' plate @ $15/lb | 2070 | lbs | 31.05
plywood mockup
| plywood, paint, etc. | 1 | lot | 3
| labor, technicians | 240 | hours | 18 | 2 techs for 3 weeks
| labor, supervision | 60 | hours | 9 | half time for 3 weeks
| total est. for contract |  |  | 30
ORNL verify weld access
| weld consumables | 1 | lot | 2 | weld wire, gas, etc.
| labor, technicians | 160 | hours | 12 | 2 techs for 2 weeks
| labor, supervision | 40 | hours | 6 | half time for 2 weeks
| total est. for contract |  |  | 20
ORNL verify CC bolt access
| wood, glue, etc | 1 | lot | 1
| labor, technicians | 160 | hours | 12 | 2 techs for 2 weeks
| labor, supervision | 40 | hours | 6 | half time for 2 weeks
| total est. for contract |  |  | 19

## Table III Fab & Assy
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
FY07$K
Task ID |  | Comments | 41MS | 48MS | 37STK | 35TRVL | 31OT | EMSM | EMTB | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
Outboard Interface Design
IH4-020 | Prepare outboard shim dwgs and release | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-045 | FDR outboard shims | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Resolve CHITs and issue shim drawings | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Bolted Joint Tests
Tension Tests of Bolted Joint
1421-3067 | Procure 2 studs f/joint test.Use existing part | [7 empty] | 48 | [10 empty] | see Table V - Basis of Estimate
1421-3075 | Setup test fixture &perform JHA & pre-job brief | [7 empty] | 16 | [10 empty] | see Table V - Basis of Estimate
1421-3077 | Meas joint deflect vs preload & loss of preload | [7 empty] | 24 | [10 empty] | see Table V - Basis of Estimate
1421-3079 | Measure joint deflec & preload v. temp @80K | [7 empty] | 24 | [10 empty] | see Table V - Basis of Estimate
1421-3084 | Measure joint deflection&preload v. cooldown cyc | [7 empty] | 24 | [10 empty] | see Table V - Basis of Estimate
1421-3087 | Perform pullout tests for tapped holes | [7 empty] | 24 | [10 empty] | see Table V - Basis of Estimate
1421-3081 | Meas joint deflect & preload v. time (days) at R | [7 empty] | 160 | [10 empty] | see Table V - Basis of Estimate
1421-3090 | Document&conduct review of test results | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Bolt Shear Test at 77k
1421-3112B | Procure/fab parts for test&initial assembly | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3115B | Assemble & test | [7 empty] | 100 | [10 empty] | see Table V - Basis of Estimate
1421-3119B | Document test results | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Inboard Interface Design
IH1-001 | Coil to coil analysis | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3125 | Determine geometry&location of high COF shims&pl | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3127 | Structural analyses to performance rqmts for bol | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3132 | PDR to review requirements, design,&development | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Conduct MC interface FDR | [18 empty] | see Table V - Basis of Estimate
AB/BC/AA welded joints
| Prepare winding form mods for weld clamping bolts | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-050 | Complete Shim fabrication drawings (ORNL) | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Release information for procurement of shim material | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-055 | FDR AB/BC/AA inboard shims | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
CC bolted joint
IH1-000 | ESTABLISH CONCEPT | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
IH1-0000 | PEER REVIEW OF JOINT CONCEPT | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Add bolt holes to C winding form for CC interface | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Bolt Reach and Access study (mockup) | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| Prepare CC shim drawiings and release | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
| FDR CC inboard shims | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Welded Joint Tests
Procedure
INTRF-035 | PPPL Determine shim material | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-001 | PPPL buy SS plate for weld trials | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-005 | Weld distortion trials at PPPL on SS plate | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-025 | ORNL build pywood mockup of flange | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-030 | ORNL verify weld access, develop alternate welding methods | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
INTRF-010 | Develop Weld Geometry Procedure | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Test
INTRF-015 | Weld trials on two MCWF's at PPPL | [7 empty] | 600 | [10 empty] | see Table V - Basis of Estimate
INTRF-020 | Document results and update weld procedure | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Overall interface
INTRF-040 | Analysis of tensil loads (ORNL) | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3134 | Develop specs & dwgs for station 2 &3 assy | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3136 | Conduct MC interface FDR incl job 1416 | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
1421-3138 | Resolve issues, release assembly spec&drawings | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
FY07 Rebaseline exercise
ECP53RBX05 | FY07 Rebaseline Exercise | [7 empty] | 0 | [10 empty] | see Table V - Basis of Estimate
Travel
Trips for ORNL personnel to PPPL
Trips for PPPL personnel to UT MDL
| TOTAL | [7 empty] | 1020

## Table IV - Conting & Risk
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | x
[5 empty] | -10 to +50 |  | Major issue is continuous iteration of design
| Design Complexity |  | x |  |  |  | Major uncertainty is C-C access for bolting at machine assembly
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
Risk |  |  |  |  | Likelihood of Occurring (%) | Mitigation Strategies |  | Consequence if Occurs
[8 empty] | Cost |  | Schedule
1 | weld distortion found in R&D exceeds allowable |  |  |  | 20% | add distortion control methods to welding procedure development, such as clamping bolts, peening, and alternate weld methods |  |  | $70k+sched hit |  | 6 wks
assume double welding time
2 | C-C access insufficient for bolts |  |  |  | 20% | Prepare mockups and check access directly |  |  | $250k
redesign and re-analyze alternate solution at CC

## Table V - Basis of Estimate
WBS Number: 142
WBS Title: Windings and Assembly
Job Number: 1421
Job Title: Design of Modular Coil Interfaces
Job Manager:David Williamson
Assumptions | [28 empty] | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions | Assumptions
Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | [28 empty] | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker | Bladder design remaining and testing are in Larry Dudek's job 1431. Still need method to retain bladder and to provide bladder at B-A interface where bladder is much thicker
Engineering and Technician Hours
Color Key | [5 empty] | Pro-E models (avg) | Pro-E models (complex) | assy dwgs | Detail drawings | installation dwg | cooling schematic | electrical schematic | I&C schematic | stress analysis | thermal analysis | special analysis (electromagnetics) | assy/install specs and procedures | procurement/fab and associated specifications | R&D reports | peer, preliminary and final design reviews | Planning | misc engr tasks | Comments for Engineering labor |  | crew size | shifts | time from detail | Comments for Technicisan labor
| ORNL |  |  |  | multiplier | 40 | 80 | 100 | 60 | 40 | 0 | 0 | 20 | 240 | 40 | 160 | 40 | 40 | 80 | 40 | 16 | 1 |  |  |  | 8
| PPPL |  |  |  | unit | hrs/model | hrs/model | hrs/dwg | hrs/dwg | hrs/dwg | hrs/dwg | hrs/dwg | hrs/dwg | hrs/calc | hrs/calc | hrs/calc | hrs/proc | hrs/spec | hrs/report | hrs/rev | hrs/wk | hrs |  |  |  | hrs/shift
|  |  | Total Engr hours | Total Tech hours
Outboard Interface Design
IH4-020 | Prepare outboard shim dwgs and release | #REF! | 60 | 0 |  |  |  |  | 1 | [14 empty] | #REF!
INTRF-045 | FDR outboard shims | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
| resolve and issue shim drawings |  | 60 | 0 |  |  |  |  | 1
Bolted Joint Tests
Tension Tests of Bolted Joint
1421-3067 | Procure 2 studs f/joint test.Use existing part | #REF! | 8 | 48 | [17 empty] | 8 | engineering judgement | #REF! | 2 | 3
1421-3075 | Setup test fixture &perform JHA & pre-job brief | #REF! | 8 | 16 | [17 empty] | 8 | engineering judgement | #REF! | 2 | 1
1421-3077 | Meas joint deflect vs preload & loss of preload | #REF! | 24 | 24 | [17 empty] | 24 | engineering judgement | #REF! | 1 | 3
1421-3079 | Measure joint deflec & preload v. temp @80K | #REF! | 24 | 24 | [17 empty] | 24 | engineering judgement | #REF! | 1 | 3
1421-3084 | Measure joint deflection&preload v. cooldown cyc | #REF! | 24 | 24 | [17 empty] | 24 | engineering judgement | #REF! | 1 | 3
1421-3087 | Perform pullout tests for tapped holes | #REF! | 24 | 24 | [17 empty] | 24 | engineering judgement | #REF! | 1 | 3
1421-3081 | Meas joint deflect & preload v. time (days) at R | #REF! | 160 | 160 | [17 empty] | 160 | engineering judgement | #REF! | 1 | 20
1421-3090 | Document&conduct review of test results | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
Bolt Shear Test at 77k | [23 empty] | #REF!
1421-3112B | Procure/fab parts for test&initial assembly | #REF! | 40 | 0 | [13 empty] | 1 | [5 empty] | #REF!
1421-3115B | Assemble & test | #REF! | 320 | 100 | [17 empty] | 320 | full time for 2 engr following test | #REF! | 2.5 | 5
1421-3119B | Document test results | #REF! | 80 | 0 | [14 empty] | 1 |  |  |  |  | #REF!
Inboard Interface Design
IH1-001 | Coil to coil analysis | #REF! | 520 | 0 | [9 empty] | 2 | [5 empty] | 1 |  |  |  | #REF!
1421-3125 | Determine geometry&location of high COF shims&pl | #REF! | 80 | 0 |  |  | 1 | [16 empty] | #REF!
1421-3127 | Structural analyses to performance rqmts for bol | #REF! | 240 | 0 | [9 empty] | 1 | [9 empty] | #REF!
1421-3132 | PDR to review requirements, design,&development | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
AB/BC/AA welded joints
| prepare winding form mods for weld clamping bolts |  | 300 |  |  | 3 |  |  | 3
INTRF-050 | Complete Shim fabrication drawings (ORNL) | #REF! | 240 | 0 |  |  |  |  | 4 | [14 empty] | #REF!
| Release information for procurement of shim material |  | 24 | [19 empty] | No hours included - RTS added 24 hours
INTRF-055 | FDR AB/BC/AA inboard shims | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
CC bolted joint
IH1-000 | ESTABLISH CONCEPT | #REF! | 680 | 0 |  | 5 | 3 |  | 2 | [10 empty] | 3 |  |  |  | #REF!
IH1-0000 | PEER REVIEW OF JOINT CONCEPT | #REF! | 80 | 0 | [15 empty] | 2 |  |  |  | #REF!
| Add bolt holes to C winding form for CC interface |  | 140 | 0 |  |  | 1 |  | 1
| Bolt Reach and Access study (mockup) |  | 200 | 0 |  | 2 |  |  | 2
| Prepare CC shim drawiings and release | #REF! | 360 | 0 |  |  | 1 | 1 | 3 | [14 empty] | #REF!
| FDR CC inboard shims | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
Welded Joint Tests
Procedure | [23 empty] | #REF!
INTRF-035 | PPPL Determine shim material | #REF! | 40 | 0 | [17 empty] | 40 |  | #REF!
INTRF-001 | PPPL buy SS plate for weld trials | #REF! | 8 | 0 | [17 empty] | 8 |  | #REF!
INTRF-005 | Weld distortion trials at PPPL on SS plate | #REF! | 40 | 0 | [17 empty] | 40 |  | #REF!
INTRF-025 | ORNL build pywood mockup of flange | #REF! | 140 | 0 |  | 1 |  | 1 | [15 empty] | #REF!
INTRF-030 | ORNL verify weld access, develop alternate welding methods | #REF! | 40 | 0 | [17 empty] | 40 |  | #REF!
INTRF-010 | Develop Weld Geometry Procedure | #REF! | 40 | 0 | [12 empty] | 1 | [6 empty] | #REF!
Test
INTRF-015 | Weld trials on two MCWF's at PPPL | #REF! | 80 | 600 | [17 empty] | 80 |  | #REF! |  |  | 665 | see detail below
INTRF-020 | Document results and update weld procedure | #REF! | 120 | 0 | [13 empty] | 1 | 1 |  |  |  |  | #REF!
Overall interface design
INTRF-040 | Analysis of tensil loads (ORNL) | #REF! | 320 | 0 |  |  | 1 | [6 empty] | 1 | [9 empty] | #REF!
1421-3134 | Issue interface drawings for comment | #REF! | 300 | 0 |  |  |  | 3 | [8 empty] | 0 | [5 empty] | AA, AB, BC only | #REF!
1421-3136 | Conduct MC interface FDR incl job 1416 | #REF! | 40 | 0 | [15 empty] | 1 |  |  |  | #REF!
1421-3138 | Resolve issues, release assembly spec&drawings | #REF! | 240 | 0 | [12 empty] | 1 |  |  |  |  | 200 |  | #REF!
FY07 Rebaseline exercise | [23 empty] | #REF!
ECP53RBX05 | FY07 Rebaseline Exercise | #REF! | 256 | 0 | [16 empty] | 16 |  |  | #REF!
| Subtotal | #REF! | 5560 | 1020 | [19 empty] | #REF!
| scheduled and unscheduled meetings/reporting/presentations (25%) |  | 1390
| TOTAL |  | 6950

## 1421 schedule detail
Sum of BQ | [8 empty] | $K |  |  |  | hours
WBS2 | JJJJ | sort code | ACT | TITLE | ES | EF | status comment | days | 41 | actual may cost | ORNL35 | ORNL41 | EA//EM | EM//EM | EM//TB | EMT/TB | ORNLDM | ORNLEM
14 | 1416 | MCDB | 1416-204.1 | Modify Type-B clamps for stud attachment | 2007-07-02 | 2007-07-13 |  | 9 | [9 empty] | 50
|  | MCDC | 1416-304 | Revise assembly models/drawings | 2007-06-01 | 2007-06-07 |  | 5 | [9 empty] | 80
|  |  | 1416-305 | Review and approve insulation concept | 2007-06-08 | 2007-06-14 |  | 5 |  |  |  |  | 10 |  |  |  |  | 30
|  |  | 1416-3198 | Report Results & Issue Dwgs | 2007-06-15 | 2007-06-28 |  | 10 |  |  |  |  | 8 |  |  |  |  | 40
|  | MCDE | 1416-503 | Complete models/drawings of power cable connect | 2007-08-01 | 2007-11-21 |  | 80 | [9 empty] | 120
|  |  | 1416-504 | Complete models/drawings of protective covers | 2007-08-01 | 2007-11-21 |  | 80 | [9 empty] | 120
|  |  | 1416-506 | Check and promote top-level models/drawings | 2007-08-01 | 2007-11-21 |  | 80 | [9 empty] | 80
|  |  | 1416-507 | Update, review and approve coil asm spec | 2007-05-01 | 2007-05-30 |  | 21 | [9 empty] | 80
|  |  | 1416-508 | Complete drawing rev to leads, terminal asm (ECN | 2007-05-01 | 2007-05-30 |  | 21 | [9 empty] | 80
|  | MCDF | 1416-601 | Prepare EM and structural analysis of leads | 2007-10-01 | 2007-11-06 | len myatt | 27 | 60 |  |  | 60 | 192 |  |  |  |  | 80
|  |  | 1416-602 | Design memo KF structural analysis | 2007-11-07 | 2007-11-27 |  | 15 | [9 empty] | 96
|  |  | 1416-603 | Update, review and approve FMECA | 2007-11-28 | 2007-12-06 |  | 5 | [9 empty] | 60
|  |  | 1416-604 | Finalize draft documents - materials, eddy curre | 2007-12-07 | 2007-12-13 |  | 5 | [9 empty] | 40
|  |  | 1416-605 | Prepare Type-ABC closeout FDR | 2007-12-14 | 2008-01-14 |  | 15 | [9 empty] | 72
|  |  | 1416-606 | Resolve FDR comments | 2008-01-15 | 2008-02-04 |  | 15 | [9 empty] | 72
|  | TCCO | 1403-47C | Perform cool-down/warmup analysis | 2007-10-01 | 2007-11-05 |  | 26 |  |  |  |  | 40 | [5 empty] | 1100
| 1421 |  | INTRF-100 | Misc travel, meetings,reporting,presentations | 2007-05-01 | 2007-09-28 | 25% | 106 |  |  | 12 |  |  | 150 |  |  |  | 1210
|  |  | REBASE1421 | Re-baseline exercise | 2007-05-01 | 2007-06-15 |  | 33 | [9 empty] | 256
|  | 142A | IH4-020 | Prepare outboard shim dwgs and release for comment | 2007-05-01 | 2007-06-15 | complete-A | 33 | [9 empty] | 60
|  |  | INTRF-045 | FDR prep outboard shims | 2007-06-18 | 2007-06-29 |  | 10 | [9 empty] | 40
|  |  | INTRF-046 | FDR outboard shims |  | 2007-06-29 |  | 0
|  |  | INTRF-047 | Resolve chit's and issue shim drawings | 2007-07-02 | 2007-07-10 |  | 6 | [9 empty] | 60
|  | 142B | 1421-3067 | Procure 2 studs f/joint test.Use existing part | 2007-05-01 | 2007-07-25 |  | 60 | 1 |  |  |  |  | 8 | 48
|  |  | 1421-3075 | Setup test fixture &perform JHA & pre-job brief | 2007-05-29 | 2007-05-30 | adjust blue cells to g27, which used to be may 28 | 2 | [5 empty] | 8 | 16
|  |  | 1421-3077 | Meas joint deflect vs preload & loss of preload | 2007-05-31 | 2007-06-04 |  | 3 | [5 empty] | 24 | 24
|  |  | 1421-3079 | Measure joint deflec & preload v. temp @80K | 2007-06-05 | 2007-06-07 |  | 3 | [5 empty] | 24 | 24
|  |  | 1421-3081 | Meas joint deflect & preload v. time (days) at R | 2007-06-18 | 2007-07-16 |  | 20 | [5 empty] | 160 | 160
|  |  | 1421-3084 | Measure joint deflection&preload v. cooldown cyc | 2007-06-08 | 2007-06-12 |  | 3 | [5 empty] | 24 | 24
|  |  | 1421-3087 | Perform pullout tests for tapped holes | 2007-06-13 | 2007-09-16 |  | 3 | [5 empty] | 24 | 24
|  |  | 1421-3090 | Document&conduct review of test results | 2007-07-17 | 2007-07-23 |  | 5 | [5 empty] | 40
|  | 142C | 1421-3112B | Procure/fab parts for test&initial assembly | 2007-05-01 | 2007-07-25 |  | 60 | 10 |  |  |  |  | 40
|  |  | 1421-3115B | Assemble & test | 2007-07-26 | 2007-09-07 |  | 31 | [6 empty] | 100 |  |  | 320
|  |  | 1421-3119B | Document test results | 2007-09-10 | 2007-10-01 |  | 16 | [9 empty] | 80
|  | 142D | 1429-3026 | COF cyclic testing | 2007-05-01 | 2007-05-18 | complete-A | 14 |  | 29.97
|  | 142E | 1421-3125 | Determine geometry&location of high COF shims&pl | 2007-05-01 | 2007-06-13 | complete-A | 31 | [9 empty] | 80
|  |  | 1421-3127 | Structural analyses to performance rqmts for bol | 2007-06-14 | 2007-06-20 | complete-A | 5 | [9 empty] | 240
|  |  | 1421-3131 | PDR prep for requirements, design,&development | 2007-06-14 | 2007-06-22 |  | 5 | [9 empty] | 40
|  |  | 1421-3132 | PDR to review requirements, design,&development |  | 2007-06-22 |  | 0
|  |  | IH1-001 | Coil to coil scoping analysis | 2007-05-01 | 2007-06-15 |  | 33 |  |  |  | 36 | [5 empty] | 520
|  | 142F | INTRF-049 | prepare winding form mods for weld clamp bolts | 2007-06-13 | 2007-06-27 |  | 11 | [9 empty] | 300
|  |  | INTRF-050 | Complete Shim fabrication drawings (ORNL) | 2007-06-14 | 2007-07-02 |  | 13 | [9 empty] | 240
|  |  | INTRF-051 | Release info for procurement of shim material | 2007-05-01 | 2007-06-22 |  | 38 | [9 empty] | 24
|  |  | INTRF-054 | FDR prep AB/BC/AA inboard shims | 2007-08-02 | 2007-08-08 |  | 5 | [5 empty] | 40
|  |  | INTRF-055 | FDR AB/BC/AA inboard shims |  | 2007-08-08 |  | 0
|  | 142G | 1421-3140 | Prep C-C shim drawings and release | 2007-08-20 | 2007-09-07 |  | 14 | [9 empty] | 360
|  |  | 1421-3142 | FDR Prep for C-C shims | 2007-09-10 | 2007-11-06 |  | 42 | [9 empty] | 40
|  |  | 1421-3143 | Add bolt holes to C winding form for CC interfac | 2007-07-19 | 2007-08-02 | need before INTRF 015 | 11 | [9 empty] | 140
|  |  | 1421-3144 | FDR C-C Shims |  | 2007-11-06 | was 11/30 | 0
|  |  | 1421-3145 | Bolt reach & access study (mockup) | 2007-08-03 | 2007-08-10 |  | 6 | [9 empty] | 200
|  |  | IH1-000 | ESTABLISH CONCEPT | 2007-06-01 | 2007-07-23 |  | 36 | [9 empty] | 680
|  |  | IH1-0000 | PEER REVIEW OF JOINT CONCEPT | 2007-07-24 | 2007-08-02 |  | 8 | [9 empty] | 80
|  | 142H | INTRF-001 | PPPL buy SS plate for weld trials | 2007-06-04 | 2007-06-15 |  | 10 | 31 |  |  |  |  | 8
|  |  | INTRF-005 | Weld distortion trials at PPPL on SS plate | 2007-06-18 | 2007-07-06 |  | 14 | 0 |  |  |  |  | 40 | 20
|  |  | INTRF-010 | Develop Weld Geometry Procedure | 2007-07-03 | 2007-07-10 |  | 5 |  |  |  |  | 40
|  |  | INTRF-025 | ORNL build pywood mockup of flange | 2007-05-01 | 2007-06-20 |  | 36 |  |  |  | 30 | [5 empty] | 140
|  |  | INTRF-030 | ORNL verify weld access | 2007-06-21 | 2007-06-25 |  | 3 |  |  |  | 20 | [5 empty] | 40
|  |  | INTRF-035 | PPPL Determine shim material | 2007-05-01 | 2007-06-01 | complete-A | 23 |  |  |  |  | 40
|  | 142I | INTRF-015 | Weld trials on two MCWF's at PPPL | 2007-07-11 | 2007-07-30 |  | 14 | 1 |  |  |  |  | 80 | 600
|  |  | INTRF-020 | Document results and update weld procedure | 2007-07-31 | 2007-08-07 |  | 6 |  |  |  |  | 120
|  | 142J | 1421-3134 | Issue interface dwgs for comment | 2007-05-01 | 2007-07-20 |  | 57 | [9 empty] | 300
|  |  | 1421-3135 | FDR Prep | 2007-07-23 | 2007-08-08 |  | 13 | [9 empty] | 40
|  |  | 1421-3136 | Conduct BC, AB, AA, MC interface FDR incl JOB 1416 |  | 2007-08-08 |  | 0
|  |  | 1421-3138 | Resolve issues, release assembly spec&drawings | 2007-08-09 | 2007-08-15 |  | 5 | [9 empty] | 240 | 4840
|  |  | INTRF-040 | ANalysis of tensile loads (ORNL) | 2007-05-01 | 2007-08-08 |  | 70 | [9 empty] | 320 | 6050
| 1431 | BLAD | 1421-3024 | Prep Req, Bid,& Award Bladders | 2007-05-01 | 2007-05-29 |  | 20
|  |  | 1421-3025 | Deliver bladders | 2007-05-30 | 2007-06-07 |  | 7 | 0
|  |  | 1421-3028 | Bladders available for FPA |  | 2007-06-07 |  | 0
|  | BUSH | 1421-3105 | Prep Req, Bid,& Award Bushings | 2007-05-01 | 2007-05-21 |  | 15
|  |  | 1421-3106 | Deliver Bushings Material | 2007-05-22 | 2007-07-02 |  | 29 | 8.05
|  |  | 1421-3107 | PPPL Machine bushings Bushings | 2007-07-03 | 2007-10-08 |  | 68 | [7 empty] | 554
|  |  | 1421-3108 | Bushings available for first coil-to-coil fitup | 2007-10-09 |  |  | 0
|  |  | 1421-3109 | All Bushings delivered |  | 2007-10-08 |  | 0
|  | SHMS | 1429-3059 | Prep Req, Bid,Award Shim Stock | 2007-06-25 | 2007-07-16 |  | 15
|  |  | 1429-3060 | Deliver Shim Stock | 2007-07-17 | 2007-09-04 |  | 35 | 60.56
|  |  | 1429-3061 | Prep Req, Bid,Award Grinding contract | 2007-07-11 | 2007-07-31 |  | 15
|  |  | 1429-3062 | Grind Shim Stock | 2007-08-07 | 2007-09-25 |  | 35 | 5.6
|  |  | 1429-3063 | Pre Req, Bid, Award Cutting Contract | 2007-08-16 | 2007-09-06 |  | 15
|  |  | 1429-3064 | Machine shop cut shim stock to size | 2007-09-07 | 2007-10-25 |  | 35 | 2.4 | [6 empty] | 448
|  |  | 1429-3065 | Prep Req, Bid, Award Alumina Application | 2007-08-16 | 2007-09-06 |  | 15
|  |  | 1429-3066 | Apply Alumina to Shims | 2007-09-28 | 2007-11-19 |  | 37 | 38.8
|  |  | 1429-3069 | Shims Req'd for 1st 3 pack MC assy | 2007-10-12 |  |  | 0
|  |  | 1429-3070 | Shims Req'd for 2nd 3 pack MC assy | 2007-10-19 |  |  | 0
|  |  | 1429-3071 | Shims Req'd for 3rd 3 pack MC assy | 2007-10-26 |  |  | 0
|  |  | 1429-3072 | Shims Req'd for 4th 3 pack MC assy | 2007-11-02 |  |  | 0
|  |  | 1429-3073 | Shims Req'd for 5th 3 pack MC assy | 2007-11-09 |  |  | 0
|  |  | 1429-3074 | Shims Req'd for 6th 3 pack MC assy | 2007-11-16 |  |  | 0
|  |  | 1429-3075 | Shims Req'd for C-C joint | 2010-01-22 |  |  | 0
|  | STUD | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 2007-05-01 | 2007-07-20 |  | 57 | 77.58
|  |  | 1421-3061 | Stud kit available for 1st 3 pack MC assy |  | 2007-07-20 |  | 0
|  |  | 1421-3062 | Re-order balance of stud kits | 2007-07-02 | 2007-10-02 |  | 65 | 312.29
|  |  | 1421-3063 | Stud kits available for balance of MC assy |  | 2007-10-02 |  | 0
|  |  | 1421-3065 | Deliver Superbolts (PE007332) | 2007-05-01 | 2007-05-31 |  | 22 | 123.75
|  |  | 1421-3066 | Super bolts available for FPA |  | 2007-05-31 |  | 0
|  |  | 1421-3070 | Order Add'l stud kits for c-c joint&weld clmp | 2007-10-01 | 2007-10-19 |  | 15
|  |  | 1421-3072 | Deliver Add'l stud kits for c-c joint&weld clmp | 2007-10-22 | 2007-12-04 |  | 30 | 45.74
|  |  | 1421-3080 | Purchase G-11 shims and machine for C-C inboard | 2007-10-01 | 2008-01-10 |  | 65 | 1.44 | [5 empty] | 48
16 | 1601 | 161 | 191-001 | Title I design WBS 161 LN2 manifolds&piping | 2008-06-02 | 2008-10-07 |  | 90 | [9 empty] | 527
|  |  | 191-002 | PDR WBS 161 LN2 manifolds&piping | 2008-10-08 | 2008-10-08 |  | 1 | [9 empty] | 8
|  |  | 191-011 | Title II design WBS 161 LN2 manifolds&piping | 2008-10-09 | 2009-02-24 |  | 90 | [9 empty] | 527
|  |  | 191-012 | FDR WBS 161 LN2 manifolds&piping | 2009-02-25 | 2009-02-25 |  | 1 | [9 empty] | 8
|  |  | 191-031 | Title III engr WBS 161 | 2009-02-26 | 2010-08-06 |  | 362 | [9 empty] | 176
|  |  | 191-037 | Prep Req,Bid,Award-manifolds,hoses,valves etc | 2009-02-26 | 2009-04-01 |  | 25
|  |  | 191-038 | Delivery of-manifolds,hoses,valves etc | 2009-04-02 | 2009-05-28 |  | 40 | 58.61
|  |  | 191-041 | Assemble manifolds and piping | 2010-03-04 | 2010-08-06 |  | 110 | [5 empty] | 123 | 492
|  | 162 | 132-001 | Title I design WBS 162 Coil leads | 2008-08-01 | 2009-03-19 |  | 155 | [9 empty] | 914
|  |  | 132-002 | PDR WBS 162 Coil leads | 2009-03-20 | 2009-03-20 |  | 1 | [9 empty] | 8
|  |  | 132-011 | Title II design WBS 162 Coil leads | 2009-03-23 | 2009-10-28 |  | 155 | [9 empty] | 914
|  |  | 132-012 | FDR WBS 162 Coil leads | 2009-10-29 | 2009-10-29 |  | 1 | [9 empty] | 8
|  |  | 132-015 | Title III design WBS 162 Coil leads | 2009-10-30 | 2010-03-31 |  | 99 | [9 empty] | 110
|  |  | 132-037 | Prep Req,Bid,Award Lead hardware and cables | 2009-10-30 | 2009-12-07 |  | 25
|  |  | 132-038 | Deliver Lead hardware and cables | 2009-12-08 | 2010-03-18 |  | 65 | 82.45
|  |  | 132-047 | Prep Req,Bid,Award Material for transition box | 2009-10-30 | 2009-12-07 |  | 25
|  |  | 132-048 | Deliver Material for Transition Boxes | 2009-12-08 | 2010-02-11 |  | 40 | 6.92
|  |  | 132-049 | Assemble Transition boxes (6) | 2010-02-12 | 2010-04-08 |  | 40 | [6 empty] | 240
|  | 163 | 163.001 | Design Coil protection(input to WBS 4 & 5) | 2008-10-01 | 2009-01-12 |  | 65 | [9 empty] | 220
|  | RBLX | ECP53RBX08 | FY07 Rebaseline exercise | 2007-05-01 | 2007-05-31 |  | 22 | [9 empty] | 40
18 | 1802 | A | 1802ORNL02 | ORNL Title III field period assy station 2 | 2007-08-14 | 2009-02-04 |  | 365 |  |  | 6 | [5 empty] | 591 | 591
|  |  | 1802ORNL03 | ORNL Title III field period assy station 3 | 2008-01-23 | 2009-05-11 |  | 327 |  |  | 6 | [5 empty] | 442 | 442
|  |  | 1802ORNL05 | ORNL Title III field period assy station 5 | 2008-08-04 | 2009-10-23 |  | 307 |  |  | 6 | [5 empty] | 444 | 444
| 1806 |  | 1803-010 | Models,design reviews, meetings,reporting, | 2007-05-01 | 2009-01-23 |  | 430 | [8 empty] | 400 | 758
|  | 1.00 | 1803-609 | Detail dwgs-spool piece | 2008-11-06 | 2009-01-27 |  | 50 | [8 empty] | 120
|  | 2.00 | 1803-201 | Station 2 Assembly Specification | 2007-05-31 | 2007-08-23 |  | 60 | [9 empty] | 80
|  |  | 1803-205 | Station 2 Assembly Drawings | 2007-05-01 | 2007-08-01 |  | 65 | [8 empty] | 160
|  | 3.00 | 1803-301 | Station 3 Assembly Specification | 2007-08-24 | 2007-11-16 |  | 60 | [9 empty] | 160
|  |  | 1803-305 | Station 3 Assembly Drawings | 2007-08-02 | 2007-11-22 |  | 80 | [8 empty] | 160
|  | 5.00 | 1803-501 | Station 5 Assembly Specification | 2008-01-02 | 2008-05-06 |  | 90 | [9 empty] | 200
|  |  | 1803-505 | Station 5 Assembly Drawings | 2008-01-02 | 2008-05-06 |  | 90 | [8 empty] | 240
|  |  | 1803-509 | Field period Assy Dwgs | 2008-01-02 | 2008-05-06 |  | 90 | [8 empty] | 160
|  |  | 1803-611 | Detail dwgs-welding ports | 2008-01-02 | 2008-05-06 |  | 90 | [8 empty] | 160
|  | 6.00 | 1803-601 | Station 6 Assembly Specification | 2008-05-01 | 2008-12-17 |  | 160 | [9 empty] | 360
|  |  | 1803-605 | Station 6 Assembly Drawings | 2008-05-01 | 2008-12-17 |  | 160 | [8 empty] | 320
|  |  | 1803-613 | Detail dwgs-man access port | 2008-05-01 | 2008-12-17 |  | 160 | [8 empty] | 80
19 | 1901 | 191 | 1901-07 | WBS 191 FY07 LOE | 2007-05-01 | 2007-09-28 |  | 106 |  |  | 3 | 0 | [5 empty] | 420.82
|  |  | 1901-08 | WBS 191 FY08 LOE | 2007-10-01 | 2008-09-29 |  | 249 |  |  | 9 | 30.44 | [5 empty] | 989.61
|  |  | 1901-09 | WBS 191 FY09 LOE | 2008-10-01 | 2009-09-28 |  | 247 |  |  | 9 | 30.44 | [5 empty] | 980.59
|  |  | 1901-10 | WBS 191 FY10 SA LOE | 2009-10-01 | 2010-09-30 |  | 248 |  |  | 8.2 | 30.44 | [5 empty] | 984.56
|  |  | 1901-11 | WBS 191 FY10 LOE | 2010-10-01 | 2011-02-23 |  | 96 |  |  | 8.2 | 30.44 | [5 empty] | 381.12
|  | 192 | 1902-07 | WBS 192 FY07 | 2007-05-01 | 2007-09-28 |  | 106 | [8 empty] | 230.02 | 344.5
|  |  | 1902-08 | WBS 192 FY08 | 2007-10-01 | 2008-09-29 |  | 249 | [8 empty] | 540 | 809.25
|  |  | 1902-09 | WBS 192 FY09 | 2008-10-01 | 2009-09-28 |  | 247 | [8 empty] | 535.99 | 802.75
|  |  | 1902-10 | WBS 192 FY10 | 2009-10-01 | 2010-09-30 |  | 248 | [8 empty] | 538.16 | 806
|  |  | 1902-11 | WBS 192 FY10 | 2010-10-01 | 2011-03-31 |  | 122 | [8 empty] | 264.74 | 396.5
74 | 7401 |  | 1802ORNLFA | ORNL Title III final machine assy | 2009-03-17 | 2011-01-31 |  | 466 |  |  | 12 | [5 empty] | 835 | 1670