## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 21
WBS Title: Gas Fueling System
Job Number: 2101
Job Title: Fueling System
Job Manager: Bill Blanchard
Description:
Only parts of the Gas Fueling Systems (WBS 211) are included in the MIE Project. The MIE project scope is limited to a single gas injector system capable of injecting any one of the species of interest, H2, D2, or He gas, into the plasma at a time. The proposed fueling system consists of a gas delivery from a single gas cylinder and a gas injection portion consisting of one piezo electric pulse valve, one manual interface valve located at one of the upper P12 port covers. The pulse valve will be operated by a valve driver controlled by the NCSX computer system (greater than 50 T-l/sec fueling rate). In its final configuration, the system will have 2 to 4 injectors capable of injecting H2, D2, or He gas into the plasma. The controls will be upgraded with a modern PLC controlling this and other systems.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 21
WBS Title: Gas Fueling System
Job Number: 2101
Job Title: Fueling System
Job Manager: Bill Blanchard
Description:
The proposed fueling system consists of a gas delivery from a single gas cylinder and a gas injection portion consisting of one piezo electric pulse valve, one manual interface valve located at one of the upper P12 port covers. The pulse valve will be operated by a valve driver controlled by the NCSX computer system (greater than 50 T-l/sec fueling rate).
| K$ | Hours
Task ID |  | EMEM | EMSM | EMSB | EMTB | EASB | EEEM | EESM | EESB | EETB | Basis of Estimate
Title I and II Design | [10 empty] | This is a relatively simple system that utilizes some existing parts/components already at PPPL. Estimate based on prior experience on similar systems (e.g., NSTX), adjusted for the simplicity of this system. Includes some P&ID drawings, weld drawings, fabrication drawings, two reviews (PDR & FDR) and installation and test procedures. Input from experienced engineers/personnel familiar with specific parts of this scope was used for estimates. Includes overall design and oversight, design activities (dwgs, support and bracket design, overall configuration of the system) and purchasing of components.
Pro-E models (avg)
assy dwgs
Detail drawings
installation dwg
designer oversight
electrical schematic
I&C schematic
stress analysis
thermal analysis
special analysis (electromagnetics)
Procurement Specifications
preliminary and final design reviews
Subtotal Title I & II Design | 5 | 120 | 0 | 96 | 64 | 32 | 0 | 96 | 0 | 0 | M&S included function generator/valve driver (~$3K) + miscellaneous
Title III |  | Hours EMEM: 40 | This effort includes fabrication/welding/assembly, installation, oversight, leak checking of the subsystems, procedures, and initial operation and testing.
Subtotal Title III | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
See Table I

## Table III - FabAssy & Instl
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 211
WBS Title: Gas Fueling Systems
Job Number: 2101
Job Title: Fueling Systems
Job Manager: Bill Blanchard
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although may be similar to previous designs, some design features (not yet defined)
-10%/+15%
| Design Complexity |  |  | X |  | Anticipated to only require standard components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)