## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 22
WBS Title: Vacuum Pumping System
Job Number: 2201
Job Title: Vacuum Pumping System
Job Manager: Bill Blanchard
Description:
The MIE project scope is limited to one TMP backed by an existing mechanical/booster pump system. Design, fabrication, installation, and system testing of equipment needed to implement the vacuum pumping system. In the future, NCSX Vacuum Pumping System will use as much as possible of the existing PBX-M vacuum pumping system hardware where it is cost effective to implement.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 22
WBS Title: Vacuum Pumping System
Job Number: 2201
Job Title: Vacuum Pumping System
Job Manager: Bill Blanchard
Description:
The proposed design consists of a high vacuum system which is manually operated and includes an isolation valve, a vertical pumpduct on a lower P12 port cover and one 1500 l/s TMP. The TMP will be backed by an existing booster mechanical pump system. The system will also contain one unshielded RGA and one ion gauge with and a valved access port for initially roughing down the vacuum vessel.
| K$ | Hours
Task ID | M&S | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | EESB | EETB | Basis of Estimate
Title I and II Design | [11 empty] | This is a relatively simple vacuum pumping system that will utilize major components (TMP, isolation valves, booster and mechnical pump) already at PPPL. Estimate based on prior experience on similar systems (e.g., NSTX), adjusted for the simplicity of this system. Input from experienced engineers/personnel familar with specific parts of this scope was used for estimates. Includes design activities, some P&ID drawings, weld drawings, fab drawings, calculations, two reviews (PDR & FDR), oversight and purchasing of components. The system should have an approximate pumping speed of 700 l/s for attaining 4e-7 Torr or less after the vacuum vessel has been baked out and the surfaces well conditioned.
AC Power / Instrumentation
AC Power for Backing System | K$ M&S: 3; Hours EASB: 72; Hours EEEM: 16
AC Power for Instrumentation Rack | K$ M&S: 3; Hours EASB: 88; Hours EEEM: 24
Rack to Instrumentation | K$ M&S: 1.536; Hours EASB: 40; Hours EESM: 48
VPS (Mechanical) | K$ M&S: 10; Hours EMEM: 208; Hours EMSB: 96; Hours EASB: 64; Hours EESM: 48
Subtotal Title I & II Design | 17.536 | 208 | 0 | 96 | 0 | 0 | 264 | 40 | 96 | 0 | 0 | M&S includes standard cabling, raceways, conduits, etc. For VPS M&S includes piping and other miscellaneous items. Major components available from legacy equipment.
Title III | [11 empty] | This effort includes both fabrication/welding/assembly, installation, oversight, leak checking of the subsystems, installation procedure, refurbishmnet of legascy equipment as required and initial operation and testing.
AC Power / Instrumentation
AC Power for Backing System | Hours EETB: 104
AC Power for Instrumentation Rack | Hours EETB: 144
Rack to Instrumentation | Hours EETB: 112
VPS (Mechanical) | Hours EMTB: 232
Subtotal Title III | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 0 | 0 | 360

## Table II - M&S
WBS Number: 22
WBS Title: Torus Vacuum Pumping Systems
Job Number: 2201
Job Title: Vacuum Pumping Systems
Job Manager: Bill Blanchard
Materials and Subcontracts (M&S) | Basis of Estimate
Description:
Included in Table I

## Table III - FabAssy & Instl
WBS Number: 22
WBS Title: Torus Vacuum Pumping Systems
Job Number: 2201
Job Title: Vacuum Pumping Systems
Job Manager: Bill Blanchard
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 22
WBS Title: Torus Vacuum Pumping Systems
Job Number: 2201
Job Title: Vacuum Pumping Systems
Job Manager: Bill Blanchard
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  | X |  |  | Although may be similar to previous designs, some design features (not yet defined)
-10%/+15%
| Design Complexity |  |  | X |  | Anticipated to only require standard components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)