## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description:
This WBS element consists of the design and fabrication of the coil electrical leads inside the cryostat which then connect the coils to the power supply bus or cables outside the cryostat.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description:
This effort covers all Title I, II, and III engineering for the LN2 distribution system inside the cryostat, which includes all the necessary manifolding and connections to interface with the ex-cryostat LN2 supply system. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS 7.
HOURS
Task ID | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL DSN | ORNOL RM | EMEM | EMSM | EMSB | EMTB | EAEM | EASM | EEEM | EESM |  | EESB | EETB | ECEM | ECSB | ECTB | Basis of Estimate
Title I an II Design
Pro-E models (avg) | 8 | hrs/model | 50 | 400 | 400 | [16 empty] | See Worksheet below - based on recent experience at MDL
assy dwgs | 16 | hrs/dwg | 15 | 240 | 240 | [16 empty] | See Worksheet below - based on recent experience at MDL
Detail drawings | 8 | hrs/dwg | 40 | 320 | 320 | [16 empty] | See Worksheet below - based on recent experience at MDL
installation dwg | 16 | hrs/dwg | 29 | 464 | 464 | [16 empty] | See Worksheet below - based on recent experience at MDL
cooling schematic | 0 | hrs/dwg | 1 | 0 | 0 | [16 empty] | See Worksheet below - based on recent experience at MDL
electrical schematic | 8 | hrs/dwg | 14 | 112 | 112 | [16 empty] | See Worksheet below - based on recent experience at MDL
I&C schematic | 8 | hrs/dwg | 0 | 0 | 0 | [16 empty] | See Worksheet below - based on recent experience at MDL
stress analysis | 0 | hrs/calc | 0 | 0 | 0 | [16 empty] | See Worksheet below - based on recent experience at MDL
thermal analysis | 24 | hrs/calc | 1 | 24 | 24 | [16 empty] | See Worksheet below - based on recent experience at MDL
special analysis (electromagnetics) | 40 | hrs/calc | 1 | 40 | 40 | [16 empty] | See Worksheet below - based on recent experience at MDL
Procuremnt Specifications | 40 | hrs/spec | 1 | 40 | 40 |  |  | 0 | [13 empty] | See Worksheet below - based on recent experience at MDL
preliminary and final design reviews | 40 | hrs/rev | 1 | 40 | 40 | [16 empty] | See Worksheet below - based on recent experience at MDL
meetings/reporting/presentations | 10% | % of tot hrs |  | 168 | 168 | [16 empty] | See Worksheet below - based on recent experience at MDL
Subtotal Title I & II Design |  |  |  | 1848 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Title III
vendor inspection & oversight | 8 | hrs per | 1 | 8 | 8
Disposition of deviation requests and non-conformances | 0.5 | hrs/wk | 20 | 10 | 10 | [16 empty] | Based on recent experience on NCSX
In-House fab/assy oversight & inspection | 2 | hrs/wk | 4 | 8 | [8 empty] | 8
As-built drawings | 1 | hrs/dwg | 84 | 84 | 84 | [16 empty] | Based on recent experience on NCSX
Subtotal Title III Design |  |  |  | 110 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Notes and worksheets
PF Coil leads
| coils at 10, 70, 130, 190, 250, 310 degrees | coils at 30, 90, 150, 210, 270, 330 degrees | coils at 50, 110, 170, 230, 290, 350 degrees | PF1-2 | PF3 | PF4 | PF5 | PF6 | coils at 0, 120, 240, degrees, top and bottom | coils at 60, 180, 300 degrees Top and bottom | Outer perimeter coils | coil 1 at 10, 70, 130, 190, 250, 310 degrees | coil 2 at 30, 90, 150, 210, 270, 330 degrees | coil 3 at 50, 110, 170, 230, 290, 350 degrees | thermal transition box | total
Pro-E models | 6 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 6 | 6 | 6 | 1 | 50 | [5 empty] | leads modeled to create drawings, reserve space in assembly
assy dwgs | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15 | [5 empty] | one assembly for each circuit
Detail drawings | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 40 | [5 empty] | drawings for lead length, mounting details
installation dwg | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 29 | [5 empty] | one installation dwg for each cable
cooling schematic | [15 empty] | 1 | [5 empty] | one cooling schematic for all leads
electrical schematic | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 14 | [5 empty] | one schematic for each circuit
I&C schematic | [21 empty] | part of WBS 163
stress analysis
thermal analysis | [15 empty] | 1 | [5 empty] | one analysis to check temp rise, cooling
special analysis | [15 empty] | 1 | [5 empty] | one analysis for field error determination
procurement specifications | [15 empty] | 1 | [5 empty] | one specification for leads, all carry the same current, will have the same terminations, only the lengths are different
preliminary and final design reviews | [15 empty] | 1 | [5 empty] | one review for all coil leads
meetings/reporting/presentations | [15 empty] | 10%

## Table II - M&S
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Description: | [5 empty] | Basis of Estimate
This effort covers all coil leads that connect the coil terminals to the buswork at the boundary of the cryostat. The lead cables are all the same except for length, and will be procured from a qualified vendor. All installation will be performed as pa
Assumptions:
outside engr rate = | 120 | $ per hour |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
outside fab rate = | 60 | $ per hour |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
outside inspection/technician rate = | 80 | $ per hour |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
TOTAL MATERIAL COST = |  | 86687.3788
Purchased parts:
set of cables | 0
misc attachment hardware | 11090.7298 | @10$/ft
thermal transition box material | 0 |  |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
subtotal, purchased parts | 11090.7298
Lead bundles consist of six, 250 MCM cable with teflon sleeve. |  | Lead ends are cooled by bleed liquid nitrogen supplied by the coil coolant header (WBS 161)
Leads connect from coil terminals to buswork at bottom of machine.
Each coil is connected separately except PF1 and PF2, which are connected in series within the central solenoid assembly
Purchased materials for in-house fabrication and sub-assembly
None required | 0
subtotal purchased materials | 0
Worksheet, TF Coils:
Lead cost, TF Coils
Terminations,assembly | 200 | ea |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 18
Total length of cables | 277.0428
Total cable cost | 17452.1382
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 11 | ft
height of lower terminals | 7 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 11 | 12.9199
coils at 70, 190, 310 degrees | 3 | 7 | 8.9199
coils at 30, 150, 270 degrees | 3 | 11 | 16.7596
coils at 90, 210, 330 degrees | 3 | 7 | 12.7596
coils at 50, 170, 290 degrees | 3 | 11 | 22.5192
coils at 110, 230, 350 degrees | 3 | 7 | 18.5192
Subtotals |  |  | 73.8781
Total length | 221.6342 | ft
25% extra for bends, offsets | 55.4086
Total procured length | 277.0428 | ft
Avg length per cable | 15.3913 | ft
Worksheet, PF Coils:
Lead cost, PF Coils
Terminations,assembly | 200 | ea |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 10
Total length of cables | 181.0457
Total cable cost | 11052.286
Geometry
radius of vertical runs | 10 | ft
height of upper runs | 12 | ft
height of connection to buswork | 0 | ft
Lengths | terminal radius | height from midplane | top length | bottom length
| (m) | (m) | (ft) | (ft)
TF Coils
PF1, PF2, connected in series as assy | 0 | 1.3 | 29.7349 | 14.2651
PF3 | 0 | 1.3 | 29.7349 | 14.2651
PF4 | 0.69 | 1.6 | 26.4869 | 12.9856
PF5 | 2.23 | 1.5 | 7.605 | 7.605
PF6 | 2.8 | 1 | 4.0945 | 4.0945
External Trim Coils
Mod Coils
Subtotals |  |  | 97.6562 | 53.2152
Total length | 150.8714 | ft
20% extra for bends, toroidal offsets | 30.1743
Total procured length | 181.0457 | ft
Avg length per cable | 18.1046 | ft
Worksheet, Error field correction coil leads:
Lead cost, Error field coils
Terminations,assembly | 200 | ea |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 2
Total length of cables | 104.399
Total cable cost | 5619.9483
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 12 | ft
height of lower terminals | 6 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 0 degrees, top and bottom | 3 | 12 | 13.9199
Subtotals |  |  | 13.9199
Total length | 83.5192 | ft
25% extra for bends, offsets | 20.8798
Total procured length | 104.399 | ft
Avg length per cable | 52.1995 | ft
Worksheet, Mod coils:
Lead cost for modular coils
Terminations,assembly | 200 | ea |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Cable with teflon insulation, reinforced teflon outer jacket | 50 | per foot |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
Total number of cables | 36
Total length of cables | 546.5855
Total cable cost | 34529.2764
Geometry
radius of vertical runs | 12 | ft
height of upper terminals | 10 | ft
height of lower terminals | 8 | ft
Lengths | terminal radius | height from floor | cable length
| (m) | (ft) | (ft)
coils at 10, 130, 250 degrees | 3 | 10 | 11.9199
coils at 70, 190, 310 degrees | 3 | 8 | 9.9199
coils at 30, 150, 270 degrees | 3 | 10 | 15.7596
coils at 90, 210, 330 degrees | 3 | 8 | 13.7596
coils at 50, 170, 290 degrees | 3 | 10 | 21.5192
coils at 110, 230, 350 degrees | 3 | 8 | 19.5192
Subtotals |  |  | 72.8781
Total length | 218.6342 | ft
25% extra for bends, offsets | 54.6586
Total procured length | 546.5855 | ft
Avg length per cable | 15.1829 | ft
Worksheet, lead thermal transition box
66 leads, 11 to a box | size
| (in) | number reqd | cost ea | total
sheet material, foil backed insul. foam | 1 x 48 x 96 | 5 | 25 | 125 |  | Based on recent experiences on NCSX and UT work being done at MDL
end seals | 1" tube x 6" | 22 | 20 | 440 |  | Based on recent experiences on NCSX and UT work being done at MDL
cryo epoxy |  | .5 lb | 28.3333 | 14.1667 |  | Based on recent experiences on NCSX and UT work being done at MDL
misc mount hardware, ss base frame |  |  |  | 500 |  | Based on recent experiences on NCSX and UT work being done at MDL
foam caulk | 16 oz | 4 | 4 | 16 |  | Based on recent experiences on NCSX and UT work being done at MDL
acryic sheet window | 3/8" x 12 x 24 | 1 | 62 | 62 |  | Based on recent experiences on NCSX and UT work being done at MDL
assembly | 40 hr each= | 40 |  |  |  | Based on recent experiences on NCSX and UT work being done at MDL
|  |  |  | 1157.1667 | each
number required for test floor |  |  |  | 6
|  |  | Total hrs for fab | 240
|  |  | Total M&S | 6943

## Table III Fab & Assy
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Fabrication and Assembly
No local fab or assembly is anticipated for the Coil leads. Installation is part of WBS 7.

## Table IV - Conting & Risk
WBS Number: 162
WBS Title: Coil Electrical Leads
Job Number: 1601-162
Job Title: Coil Electrical Leads
Job Manager: Paul Goranson
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) |  | Comments/Other Considerations
| Design Maturity | X |  |  |  | Design well established based on previous devices
-5%/+10%
| Design Complexity |  |  | X |  | Standard Components
Other Comments:
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[9 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan |  | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)