## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 171
WBS Title: Cryostat
Job Numbers: 1701 and 1751
Job Titles: Cryostat Design (1701) and Cryostat Procurements (1751)
Job Manager:G. Gettelfinger
Description:
This WBS element includes the efforts to design and fabricate the cryostat shell & structure, the wall insulation for the cryostat shell & structure, attachments for the structural support of internal components, and the required electrical, cooling and mechanical penetrations. Provisions shall be established to maintain thermal and electrical isolation, local I&C, and appropriate interface control with the other WBS elements.
Schedule:
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 171
WBS Title: Cryostat
Job Number: 1701
Job Titles: Cryostat Design
Job Manager:G. Gettelfinger
Description:
This tab covers all Title I, II, and III engineering for the insulating cryostat, which includes penetrations for all piercing conduits, pipes, and structures. This system will be fabricated in-house by PPPL. All Title III engr associated with installation is included in WBS In this job. Shop fab hours are covered in tab 3. Test cell installation time (approx. 1200 hrs.) is in WBS 7xx.
Job 1701
HOURS
Task ID |  | Multiplier | Unit | Number of Units | Hours | ORNL EM | ORNL DSN | ORNOL RM | EMEM | EMSM | EMSB | EMTB | EAEM | EASB | EEEM | EESM | Basis of Estimate
Title I and II Design
Pro-E models (avg) |  | 8 | hrs/model | 21 | 168 | [8 empty] | 168 |  |  | Based on recent experience on similar projects
assy dwgs |  | 12 | hrs/dwg | 18 | 216 | [8 empty] | 216 |  |  | Based on recent experience on similar projects
Detail drawings |  | 12 | hrs/dwg | 20 | 240 | [8 empty] | 240 |  |  | Based on recent experience on similar projects
installation dwg |  | 12 | hrs/dwg | 15 | 180 | [8 empty] | 180 |  |  | Based on recent experience on similar projects
designer oversight |  | 320 | hrs | 1 | 320 |  |  |  | 320 | [7 empty] | Engineering judgement based on recent experience tempered by WBS manager
electrical schematic |  | 0 | hrs/dwg | 0 | 0 | 0
I&C schematic |  | 0 | hrs/dwg | 0 | 0 | 0
stress analysis |  | 200 | hrs/calc | 1 | 200 | [7 empty] | 200 |  |  |  | Engineering judgement based on recent experience tempered by WBS manager
thermal analysis |  | 160 | hrs/calc | 0 | 0 | [7 empty] | 0
special analysis (electromagnetics) |  | 0 | hrs/calc | 0 | 0 | 0
Procuremnt Specifications |  | 0 | hrs/spec | 0 | 0 | 0
preliminary and final design reviews |  | 80 | hrs/rev | 1 | 80 |  |  |  | 80 | [7 empty] | Engineering judgement based on recent experience tempered by WBS manager
Subtotal Title I & II Design |  |  |  |  | 1404 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 200 | 804 | 0 | 0
Title III
vendor inspection & oversight |  | 0 | hrs per | 1 | 0 | 0
Disposition of deviation requests and non-conformances |  | 0 | hrs/wk | 20 | 0 | 0
In-House fab/assy oversight & inspection |  | 14 | hrs/wk | 20 | 280 |  |  |  | 280
Prelimary shake-down testing |  | 40 | hrs/wk | 2 | 80 |  |  |  | 80 | [7 empty] | Based on past system start-ups.
As-built drawings |  | 0 | hrs/dwg | 84 | 0 | 0
Subtotal Title III Design |  |  |  |  | 360 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Table II - M&S
WBS Number: 171
WBS Title: Cryostat
Job Numbers: 1751
Job Title: Cryostat Procurements
Job Manager:G. Gettelfinger
Materials and Subcontracts (M&S)
Materials |  |  |  | Assumptions |  |  |  | Basis of Estimate
Purchased raw goods: | $/unit | # units | Line Total | Assume the stellarator's cryostat is a sphere that is 18 ft in diameter. |  | Assume a sphere 18-foot dia
Cryostat
Extren Boards - Ribs | 493 | 36 | 17748 | 1017.9 sq ft |  | 1017.8784 | sqft | See McMaster Carr Catalogue Item (see Table V)
Extren Boards - Flats | 493 | 48 | 23664 | 31.8 4x8 sheets (no waste) |  | 31.8087 | 31 sheets no waste 1 layer | See McMaster Carr Catalogue Item (see Table V)
Urethane Foam - Cans | 7 | 200 | 1400 | 47.7 sheets (assumes 50% waste) |  | 47.7131 | 48 sheets, 33% waste | Current retail price (Home Depot)
1" Rigid Urethane Foam | 19 | 288 | 5472 |  |  |  |  | Current retail price (Home Depot)
Solimide Foam - Joints (bd ft) | 9 | 4750 | 42750 | Ribs assume 18 ribs and 2 sheets per rib |  | Assume 18 longitudnal & 10horiz joints |  | See vendor quote (Table V)
Alum Unistrut (10 ft) | 25 | 203.6016 | 5090.04 |  |  | 1018.008 | linear feet joints long only
Acrylic Beauty Cover Panels | 129 | 48 | 6192 | Assume 18 longitudnal & 10horiz joints |  |  |  | See McMaster Carr Catalogue Item (see Table V)
Mylar/Polyester Seal Goods | 20 | 20 | 400 | 1018.008 |  | 1583.568 | linear feet joints both dir | See McMaster Carr Catalogue Item (see Table V)
Humidity Sensor | 300 | 1 | 300 |  |  | Assume avg solimide joint 6" wde, 6 layers |  | Omega quote - see Table V
Compliant Penetrations |  |  |  | 1583.568 |  | 4750.704 | board feet
Solimide Foam - Penetrations (bd ft) | 9 | 800 | 7200 | Assume avg solimide joint 6" wde, 6 layers |  |  |  | See vendor quote (Table V)
Mylar/Polyester Seal Goods (50 sq ft) | 20 | 40 | 800 | 4750.704 |  |  |  | See McMaster Carr Catalogue Item (see Table V)
Rigid Penetrations
Extren Pipe (3" x 10") | 153 | 4 | 612 |  |  |  |  | See McMaster Carr Catalogue Item (see Table V)
Urethane Foam - Cans | 7 | 40 | 280 |  |  |  |  | Current retail price (Home Depot)
Misc M&S | 10000 | 1 | 10000 |  |  |  |  | Engineering Judgement
Subtotal M&S |  |  | 121908.04
PPPL Fabrication Support Labor |  |  |  |  | EMTB |  |  | Basis of Estimate
|  | Mech Tech Time (RESA, hrs) |  |  | 800 |  |  | Experience in jobs 1409 & 1414
|  | Water Jet Tech Time (RESA, hrs) |  |  | 240 |  |  | Estimate based on interview with waterjet operator
|  | Test Cell Tech Time (Test Cell, hrs) | [5 empty] | Covered in WBS 7
Subtotal PPPL Support Labor |  |  |  |  | 1040

## Table III Fab & Assy
WBS Number: 171
WBS Title: Cryostat
Job Numbers: 1751
Job Title: Cryostat Procurements
Job Manager:G. Gettelfinger
Fabrication and Assembly
Included in M&S Table II

## Table IV - Conting & Risk
WBS Number: 171
WBS Title: Cryostat
Job Numbers: 1701 and 1751
Job Titles: Cryostat Design (1701) and Cryostat Procurements (1751)
Job Manager:G. Gettelfinger
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
Job 1701 |  |  |  |  | -20%/+40%
| Design Maturity |  |  | X |  | Only have conceptual designs
| Design Complexity |  | X |  |  | Experience dealing with material gained, but flexible joints must be demonstrated
Job 1751 |  |  |  |  | -5%/+10%
| Design Maturity | X |  |  |  | Majority of materials are catalogue items
| Design Complexity |  |  | X |  | Standard materials
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
Job 1701 - NONE
Job 1751 - NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 171
WBS Title: Cryostat
Job Numbers: 1701 and 1751
Job Titles: Cryostat Design (1701) and Cryostat Procurements (1751)
Job Manager:G. Gettelfinger
Job 1751 Backup
Solimide Foam Basis
Plexiglass Exterior
Extren Panels
Mylar/Polyester Film
Aluminum Unistrut
Humidity Sensor Quote
Exten Pipe