## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 39
WBS Title: Diagnostics Integration & Oversight
Job Number: 3901
Job Title: Diagnostics Integration & Oversight
Job Manager: Brent Stratton
Description:
This WBS element consists of the physics support to provide diagnostic input through the detailed design phase of the machine. As the design of the core machine continues, it is important to continue the integration of diagnostics into the deviceand the NCSX facility with higher levels of definition.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 39
WBS Title: Diagnostics Integration & Oversight
Job Number: 3901
Job Title: Diagnostics Integration & Oversight
Job Manager: Brent Stratton
Description: This is a LOE effort for design intergration, interface definition, and oversight of diagnostic systems design, fabrication, and installation
|  | $ |  | Labor Hours | [7 empty] | Basis of Estimate
Task Description |  | M&S | Travel | EMEM | EMSM | EMTB | EEEM | EETB | EADM | ECEM | RM2
Design integration and oversight
| FY2007 | [9 empty] | 86.3 | Assumes 1/2 year @ 10% - based on past experience on NCSX
| FY2008 | [9 empty] | 172.6 | Assumes 1 year @ 10% - based on experience on NCSX
| FY2009 | [9 empty] | 173 | Assumes 1 year @ 10% - based on experience on NCSX
| FY2010 | [9 empty] | 345 | Assumes 1 year @ 20% - based on experience on NCSX
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 776.9

## Table II - M&S
WBS Number: 39
WBS Title: Diagnostics Integration & Oversight
Job Number: 3901
Job Title: Diagnostics Integration & Oversight
Job Manager: Brent Stratton
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 39
WBS Title: Diagnostics Integration & Oversight
Job Number: 3901
Job Title: Diagnostics Integration & Oversight
Job Manager: Brent Stratton
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 39
WBS Title: Diagnostics Integration & Oversight
Job Number: 3901
Job Title: Diagnostics Integration & Oversight
Job Manager: Brent Stratton
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Estimates based on actual NCSX experience over past several years
-5%/+10%
| Design Complexity |  |  | X |  | Estimates based on actual NCSX experience over past several years
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)