## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 41
WBS Title: AC Power
Job Number: 4101
Job Title: AC Power
Job Manager: Raki Ramkrishnan
Description:
This WBS element consists of the effort to design and reconfigure existing auxiliary and experimental AC power systems. The existing AC power infrastructure at C-site will be re-used to the maximum practical extent. A new AC distribution system, up to and including power panels, is provided in the NCSX test cell. Activities associated with the reactivation of AC power systems at C-site are included. Grounding in the NCSX test cell is provided. For initial operation, the C-Site Rectifiers will be used to power the NCSX PF and modular coils.
Schedule:
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 41
WBS Title: AC Power
Job Number: 4101
Job Title: AC Power
Job Manager: Raki Ramkrishnan
Description: This is a LOE effort for design intergration, interface definition, and oversight of diagnostic systems design, fabrication, and installation
|  | K$ |  | Labor Hours |  |  |  |  | Basis of Estimate
Task Description | Activity | M&S | Travel | EASM | ECEM | EEEM | EESM | EETB | (See Basis of Estimate Notes Below)
WBS 411 - Auxiliary AC Power
Prepare Preliminary One line diagram | 4101-100.1 |  |  | 6 |  | 2.4 | 1.6 | 0 |  | 10
Ex-Test cell AC pwr-Reactivate& new instl | 411-1-100 | 5 |  | 5 |  | 8 | 13 | 21 |  | 47
Grounding-Dsn - minimum required for first plasma | 411-2-2 |  |  | 160 |  | 72 |  |  |  | 232
Grounding-Procure | 411-2-4 | 10 | [7 empty] | 0
Grounding-Install | 411-2-6 | 17.5 |  | 56 |  | 28 |  | 112 |  | 196
Grounding-Commission | 411-2-8 |  |  | 40 |  | 24 |  | 80 | Needed prior to testing coils | 144
Test Cell AC Power Distr-Dsn | 411-3-2 |  |  | 16 |  | 8 |  |  | Covered by PPPL Facilities as an Infrastructure cost - NOT PART OF MIE PROJECT
Test Cell AC Power Distr-Procure(equipment/materials) | 411-3-4 | 10 | [6 empty] | Covered by PPPL Facilities as an Infrastructure cost - NOT PART OF MIE PROJECT
Test Cell AC Power Distr-Install | 411-3-6 | 35 |  | 64 |  | 16 | 16 | 24 | Covered by PPPL Facilities as an Infrastructure cost - NOT PART OF MIE PROJECT
Test Cell AC Power Distr-Commission | 411-3-8 |  |  |  |  | 16 | 16 | 16 | Covered by PPPL Facilities as an Infrastructure cost - NOT PART OF MIE PROJECT
Standby Power for Cryo Sys -Dsn | 411-4-2 | [7 empty] | Not Applicable - not funded at this time | 0
Standby Power for Cryo Sys -Procure | 411-4-4 | [7 empty] | Not Applicable - not funded at this time | 0
Standby Power for Cryo Sys -Install | 411-4-6 | [7 empty] | Not Applicable - not funded at this time | 0
WBS 412 - Experimental AC Power | [9 empty] | 0
C-site Pulsed AC Power Distr-Dsn | 412-1-2 |  |  | 16 |  | 16 |  |  |  | 32
C-site Pulsed AC Power Distr-Procure | 412-1-4 | 5 | [7 empty] | 0
C-site Pulsed AC Power Distr-Install | 412-1-6 |  |  | 8 |  | 8 | 16 | 80 |  | 112
C-site Pulsed AC Power Distr-Commission | 412-1-8 |  |  |  |  | 24 | 24 | 40 | Needed prior to testing coils | 88
Totals |  | 82.5 | 0 | 371 | 0 | 222.4 | 86.6 | 373
Notes on the Basis of Estimate
(1) Design and Fabrication/Installation
Estimate based on estensive experience of engineer performing similar tasks at PPPL and EBASCO - e.g. recent experience on NSTX. This is basically a job modifying existing PPPL systems and re-installing for NCSX. Design and engineering estimates developed based on assessements of the number of drawings needed (new or modified), the effort to reconfigure existing designs, interfaces with other systems, supervision of on-site contractors, and all necessary re-activation and pre-operational testing needed.
(2) M&S
M&S estimated based on similar recent procurements and needed interfaces with installation contractors - this will be Davis-Bacon covered, except tor those activities within the Test Cell.

## Table II - M&S
WBS Number: 41
WBS Title: AC Power
Job Number: 4101
Job Title: AC Power
Job Manager: Raki Ramkrishnan
Materials and Subcontracts (M&S) |  |  | Basis of Estimate
| Material | Labor |  | Status
Description - inlcuded in Table I

## Table III - FabAssy & Instl
WBS Number: 41
WBS Title: AC Power
Job Number: 4101
Job Title: AC Power
Job Manager: Raki Ramkrishnan
In-house Fabrication and Assembly and Installation
Included in Table I

## Table IV - Conting & Risk
WBS Number: 41
WBS Title: AC Power
Job Number: 4101
Job Title: AC Power
Job Manager: Raki Ramkrishnan
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty of Estimate (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | Requirements still evolving, but do not expect major perturbations
-5%/+10%
| Design Complexity |  |  | X |  | Standard electrical systems design and fabrication
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)