## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 76
WBS Title: Tooling Design & Fabrication
Job Number: 7601
Job Title: Tooling Design & Fabrication
Job Manager: Erik Perry
Description:
This WBS element consists of the activities associated with the design and fabrication of tooling required to assemble the NCSX device. The work scope includes the design and fabrication of special fixtures and tooling which will be required during final assembly of the NCSX machine components in the C-site NCSX test cell. To the extent feasible, special tooling utilized in the pre-assembly of the field periods in the TFTR test cell will be utilized.
Schedule:
See Attached
Approvals:
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 76
WBS Title: Tooling Design & Fabrication
Job Number: 7601
Job Title: Tooling Design & Fabrication
Job Manager: Erik Perry
Description:
Title I and II Engineering for PF Coils and Title III Support of Fabrication Effort. | [16 empty] | Basis of Estimate
| FY07$K |  |  |  |  | HOURS
Task ID | 41MS | 48MS | 37STK | 35TRVL | 31OT | ORNL EM | ORNL DSN | EMEM | EMSM | EMSB | EMTB | EAEM | EAEM Dsn | EASB | EEEM | EESM | EESB | EETB | ECEM | ECSB | ECTB | RM2 | RM3 | Basis of Estimate
None - this is an assembly operation

## Table II - M&S
WBS Number: 76
WBS Title: Tooling Design & Fabrication
Job Number: 7601
Job Title: Tooling Design & Fabrication
Job Manager: Erik Perry
Weldments & Assy H/w
Materials and Subcontracts (M&S) |  | Basis of Estimate
Description:
None - this is an assembly operation

## Table III - FabAssy & Instl
WBS Number: 76
WBS Title: Tooling Design & Fabrication
Job Number: 7601
Job Title: Tooling Design & Fabrication
Job Manager: Erik Perry
In-house Fabrication and Assembly and Installation
Job 7601 - Tooling Design & Fabrication | [10 empty] | Basis of Estimate
|  | K$ | Hours |  |  |  |  | Duration in Shifts | Persons per Shift | Assumptions | Estimates are based on similar assembly, installation for TFTR and NSTX
Description of Task | ACT | M&S | EAEM | Metrology | EMEM | EMSM | EMTB
Lab Fab/Assy/Installation | 713.020 |  |  |  | 80 | 42 | 140
Tooling,assy fixtures,misc equipt | 713.030 | 60
General procurements | 713.040 | 45
Welding tools, materials & equipt | 713.050 | 80
Torque wrenches and multipliers |  | 80 |  |  | 40
Subtotal Job 7301 |  | 265 | 0 | 0 | 120 | 42 | 140

## Table IV - Conting & Risk
WBS Number: 76
WBS Title: Tooling Design & Fabrication
Job Number: 7601
Job Title: Tooling Design & Fabrication
Job Manager: Erik Perry
Uncertainty of the Estimate
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity |  |  | X |  | Have extensive experience building and using special tooling for fabrication and decommissioning
-15%/+25%
| Design Complexity |  |  | X |  | Nothing exotic anticipated.
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)