## Tab 0 Approval Form
NCSX Work Approval Form (WAF)
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Management and Control - ORNL (8102)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101 & 8998) & Jim Lyon (8102)
Description:
This WBS element includes the efforts of the Laboratory Project Manager, the ORNL Deputy Project Manager, and administrative staff. Also includes the efforts of the Project Control Manager. PPPL collects direct allocation costs in charged to the NCSX Project and Program i Job 8998. The direct allocation charges are to cover the allocated charges for the Computer Division's support and maintenance of the Laboraotycomputer systems and desktop computer support at PPPL and the diagnostic and rf development activities at PPPL.
Schedule:
See Attached
Approvals: | ____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Job Manager Date
____________________________________ ___________________
Responsible Line Manager Date
____________________________________ ___________________
Project Manager Date
____________________________________ ___________________
Engineering Department Head Date

## Table I - Dsn Labor
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)
Job 8101
[5 empty] | Annualized FTE's , M&S ,Travel | [7 empty] | FY07 | [11 empty] | FY08 | [11 empty] | FY09 | [11 empty] | FY10
FY-07 ETC Update |  |  |  | Avg. last 24 months | FY07 | FY08 | FY09 | FY10 | FY11 |  | hours |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
| 81 | R///RM3 | Neilson | 0.85 | 0.85 | 0.5 | 0.5 | 0.25 | 0.25 |  | R///RM3 | Neilson | hours | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 71.9167 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583 | 35.9583
| 81 | EM//EM | Project Mgr. |  |  | 0.75 | 1 | 1 | 1
| 81 | EM//EM | Const Mgr |  |  | 0.5 | 0.5 | 0.5
| 81 | FC//AM | Strykowsky | 0.94 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 |  | FC//AM | Strykowsky | hours | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583 | 122.2583
| 81 | FC//AM | P&C Officer |  | 0.25 | 0.5 | 0.5 | 0.5 | 0.5
| 81 | B///CB | Hampton | 0.29 | 0.4 | 0.8 | 0.8 | 0.8 | 0.5 |  | B///CB | Hampton | hours | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 57.5333 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667 | 115.0667
| 81 | 41 | M&S | 6 | 12 | 10 | 10 | 6 | 3 | 41
| 81 | 35 | Travel | 9.7 | 10 | 10 | 10 | 8 | 4 | 42 |  | $k
Job 8102
[5 empty] | Annualized FTE's , M&S ,Travel | [7 empty] | FY07 N: FY07; FY08 N: FY08; FY09 N: FY09; FY10 N: FY10
| 81 | ORNL | Lyon,Akers,Martin,travel,m&s | 140 | 144.9 | 120 | 120 | 60 | 60 | budget based on actual plus 3.5%/yr - includes travel and M&S | ORNL | Lyon,Akers,Martin,travel,m&s | $k | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 12.075 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
|  | ORNL | Dep Proj. Cntl |  | 1e-07 | 39 | 40 | 41 | 0 | Converted to $ | bar: FY07 N
| 81 | ORNL | Akers |  |  |  |  | 0
| 81 | ORNL 41 | M&S |  |  |  |  | 0
| 81 | ORNL 35 | Travel |  |  |  |  | 0
Job 8998 |  |  |  |  | 144.9 | 159 | 160 | 101 | 60
[5 empty] | Annualized FTE's , M&S ,Travel |  |  |  | 0.24 |  |  |  | FY07 N: FY07; FY08 N: FY08; FY09 N: FY09; FY10 N: FY10
| 89 Direct allocations (PPPL applied "overhead") |  |  | n/a | 218 | 224 | 232 | 240.12 | $120/yr approx. $12k/mo. | Estimated (as calculated by PPPL based on RM's and EA analysts plus hp techs)
Basis of Estimate:
Level of Effort for Project Manager, Deputy Project Manager, and Project Control Manager for the balance of the project are estimated based on the actuals for the last two years, with adjustments. A Construction Manager is being added and Project Control support and Admin staffing is increased to strengthen management of the Project. Most of the remaining work, and all of the high-risk work, is in in-house activities carried out by an experienced PPPL Engineering Department staff. A Construction Manager us eing added to ensure schedule management in the construction & integration of the facility. Project control staff is also being augmented to strengthen cost and schedule and risk management. As part of the “standing army” costs, project management is budgeted at the FY 09 LOE rate throughout the schedule contingency period.
CD-4
CD-4

## Table II - M&S
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)
Description:
Included in Table I
Why do all of these formulas refer back to B87 => seems like it should progress with coil

## Table III Fab & Assy
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)
Fabrication and Assembly | NONE

## Table IV - Conting & Risk
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)
Uncertainty of the Estimate fgor Jobs 8101, 8202, and 8998
|  | High | Medium | Low | Uncertainty Range (%) | Comments/Other Considerations
| Design Maturity | X |  |  |  | LOE effort dependent on length of schedule
-5%/+10%
| Design Complexity |  |  | X |  | LOE effort dependent on length of schedule
Note: High/Medium/Low uncertainty assessment from Job Manager. Uncertainty range based on AACEI recommended practice 18R-97 as amended for NCSX.
Residual Impacts
[8 empty] | Cost Impact |  | Schedule Impact
Job | Risk Description |  |  |  | Likelihood of Occurring | Mitigation Plan | Basis of estimate | Low | High | Low | High
8101
| Funding profile may not match assumptions which in turn could impact cost and schedule |  |  |  | U |  | Cost impact derived from stretchout | 0 | 0 | -2 | 2
| Overhead rates may change signficiantly which in turn could impact cost and schedule |  |  |  | U |  | Calculated on basis of $45M ETC | -900 | 900 | -1 | 1
| Escalation of Copper higher than base escalation rates |  |  |  | VL | Funding limits preclude early procurements to avoid escalation impacts | See separate sheet (Table VI) - assume 5% to 20% higher per year escalation rate | 11 | 81 | 0 | 0
| Escalation of Stainless Sheet and Inconel higher than base escalation rates |  |  |  | VL | Funding limits preclude early procurements to avoid escalation impacts | See separate sheet (Table VI) - assume 5% to 20% higher per year escalation rate | 0 | 0 | 0 | 0
| GPP projects not completed in time to support project needs |  |  |  | NC | Crane/HVAC Lab/DOE overisght Ample float
| Labor rates may be significantly lower/higher than projected |  |  |  | L |  | Escalation rate may be anywhere in the range of 2-5% instead of the nominal rate of 3.4% for labor. Schedule impact is due to annual fundign constraints. | -500 | 500 | -0.5 | 0.5
8102 - NONE
8998 - NONE
Notes:
[1] | Low cost and schedule impacts are considered the minimum (0-percentile) impacts should the event occur.
High cost and schedule impacts are considered the maximum (100-percentile) impacts should the event occur
[2] | Cost impacts should be entered as man-hours (by demographic) and M&S direct cost under basis of estimate.
Cost impacts should NOT include standing army costs which are separately calculated from the schedule impact
Project control is reponsible for quantifying the low and high cost impacts based on the labor hours and M&S identified
[3] | The schedule impacts should be entered as the min and max impacts on the critical path.
If there is no critical path impact then the schedule entries should be zero.
[4] | Likelihood of occurrence should be entered consistent with our risk classification methodology, i.e.
VL= Very Likely (P>80%), L=Likely (80%>P>40%), U=Unlikley (40%>P>10%), VU=Very Unlikely (P<10%), NC=Non-credible (P<1%)

## Table V - Basis of Estimate
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)

## Table VI - Special Material Esc
WBS Number: 81
WBS Title: Project Management and Control
Job Numbers: 8101, 8102, and 8998
Job Title: Project Management and Control - ORNL (8201)
Job Title: Project Management and Control - PPPL (8101)
Job Title: Project Allocations (8998)
Job Managers: Hutch Neilson (8101), Jim Lyon (8102), & Ron Strykowsky (8998)
Special Materials
Delivery cost estimate (includes raw material cost, and vendor fabrication) |  |  |  | as spent $K
|  |  |  | FY 2007 | FY 2008 | FY 2009 | FY 2010 | FY 2011 | TOTAL
C - copper
| 1352 - Job: 1352 - PF Coil Procurement-KALISH | 141-038.1 | PF Conductor Delivery |  | 95.3 |  |  |  | 95.3
| 1354 - Job: 1354 - Trim Coil Design &Procurement-KALISH | 184-037 | External Trim Coil Procurement |  |  | 33.7 |  |  | 33.7
| 1601 - Job: 1601 - Coil Services Design-GORANSON | 132-038 | Deliver Lead hardware and cables |  |  | 64.7 | 17.8 |  | 82.5
| 4101 - Job: 4101 - AC Power-RAMAKRISHNAN | 411-2-4 | Grounding-Procure |  |  | 10 |  |  | 10
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-265 | Fabricate bus components |  |  | 45 |  |  | 45
| 4301 - Job: 4301 - DC Systems-RAMAKRISHNAN | 431-275 | Power cabling & Installation |  |  | 140 |  |  | 140
|  |  |  | 0 | 95.3 | 293.4 | 17.8 | 0 | 406.5
S - Stainless Steel/Inconnel
| 1204 - Job: 1204 - VV Sys Procurements (nonVVSA)-DUDEK | 124-130 | VV NB port cover Fabrication |  |  | 58.5 |  |  | 58.5
| 1421 - Job: 1421 - Mod Coil Interface Design-WILLIAMSON | INTRF-001 | PPPL buy SS plate for weld trials | 30 |  |  |  |  | 30
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1421-3060 | Deliver Stud Kit (PE007330) (for 1st 3 pack only | 77.6 |  |  |  |  | 77.6
| 1431 - Job: 1431 - Mod. Coil Interface Hardware-DUDEK | 1429-3060 | Deliver Shim Stock | 57.1 | 3.5 |  |  |  | 60.6
| 1752 - Job: 1752 - Base Support Proc-DAHLGREN | 161-036.9 | Deliver base support materials |  | 30 |  |  |  | 30
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-037 | Fabricate TF/MCWF mounting Components |  | 371.2 | 88.4 |  |  | 459.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-038 | Fabricate PF Mounting components |  |  | 480.1 | 108.7 |  | 588.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-039 | Fabricate Final TF Assy components Components |  |  | 83.6 |  |  | 83.6
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-040 | Fabricate Machine/base support interface |  |  | 84.8 |  |  | 84.8
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-053 | Deliver Inconnel hardware |  | 97.5 |  |  |  | 97.5
| 1550 - Job: 1550 - Coil Struct. Procurement -DAHLGREN | 162-057 | Deliver Belleville Washers |  | 13.9 |  |  |  | 13.9
|  |  |  | 164.7 | 516.1 | 795.4 | 108.7 | 0 | 1584.9
Estimate Raw material cost (delivery cost estimate x 50%)
| C - copper - base estimate (assumes 2.5%/year escalation) |  |  | 0 | 47.65 | 146.7 | 8.9 | 0 | 203.25
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 1.4295 | 8.934 | 0.82527 | 0 | 11.1888
| Additional Copper Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 9.53 | 64.548 | 6.4792 | 0 | 80.5572
| S - Stainless Steel/Inconnel (assumes 2.5%/year escalation) |  |  | 82.35 | 258.05 | 397.7 | 54.35 | 0 | 792.45
| Additional Copper Escalation - Low End of Range | 3% | additional per year | 0 | 0.03 | 0.0609 | 0.092727 | 0.12551
|  |  |  | 0 | 7.7415 | 24.2199 | 5.0397 | 0 | 37.0011
| Additional Stainless Steel/Inconel Escalation - High End of Range | 20% | additional per year | 0 | 0.2 | 0.44 | 0.728 | 1.0736
|  |  |  | 0 | 51.61 | 174.988 | 39.5668 | 0 | 266.1648