| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Robert Simmons |  |  | Date: January 20, 2004 |  |
| ECP No: ECP-04-004 |  | ECP Title: CD-2 Baseline |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Full CCB |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: 2 Federal Project Director Approving Official: |  |  |  |  |
| Actions Incorporate recommendations from a series of DOE reviews (Preliminary Design Review and combined Performance Baseline Review/External Independent Review) and follow-on discussions with OFES concerning the funding constraints and the CD-4 scope. |  |  |  |  |
| APROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Manager |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Robert Simmons | Date: January 20, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: - Recommendations from PDR, PBR, and EIR resulted in reassessment of scope, cost, and schedule baselines. In addition, as result of incorporating these recommendations, the project scope was increased and, as a result, schedule stretch-out and escalation due to funding constraints incurred. - Follow-on discussions with OFES concerning the CD-4 scope Impacted WBS Elements: All elements Impacts of Change (Briefly Describe): - PDR recommendations – include additional winding R&D, reassessment of coil services, adjustments to the cryogenics system estimates, incorporation of a 350°C bakeout, project stretch-out of approximately 2 months due to these items, and several miscellaneous minor items that include: - WBS 12 (Vacuum Vessel) – redesign of port extensions & use of skip welds; re-evaluation of viability of manual welds; reassessment of planned vacuum vessel leak provisions; and re-evaluation of the scope of the auxiliary utility lines inside the VV. - WBS 14 (Modular Coils) – reassessment of access through the VV and reassessment of the assembly tolerance budgets. - WBS 16 (Coil Services) - Reassessment of LN2 design details; re-evaluation of scope of auxiliary utility lines inside the cryostat; reassessment of impact the close confines of the cryostat on the routing of lines. - WBS 18 (Field period Assembly) – Providing additional time for pre-assembly and providing for a full size mockup. - PBR/EIR Recommendations – include cold testing of all 18 modular coils, adding a 2nd winding line, and additional time for field period assembly final alignment. In addition, the PBR/EIR team noted some inconsistencies/errors in the estimates for WBS 13 (Conventional Coils) and WBS 62 (Cryogenic Systems) and requested a reassessment and correction as necessary. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Robert Simmons | Date: January 20, 2004 |
| - Funding Constraints and CD-4 Scope Adjustments – as a result of follow-on discussions with OFES, a revised funding profile guidance with flat funding in FY2004 and FY2005 and redefinition of the CD-4 scope was provided. - As a result of the funding constraints in FY2004 and FY2005, the project incurred an additional schedule stretch-out of approximately 2 months. In addition, several activities needed to be re-sequenced, resulting in a cost growth solely due to escalation. - As a result of CD-4 scope definition that added power testing and e-beam mapping; cryostat installation, testing, and cooldown; cold power testing, and a ground fault monitor, the schedule needed to lengthened an additional 4 months and the startup testing reassessed. Assessment of Other Options: Several options were considered during discussions with OFES as to how to address these recommendations. The resultant agreements are documented in this ECP. Detailed Description of the Change: List Attachments, Impacted Documents, etc. - Primavera Database showing revised project schedule and cost baseline - Revised Summary Cost Table - Revised Funding Profile - Revised DOE Project Milestones Table - Detailed breakdown of cost impacts Description of Change: See detailed attachments. |  |