| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Robert Simmons |  |  | Date: January 27, 2004 |  |
| ECP No: ECP-04-004 |  | ECP Title: CD-2 Baseline |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Full CCB |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: 2 Federal Project Director Approving Official: |  |  |  |  |
| Actions Incorporate recommendations from a series of DOE reviews (Preliminary Design Review and combined Performance Baseline Review/External Independent Review) and follow-on discussions with OFES concerning the funding constraints and the CD-4 scope. |  |  |  |  |
| APROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Manager |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Robert Simmons | Date: January 27, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: - Recommendations from PDR, PBR, and EIR resulted in reassessment of scope, cost, and schedule baselines. As a result of incorporating these recommendations, the project scope was increased. - The CD-4 project completion criteria were expanded per OFES direction, requiring additional equipment and testing scope in the baseline. - The funding profile was modified, per OFES guidance to reduce expected FY-05 funding by $4.5M. - Updated estimates of tasks in progress were incorporated as a result of knowledge gained from design and R&D work in the first quarter of FY-04. Items (1) through (3) resulted in an increase in TEC of $5.3M and an extension of the project by 8 months, relative to the PDR baseline. Item (4) resulted in a reduction of contingency. Impacted WBS Elements: All elements Impacts of Change (Briefly Describe): - PDR recommendations – include additional winding R&D, reassessment of coil services, adjustments to the cryogenics system estimates, incorporation of a 350°C vacuum vessel bakeout capability, project stretch-out of approximately 2 months for additional testing and mock-up activities, and several miscellaneous items that include: - WBS 12 (Vacuum Vessel) – redesign of port extensions & use of skip welds; re-evaluation of viability of manual welds; reassessment of planned vacuum vessel leak provisions; and re-evaluation of the scope of the auxiliary utility lines inside the VV. - WBS 14 (Modular Coils) – reassessment of access through the VV and reassessment of the assembly tolerance budgets. - WBS 16 (Coil Services) - Reassessment of LN2 design details; re-evaluation of scope of auxiliary utility lines inside the cryostat; reassessment of impact the close confines of the cryostat on the routing of lines. - WBS 18 (Field period Assembly) – Providing additional time for pre-assembly and providing for a full size mockup. - PBR/EIR Recommendations – include cold testing of all 18 modular coils, adding a 2nd winding line, and additional effort for field period assembly final alignment. In addition, the PBR/EIR team noted some inconsistencies/errors in the estimates for WBS 13 (Conventional Coils) and WBS 62 (Cryogenic Systems) and requested a reassessment and correction as necessary. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Robert Simmons | Date: January 20, 2004 |
| - Funding Constraints and CD-4 Scope Adjustments – as a result of follow-on discussions with OFES, a revised funding profile guidance with flat funding in FY2004 and FY2005 and redefinition of the CD-4 scope was provided. - As a result of the reduced funding guidance for FY2005, the project incurred an additional schedule stretch-out of approximately 2 months. In addition, several activities needed to be re-sequenced, resulting in a cost growth solely due to escalation. - As a result of CD-4 scope definition that added power testing and e-beam mapping; cryostat installation, testing, and cooldown; cold power testing, and a ground fault monitor, the schedule needed to by lengthened by an additional 4 months. - Updated Estimates of Tasks in Progress – based on knowledge gained from design and R&D work in the first quarter of FY-04, several updated estimates were reflected in this ECP. - Revised estimates from vacuum vessel prototype vendors to reflect additional scope and greater complexity than originally estimated. - Revised estimates from modular coil prototype vendors to reflect additional scope and greater complexity than originally estimated. - Additional design and analysis for both vacuum vessel and modular coil final design effort. - Updated estimate of the twisted racetrack R&D. - Correction of omission in Project Physics estimate. Assessment of Other Options: Several options were considered during discussions with OFES as to how to address these recommendations. The resultant agreements are documented in this ECP and the PDR, PBR, and EIR Disposition Plans Detailed Description of the Change: List Attachments, Impacted Documents, etc. - Primavera Database showing revised project schedule and cost baseline - Revised Funding Profile and Budget Totals - Revised DOE Project Milestones Table - Detailed breakdown of cost impacts Description of Change: See detailed attachments. Suggest including the disposition plans as attachments. |  |