## Sheet1
WBS II | WBS III | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL | WBS II TOTALS | WBS 1 TOTALS
WBS 1 | [9 empty] | 42354986
11 - In-Vessel Components | 111 - Limiters | 7600 | [5 empty] | 7600 | 7600
12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly | 1020309 | 1802684 | 2451903 | 90745 | 12147 |  | 5377789 | 6065840
12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation |  | 60930 | 12001 | 120009 |  |  | 192940
12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib |  | 42270 |  | 344805 |  |  | 387075
12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports |  | 40769 |  | 41142 |  |  | 81911
12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C |  | 20385 |  | 5740 |  |  | 26125
13 - Conventional Coils | 130 | 121316 | 182610 |  |  |  |  | 303926 | 4168402
13 - Conventional Coils | 131 - TF Coils |  | 84095 | 621480 | 823555 | 301 |  | 1529431
13 - Conventional Coils | 132 - PF Coils |  | 51489 | 220223 | 1018001 | 510772 |  | 1800485
13 - Conventional Coils | 133 - External Trim Coils |  |  | 105271 | 332319 |  |  | 437590
13 - Conventional Coils | 134 - Conventional Coil Local |  |  |  | 71552 | 25419 |  | 96970
14 - Modular Coils | 141 - Modular Coil Winding Form | 1096040 | 3221603 | 3483505 | 1262589 |  |  | 9063737 | 20548086
14 - Modular Coils | 142 - Modular Coil Windings and Assembly | 1041146 | 2830050 | 2399625 | 2467571 | 45432 |  | 8783823
14 - Modular Coils | 143 - Modular Coil Local I&C |  |  |  | 50979 | 70223 |  | 121203
14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures | 283585 | 2295738 |  |  |  |  | 2579323
15 - Structures | 151 - Coil Support Structure |  | 164840 | 333123 | 951865 |  |  | 1449829 | 1449829
16 - Coil Services | 161 - LN2 Distribution |  |  |  | 198563 | 138961 |  | 337525 | 1036838
16 - Coil Services | 162 - Electrical Leads |  |  |  | 235265 | 385991 |  | 621255
16 - Coil Services | 163 - Coil Protection System |  |  |  | 78058 |  |  | 78058
17 - Cryostat and Base Support Structure | 171 -Cryostat | 17768 | 88222 | 247394 | 254425 | 256477 |  | 864287 | 1305323
17 - Cryostat and Base Support Structure | 172 - Base Support Structure |  | 42599 | 65214 | 328531 | 4692 |  | 441036
18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight | 88160 | 186389 | 393821 | 699621 | 2810 |  | 1370800 | 5110450
18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations |  |  |  | 92942 |  |  | 92942
18 - Field Period Assembly | 183 - Receive Inspect and Test Coils |  |  |  | 77366 |  |  | 77366
18 - Field Period Assembly | 184 - Receive Inspect and Test VV |  |  |  | 326270 |  |  | 326270
18 - Field Period Assembly | 185 - Assemble Field Periods |  |  |  | 1088607 | 268215 |  | 1356821
18 - Field Period Assembly | 186 - Tooling Design and Fabrication |  | 731506 | 303220 | 303220 | 434 |  | 1338380
18 - Field Period Assembly | 187 - Measurement Systems |  | 260527 | 237370 | 49974 |  |  | 547871
19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight | 176339 | 59478 | 217178 | 222309 | 245201 | 162000 | 1082504 | 2662618
19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis | 70452 | 429432 | 513311 | 207438 | 231336 | 128144 | 1580114
WBS 2 | [9 empty] | 1627430
21 - Fueling Systems |  |  |  |  | 60086 | 79959 |  | 140045 | 140045
22 - Torus Vacuum Pumping Systems |  | 60196 |  |  | 193136 | 130855 |  | 384187 | 384187
25 - Neutral Beam Injection System | 250 - Neutral Beam Injection System | 168753 | 87264 | 79332 | 226739 | 541110 |  | 1103198 | 1103198
WBS 3 | [9 empty] | 1681335
31 - Magnetic Diagnostics |  |  |  | 89086 | 365014 |  |  | 454101 | 454101
36 - Edge and Divertor Diagnostics |  |  |  |  | 27377 | 71910 |  | 99287 | 99287
38 - Electron Beam (EB) Mapping |  |  |  |  | 42118 | 249952 |  | 292070 | 292070
39 - Diagnostics Integration |  | 146710 | 75483 | 183997 | 187148 | 204787 | 37751 | 835877 | 835877
WBS 4 | [9 empty] | 5317506
41 - AC Power | 411 - Auxliary AC Power Systems |  | 50533 | 79399 | 240578 | 197661 |  | 568170 | 611003
41 - AC Power | 412 - Experimental AC Power Systems |  |  | 10356 | 31188 | 1288 |  | 42833
42 - AC/DC Converters | 422 - D-Site AC/DC Converters |  |  |  |  | 23534 |  | 23534 | 23534
43 - DC Systems | 431 - C-Site DC Systems |  |  |  | 171895 | 160805 |  | 332700 | 2147403
43 - DC Systems | 432 - D-to-C Site DC Systems | 2294 | 496830 |  | 824512 |  |  | 1323635
43 - DC Systems | 433 - D-Site DC Systems |  | 89597 | 17634 | 354395 | 29442 |  | 491068
44 - Control and protection Systems | 441 - Electrical Interlocks | 12060 | 71784 | 75352 | 305946 | 110330 |  | 575472 | 1593226
44 - Control and protection Systems | 442 - Kirk Key Interlocks |  |  |  | 68617 | 29421 |  | 98037
44 - Control and protection Systems | 443 - Real Time Control Systems |  |  |  | 30556 | 7842 |  | 38398
44 - Control and protection Systems | 444 - Instrument Systems |  | 9795 | 8431 | 339060 | 75604 |  | 432890
44 - Control and protection Systems | 445 - Coil protection Systems | 5990 | 14262 | 4145 | 219437 | 37573 |  | 281406
44 - Control and protection Systems | 446 - Ground Fault Monitoring |  |  |  | 34652 | 132370 |  | 167023
45 - Power System Design and Integration | 451 - System Design and Interfaces | 101514 | 157513 | 115650 | 115830 | 85178 | 3079 | 578764 | 861490
45 - Power System Design and Integration | 452 - Electrical Systems Support |  | 11553 | 22475 | 35505 | 21208 |  | 90741
45 - Power System Design and Integration | 453 - System Testing (PTP's) |  |  |  | 80304 | 111681 |  | 191985
46 - FCPC Building Modifications | 460 | 18720 | 34626 | 20566 | 6938 |  |  | 80850 | 80850
WBS 5 | [9 empty] | 2579836
51 - TCP/IP Infrastructure Systems |  |  | 12504 | 12848 | 4025 | 399649 |  | 429027 | 429027
52 - Central Instrumentation & Control |  |  |  |  | 161176 | 416864 |  | 578040 | 578040
53 - Data Acquisition & Facility Computing |  |  |  |  | 143108 | 264710 |  | 407817 | 407817
54 - Facility Timing & Synchronization |  |  |  |  | 71151 | 280881 |  | 352032 | 352032
55 - Real Time Plasma & Power Supply Control Sys |  |  |  |  | 11659 | 281621 |  | 293280 | 293280
56 - Central Safety Interlock Systems |  |  |  |  | 30048 | 369878 |  | 399926 | 399926
57 - Control Room Facility |  |  |  |  | 5636 | 114078 |  | 119714 | 119714
WBS 6 | [9 empty] | 2037582
61 - Water Systems | 611 - C-Site Cooling System |  |  |  | 9796 | 143474 |  | 153270 | 531502
61 - Water Systems | 612 - NB Water Cooling Systems |  |  |  | 38998 | 200929 |  | 239927
61 - Water Systems | 613 - Vacuum Pumping System |  | 5137 | 4685 | 16419 | 73554 |  | 99795
61 - Water Systems | 614 - Bakeout Water System |  |  |  | 24356 | 14154 |  | 38510
62 - Cryogenic Systems | 621 - LN2-LHe Supply System |  |  |  | 30498 | 222376 |  | 252873 | 747435
62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply |  |  |  | 29475 | 244915 |  | 274390
62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System |  |  |  | 35437 | 184735 |  | 220172
63 - Utility Systems |  |  | 8206 | 8173 | 23848 | 80273 |  | 120500 | 120500
64 - PFC/VV Heating & Cooling | 640 - PFC/VV Heating & Cooling |  |  |  | 109595 | 519270 |  | 628865 | 628865
65 - Facility Systems Integration | 612 - NB Water Cooling Systems | 9280 | [5 empty] | 9280 | 9280
WBS 7 | [9 empty] | 4253730
71 - Shield Wall Seismic Modifications |  | 16589 | 10490 |  |  |  |  | 27079 | 27079
72 - Control Room Refurbishment |  |  | 39512 |  |  |  |  | 39512 | 47989
72 - Control Room Refurbishment | 741 - Planning Prior to Machine Assembly |  |  |  | 8477 |  |  | 8477
73 - Platform Design & Fabrication |  |  | 54170 |  | 69971 |  |  | 124141 | 196077
73 - Platform Design & Fabrication | 741 - Planning Prior to Machine Assembly | 71936 | [5 empty] | 71936
74 - Machine Assembly Planning and Oversight | 741 - Planning Prior to Machine Assembly | 193808 | 149204 |  |  |  |  | 343013 | 1527416
74 - Machine Assembly Planning and Oversight | 742 - Construction Management |  |  | 236807 | 311497 | 371055 | 265044 | 1184403
75 - Test Cell and Basement Assembly Operations | 750 - Test Cell & Basement Assembly Operations |  | 69847 | 828 | 584291 | 1192305 | 387163 | 2234434 | 2234434
76 - Tooling Design & Fabrication |  |  | 27310 | 808 | 96734 | 95884 |  | 220735 | 220735
WBS 8 | [9 empty] | 9610729
81 - Project Management and Control | 810 - Project Management & Control | 408770 | 736916 | 624654 | 542051 | 521820 | 361158 | 3195369 | 3195369
82 - Project Engineering | 820 - Project Engineering | 485040 | 1091970 | 933340 | 870154 | 939815 | 368770 | 4689090 | 4689090
84 - Project Physics | 840 - Project Physics | 236475 | 169442 | 95530 |  |  |  | 501447 | 501447
85 - Integrated Systems Testing |  |  |  |  | 226328 | 833116 | 165378 | 1224823 | 1224823
PPPL Allocations | PPPL Allocations | 84750 | 210604 | 214140 | 214080 | 232077 |  | 955651 | 955651 | 955651
Contingency | Contingency |  | 1623007 | 1465991 | 2725260 | 6885242 | 3210471 | 15909970 | 15909970 | 15909970
|  | 5945600 | 17903175 | 15908866 | 22098560 | 19383596 | 5088958 | 86328755 | 86328755 | 86328755