## Sheet1
WBS | CD-2 Estimate | ECP-04-005 Estimate | Delta ECP-CD-2 | Delta FY2003 Actuals | Re-Estimate of R&D Tasks | Re-Estimate of Analyses & Design Tasks/Escalation | Revised M&S Estimate (Incl Prototype Contracts) | TOTALS ADDED (w/o Cont)
111 - Limiters | 7.6 | 0.06 | -7.54 | -7.5 |  |  |  | -7.54
Subtotal WBS 11 | 7.6 | 0.06 | -7.54 | -7.5 | 0 | 0 | 0 | -7.54
121 - Vacuum Vessel Assembly | 5378 | 5929 | 551 |  |  |  |  | 551
122 - Vacuum Vessel Thermal Insulation | 193 | 174.9 | -18.1 |  |  |  |  | -18.1
123 - Vacuum Vessel Heating and Cooling Distrib | 387 | 375.8 | -11.2 |  |  |  |  | -11.2
124 - Vacuum Vessel Supports | 82 | 62.6 | -19.4 |  |  |  |  | -19.4
125 - Vacuum Vessel Local I&C | 26 | 26.7 | 0.7 |  |  |  |  | 0.7
Subtotal WBS 12 | 6066 | 6569 | 503 | 83.7 | 163.5 | 256 | 0 | 503
130 - General Conventional Coil Design | 304 | 407.1 | 103.1 |  |  |  |  | 103.1
131 - TF Coils | 1529 | 1546.3 | 17.3 |  |  |  |  | 17.3
132 - CS Solenoid/133-PF Ring Coils | 1800 | 1747.4 | -52.6 |  |  |  |  | -52.6
133 - External Trim Coils | 438 | 372 | -66 |  |  |  |  | -66
134 - Conventional Coil Local I&C | 96.97 | 85.5 | -11.47 |  |  |  |  | -11.47
Subtotal WBS 13 | 4167.97 | 4158.3 | -9.67 | 0 | 0 | -10.1 | 0 | -9.67
141 - Modular Coil Winding Form | 9064 | 9171.9 | 107.9 |  |  |  |  | 107.9
142 - Modular Coil Windings and Assembly | 8784 | 8683.4 | -100.6 |  |  |  |  | -100.6
143 - Modular Coil Local I&C | 121 | 121.2 | 0.2 |  |  |  |  | 0.2
144 - Modular Coil Winding Facility & Fixtures | 2579 | 2283.4 | -295.6 |  |  |  |  | -295.6
Subtotal WBS 14 | 20548 | 20259.9 | -288.1 | 0 | 0 | -43 | -245.2 | -288.1
151 - Coil Support Structure | 1450 | 1435.9 | -14.1 |  |  |  |  | -14.1
Subtotal WBS 15 | 1450 | 1435.9 | -14.1 | 0 | 0 | -13.9 | 0 | -14.1
161 - LN2 Distribution | 338 | 337.5 | -0.5 |  |  |  |  | -0.5
162 - Electrical Leads | 621 | 621.3 | 0.3 |  |  |  |  | 0.3
163 - Coil Protection System | 78 | 78.1 | 0.1 |  |  |  |  | 0.1
Subtotal WBS 16 | 1037 | 1036.9 | -0.1 | 0 | 0 | 0 | 0 | -0.1
171 -Cryostat | 864 | 858.5 | -5.5 |  |  |  |  | -5.5
172 - Base Support Structure | 441.036 | 438.2 | -2.836 |  |  |  |  | -2.836
Subtotal WBS 17 | 1305.036 | 1296.7 | -8.336 | -8.6 | 0 | 0 | 0 | -8.336
181 - Field Period Assembly Planning/Oversight | 1371 | 1379.3 | 8.3 |  |  |  |  | 8.3
182 - TFTR Test Cell Area preparations | 93 | 92.9 | -0.1 |  |  |  |  | -0.1
183 - Receive Inspect and Test Coils | 77 | 77.4 | 0.4 |  |  |  |  | 0.4
184 - Receive Inspect and Test VV | 326 | 326.3 | 0.3 |  |  |  |  | 0.3
185 - Assemble Field Periods | 1357 | 1357.3 | 0.3 |  |  |  |  | 0.3
186 - Tooling Design and Fabrication | 1338 | 1341.5 | 3.5 |  |  |  |  | 3.5
187 - Measurement Systems | 548 | 588.8 | 40.8 |  |  |  |  | 40.8
Subtotal WBS 18 | 5110 | 5163.5 | 53.5 | 0 | 0 | 27 | 26.1 | 53.5
191 - Stellarator Core Management & Oversight | 1083 | 1083 | 0 |  |  |  |  | 0
192 - Stellarator Core Integration & Analysis | 1580 | 1581.6 | 1.6 |  |  |  |  | 1.6
Subtotal WBS 19 | 2663 | 2664.6 | 1.6 | 0 | 0 | 1.5 | 0 | 1.6
21 - Fueling Systems | 140.045 | 140 | -0.045 |  |  |  |  | -0.045
Subtotal WBS 21 | 140.045 | 140 | -0.045 | 0 | 0 | 0 | 0 | -0.045
22 - Torus Vacuum Pumping Systems | 384 | 384.2 | 0.2 |  |  |  |  | 0.2
Subtotal WBS 22 | 384 | 384.2 | 0.2 | 0 | 0 | 0 | 0 | 0.2
25 - Neutral Beam Injection System | 1103 | 1169.1 | 66.1 |  |  |  |  | 66.1
Subtotal WBS 25 | 1103 | 1169.1 | 66.1 | 37.9 | 0 | 16 | 12 | 66.1
31 - Magnetic Diagnostics | 454 | 454.1 | 0.1 |  |  |  |  | 0.1
Subtotal WBS 31 | 454 | 454.1 | 0.1 | 0 | 0 | 0 | 0 | 0.1
36 - Edge and Divertor Diagnostics | 99 | 99.3 | 0.3 |  |  |  |  | 0.3
Subtotal WBS 36 | 99 | 99.3 | 0.3 | 0 | 0 | 0 | 0 | 0.3
38 - Electron Beam (EB) Mapping | 292 | 292.1 | 0.1 |  |  |  |  | 0.1
Subtotal WBS 38 | 292 | 292.1 | 0.1 | 0 | 0 | 0 | 0 | 0.1
39 - Diagnostics Integration | 836 | 847.2 | 11.2 |  |  |  |  | 11.2
Subtotal WBS 39 | 836 | 847.2 | 11.2 | 11.3 | 0 | 0 | 0 | 11.2
411 - Auxliary AC Power Systems | 568 | 569.3 | 1.3 |  |  |  |  | 1.3
412 - Experimental AC Power Systems | 43 | 42.8 | -0.2 |  |  |  |  | -0.2
Subtotal WBS 41 | 611 | 612.1 | 1.1 | 0 | 0 | 1.1 | 0 | 1.1
422 - D-Site AC/DC Converters | 24 | 23.5 | -0.5 |  |  |  |  | -0.5
Subtotal WBS 42 | 24 | 23.5 | -0.5 | 0 | 0 | 0 | 0 | -0.5
431 - C-Site DC Systems | 333 | 326.7 | -6.3 |  |  |  |  | -6.3
432 - D-to-C Site DC Systems | 1324 | 1328.7 | 4.7 |  |  |  |  | 4.7
433 - D-Site DC Systems | 491 | 487.9 | -3.1 |  |  |  |  | -3.1
Subtotal WBS 43 | 2148 | 2143.3 | -4.7 | 0 | 0 | -4.1 | 0 | -4.7
441 - Electrical Interlocks | 575 | 578.6 | 3.6 |  |  |  |  | 3.6
442 - Kirk Key Interlocks | 98.037 | 98 | -0.037 |  |  |  |  | -0.037
443 - Real Time Control Systems | 38 | 38.4 | 0.4 |  |  |  |  | 0.4
444 - Instrument Systems | 433 | 433.2 | 0.2 |  |  |  |  | 0.2
445 - Coil Protection Systems | 281 | 283.4 | 2.4 |  |  |  |  | 2.4
446 - Ground Fault Monitoring System | 167 | 167 | 0 |  |  |  |  | 0
Subtotal WBS 44 | 1592.037 | 1598.6 | 6.563 | 0 | 0 | 5.4 | 0 | 6.563
451 - System Design and Interfaces | 579 | 591.4 | 12.4 |  |  |  |  | 12.4
452 - Electrical Systems Support | 91 | 91.4 | 0.4 |  |  |  |  | 0.4
453 - System Testing (PTP's) | 191.985 | 192 | 0.015 |  |  |  |  | 0.015
Subtotal WBS 45 | 861.985 | 874.8 | 12.815 | 0 | 0 | 13.3 | 0 | 12.815
46 - FCPC Building Modifications | 81 | 78.6 | -2.4 |  |  |  |  | -2.4
Subtotal WBS 46 | 81 | 78.6 | -2.4 | 0 | 0 | -2.3 | 0 | -2.4
51 - TCP/IP Infrastructure Systems | 429.027 | 429 | -0.027 |  |  |  |  | -0.027
Subtotal WBS 51 | 429.027 | 429 | -0.027 | 0 | 0 | 0 | 0 | -0.027
52 - Central Instrumentation & Control | 578.04 | 578 | -0.04 |  |  |  |  | -0.04
Subtotal WBS 52 | 578.04 | 578 | -0.04 | 0 | 0 | 0 | 0 | -0.04
53 - Data Acquisition & Facility Computing | 408 | 407.8 | -0.2 |  |  |  |  | -0.2
Subtotal WBS 53 | 408 | 407.8 | -0.2 | 0 | 0 | 0 | 0 | -0.2
54 - Facility Timing & Synchronization | 352.032 | 352 | -0.032 |  |  |  |  | -0.032
Subtotal WBS 54 | 352.032 | 352 | -0.032 | 0 | 0 | 0 | 0 | -0.032
55 - Real Time Plasma & Power Supply Control Sys | 293 | 293.3 | 0.3 |  |  |  |  | 0.3
Subtotal WBS 55 | 293 | 293.3 | 0.3 | 0 | 0 | 0 | 0 | 0.3
56 - Central Safety Interlock Systems | 400 | 399.9 | -0.1 |  |  |  |  | -0.1
Subtotal WBS 56 | 400 | 399.9 | -0.1 | 0 | 0 | 0 | 0 | -0.1
57 - Control Room Facility | 120 | 119.7 | -0.3 |  |  |  |  | -0.3
Subtotal WBS 57 | 120 | 119.7 | -0.3 | 0 | 0 | 0 | 0 | -0.3
611 - C-Site Cooling System | 153 | 153.3 | 0.3 |  |  |  |  | 0.3
612 - NB Water Cooling Systems | 240 | 239.9 | -0.1 |  |  |  |  | -0.1
613 - Vacuum Pumping System | 100 | 100 | 0 |  |  |  |  | 0
614 - Bakeout Water System | 39 | 38.5 | -0.5 |  |  |  |  | -0.5
Subtotal WBS 61 | 532 | 531.7 | -0.3 | 0 | 0 | 0 | 0 | -0.3
621 - LN2-LHe Supply System | 253 | 252.9 | -0.1 |  |  |  |  | -0.1
622 - LN2 Coil Cooling Supply | 274 | 274.4 | 0.4 |  |  |  |  | 0.4
623 - 623 - GN2 Cryostat Cooling System | 220 | 220.2 | 0.2 |  |  |  |  | 0.2
Subtotal WBS 62 | 747 | 747.5 | 0.5 | 0 | 0 | 0.1 | 0 | 0.5
63 - Utility Systems | 121 | 120.9 | -0.1 |  |  |  |  | -0.1
Subtotal WBS 63 | 121 | 120.9 | -0.1 | 0 | 0 | 0.4 | 0 | -0.1
64 - PFC/VV Heating & Cooling | 629 | 628.9 | -0.1 |  |  |  |  | -0.1
Subtotal WBS 64 | 629 | 628.9 | -0.1 | 0 | 0 | 0 | 0 | -0.1
65 - Facility Systems Integration | 9 | 41.6 | 32.6 |  |  |  |  | 32.6
Subtotal WBS 65 | 9 | 41.6 | 32.6 | 0 | 0 | 32.3 | 0 | 32.6
71 - Shield Wall Reconfiguration | 27 | 32.2 | 5.2 |  |  |  |  | 5.2
Subtotal WBS 71 | 27 | 32.2 | 5.2 | 0 | 0 | 5.1 | 0 | 5.2
72 - Control Room Refurbishment | 48 | 47.6 | -0.4 |  |  |  |  | -0.4
Subtotal WBS 72 | 48 | 47.6 | -0.4 | 0 | 0 | -0.4 | 0 | -0.4
73 - Platform Design & Fabrication | 196 | 159.6 | -36.4 |  |  |  |  | -36.4
Subtotal WBS 73 | 196 | 159.6 | -36.4 | 0 | 0 | -36.5 | 0 | -36.4
741 - Planning Prior to Machine Assembly | 343.013 | 430 | 86.987 |  |  |  |  | 86.987
742 - Construction Management | 1184 | 1184.2 | 0.2 |  |  |  |  | 0.2
Subtotal WBS 74 | 1527.013 | 1614.2 | 87.187 | 0 | 0 | 87.2 | 0 | 87.187
75 - Test Cell and Basement Assembly Operations | 2234 | 2160 | -74 |  |  |  |  | -74
Subtotal WBS 75 | 2234 | 2160 | -74 | 0 | 0 | -74.4 | 0 | -74
76 - Tooling Design & Fabrication | 221 | 223.7 | 2.7 |  |  |  |  | 2.7
Subtotal WBS 76 | 221 | 223.7 | 2.7 | 0 | 0 | 3 | 0 | 2.7
77 - Measurement Systems | 0 | 0 | 0 |  |  |  |  | 0
Subtotal WBS 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 - Project Management and Control | 3195 | 3354.3 | 159.3 |  |  |  |  | 159.3
Subtotal WBS 81 | 3195 | 3354.3 | 159.3 | 37 | 0 | 81 | 40.9 | 159.3
82 - Project Engineering | 4689 | 4723.1 | 34.1 |  |  |  |  | 34.1
Subtotal WBS 82 | 4689 | 4723.1 | 34.1 | 34 | 0 | 0 | 0 | 34.1
84 - Project Physics | 501 | 507.7 | 6.7 |  |  |  |  | 6.7
Subtotal WBS 84 | 501 | 507.7 | 6.7 | 15 | 0 | -8.7 | 0 | 6.7
85 - Integrated Systems Testing | 1225 | 1225 | 0 |  |  |  |  | 0
Subtotal WBS 85 | 1225 | 1225 | 0 | 0 | 0 | 0 | 0 | 0
AA - PPPL Allocations | 956 | 983.3 | 27.3 |  |  |  |  | 27.3
Subtotal Allocations | 956 | 983.3 | 27.3 | -24 | 0 | 51.6 | 0 | 27.3
CC - Contingency | 15909.97 | 15347.8 | -562.17 |  |  |  |  | -562.17
Subtotal Contingency | 15909.97 | 15347.8 | -562.17 | -178.8 | -163.5 | -387.6 | 166.3 | -562.17
Totals | 86327.755 | 86333.56 |  | 0 | 0 | 0 | 0.1 | 0.1