## P3
NCSX
ecp4 | DESC | TOTAL | ecp4 | ecp5 |  | ecp4 ecp5 reconciliation |  | ECP 4 | ECP 5 | change | Description (applies to WBS level II) |  | WBS II
11 - 11 - In-Vessel Components | 111 - Limiters | 8 |  |  |  | 11 - 11 - In-Vessel Components | 111 - Limiters | 7.6 | 0.1 | -7.5 | FY03 actual vs estimate | -7.5 | -7.5 |  | 11 - 11 - In-Vessel Components | 111 | 0.1
12 - 12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly | 5378 | 6066 | 6569 | 503 | 12 - 12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly | 5378 | 5929 | 551 | Fy03 vv design actual cost vs estimate | 59 | 503 | 503.5 | 12 - 12 - Vacuum Vessel Systems | 121 | 5929
12 - 12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation | 193 |  |  |  | 12 - 12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation | 193 | 174.9 | -18.1 | FY03 vv R&D oversight c vs e | 25 |  |  | 12 - 12 - Vacuum Vessel Systems | 122 | 174.9
12 - 12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib | 387 |  |  |  | 12 - 12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib | 387 | 375.8 | -11.2 | vsl weld joint R&D increase | 80.4 |  |  | 12 - 12 - Vacuum Vessel Systems | 123 | 375.8
12 - 12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports | 82 |  |  |  | 12 - 12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports | 82 | 62.6 | -19.4 | FY04 vv R&D oversight increase | 83.1 |  |  | 12 - 12 - Vacuum Vessel Systems | 124 | 62.6
12 - 12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C | 26 |  |  |  | 12 - 12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C | 26 | 26.7 | 0.7 | VVSA final design analyses/design | 256 |  |  | 12 - 12 - Vacuum Vessel Systems | 125 | 26.7
13 - 13 - Conventional Coils | 130 - Conventional Coils Design | 304 | 4168 | 4158.3 | -9.7 | 13 - 13 - Conventional Coils | 130 - Conventional Coils Design | 304 | 407.1 | 103.1 | Misc. escalation | -10 | -9.7 |  | 13 - 13 - Conventional Coils | 130 | 409.5
13 - 13 - Conventional Coils | 131 - TF Coils | 1529 |  |  |  | 13 - 13 - Conventional Coils | 131 - TF Coils | 1529 | 1546.3 | 17.3 |  |  |  |  | 13 - 13 - Conventional Coils | 131 | 1546.3
13 - 13 - Conventional Coils | 132 - PF Coils | 1800 |  |  |  | 13 - 13 - Conventional Coils | 132 - PF Coils | 1800 | 1747.4 | -52.6 |  |  |  |  | 13 - 13 - Conventional Coils | 132 | 1747.4
13 - 13 - Conventional Coils | 133 - External Trim Coils | 438 |  |  |  | 13 - 13 - Conventional Coils | 133 - External Trim Coils | 438 | 372 | -66 |  |  |  |  | 13 - 13 - Conventional Coils | 133 | 372
13 - 13 - Conventional Coils | 134 - Conventional Coil Local | 97 |  |  |  | 13 - 13 - Conventional Coils | 134 - Conventional Coil Local | 97 | 85.5 | -11.5 |  |  |  |  | 13 - 13 - Conventional Coils | 134 | 85.5
14 - 14 - Modular Coils | 141 - Modular Coil Winding Form | 9064 | 20548 | 20259.9 | -288.1 | 14 - 14 - Modular Coils | 141 - Modular Coil Winding Form | 9064 | 9171.9 | 107.9 | 2nd winding line | -85 | -288.1 | -288 | 14 - 14 - Modular Coils | 141 | 9171.9 | 20259.9
14 - 14 - Modular Coils | 142 - Modular Coil Windings and Assembly | 8784 |  |  |  | 14 - 14 - Modular Coils | 142 - Modular Coil Windings and Assembly | 8784 | 8683.4 | -100.6 | winding fixtures &autoclave | -158 |  |  | 14 - 14 - Modular Coils | 142 | 8683.4 | 20259.9
14 - 14 - Modular Coils | 143 - Modular Coil Local I&C | 121 |  |  |  | 14 - 14 - Modular Coils | 143 - Modular Coil Local I&C | 121 | 121.2 | 0.2 | fixtures & autoclave oversight | -41 |  |  | 14 - 14 - Modular Coils | 143 | 121.2
14 - 14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures | 2579 |  |  |  | 14 - 14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures | 2579 | 2283.4 | -295.6 | add'l materials & supplies for windings | 54 |  |  | 14 - 14 - Modular Coils | 144 | 2283.4
[11 empty] | Misc waf re-estimnates | 38
[11 empty] | MCWF prototype EIO | -65
[11 empty] | Prototype winding oversight | -31
15 - 15 - Structures |  | 1450 |  |  |  | 15 - 15 - Structures |  | 1450 | 1435.9 | -14.1 | FY04 bottoms up waf estimate | -14.1 | -14.1 |  | 15 - 15 - Structures | 151 | 1435.9
16 - 16 - Coil Services | 161 - LN2 Distribution | 338 |  |  |  | 16 - 16 - Coil Services | 161 - LN2 Distribution | 338 | 337.5 | -0.5 |  | -0.1 | -0.1 |  | 16 - 16 - Coil Services | 161 | 337.5
16 - 16 - Coil Services | 162 - Electrical Leads | 621 |  |  |  | 16 - 16 - Coil Services | 162 - Electrical Leads | 621 | 621.3 | 0.3 |  |  |  |  | 16 - 16 - Coil Services | 162 | 621.3
16 - 16 - Coil Services | 163 - Coil Protection System | 78 |  |  |  | 16 - 16 - Coil Services | 163 - Coil Protection System | 78 | 78.1 | 0.1 |  |  |  |  | 16 - 16 - Coil Services | 163 | 78.1
17 - 17 - Cryostat and Base Support Structure | 171 -Cryostat | 864 |  |  |  | 17 - 17 - Cryostat and Base Support Structure | 171 -Cryostat | 864 | 858.5 | -5.5 | FY03 actual vs estimate | -8.3 | -8.3 |  | 17 - 17 - Cryostat and Base Support Structure | 171 | 858.5
17 - 17 - Cryostat and Base Support Structure | 172 - Base Support Structure | 441 |  |  |  | 17 - 17 - Cryostat and Base Support Structure | 172 - Base Support Structure | 441 | 438.2 | -2.8 |  |  |  |  | 17 - 17 - Cryostat and Base Support Structure | 172 | 438.2
18 - 18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight | 1371 | 5110 | 5163.5 | 53.5 | 18 - 18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight | 1371 | 1379.3 | 8.3 | bottomsup waf re-estimate | 27 | 53.5 |  | 18 - 18 - Field Period Assembly | 181 | 1379.3
18 - 18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations | 93 |  |  |  | 18 - 18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations | 93 | 92.9 | -0.1 |  |  |  |  | 18 - 18 - Field Period Assembly | 182 | 92.9
18 - 18 - Field Period Assembly | 183 - Receive Inspect and Test Coils | 77 |  |  |  | 18 - 18 - Field Period Assembly | 183 - Receive Inspect and Test Coils | 77 | 77.4 | 0.4 |  |  |  |  | 18 - 18 - Field Period Assembly | 183 | 77.4
18 - 18 - Field Period Assembly | 184 - Receive Inspect and Test VV | 326 |  |  |  | 18 - 18 - Field Period Assembly | 184 - Receive Inspect and Test VV | 326 | 326.3 | 0.3 |  |  |  |  | 18 - 18 - Field Period Assembly | 184 | 326.3
18 - 18 - Field Period Assembly | 185 - Assemble Field Periods | 1357 |  |  |  | 18 - 18 - Field Period Assembly | 185 - Assemble Field Periods | 1357 | 1357.3 | 0.3 |  |  |  |  | 18 - 18 - Field Period Assembly | 185 | 1357.3
18 - 18 - Field Period Assembly | 186 - Tooling Design and Fabrication | 1338 |  |  |  | 18 - 18 - Field Period Assembly | 186 - Tooling Design and Fabrication | 1338 | 1341.5 | 3.5 |  |  |  |  | 18 - 18 - Field Period Assembly | 186 | 1341.5
18 - 18 - Field Period Assembly | 187 - Measurement Systems | 548 |  |  |  | 18 - 18 - Field Period Assembly | 187 - Measurement Systems | 548 | 588.8 | 40.8 | increased M&S | 26 |  |  | 18 - 18 - Field Period Assembly | 187 | 588.8
19 - 19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight | 1083 | 2663 | 2664.6 | 1.6 | 19 - 19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight | 1083 | 1083 | 0 | Note +$221k increase in FY04 waf's taken out |  | 1.6 |  | 19 - 19 - Stellarator Core Management and Integration | 191 | 1083
19 - 19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis | 1580 |  |  |  | 19 - 19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis | 1580 | 1581.6 | 1.6 | of future years. |  |  |  | 19 - 19 - Stellarator Core Management and Integration | 192 | 1581.6
21 - 21 - Fueling Systems |  | 140 |  |  |  | 21 - 21 - Fueling Systems |  | 140 | 140 | 0 |  | 0.2 | 0.2 |  | 21 - 21 - Fueling Systems |  | 140
22 - 22 - Torus Vacuum Pumping Systems |  | 384 |  |  |  | 22 - 22 - Torus Vacuum Pumping Systems |  | 384 | 384.2 | 0.2 |  |  |  |  | 22 - 22 - Torus Vacuum Pumping Systems |  | 384.2
25 - 25 - Neutral Beam Injection System |  | 1103 |  |  |  | 25 - 25 - Neutral Beam Injection System |  | 1103 | 1169.1 | 66.1 | Fy03 c vs est +38;Power sys testing+16Control dev M&S $12 | 66 | 66.1 |  | 25 - 25 - Neutral Beam Injection System | 250 | 1169.1
31 - 31 - Magnetic Diagnostics |  | 454 |  |  |  | 31 - 31 - Magnetic Diagnostics |  | 454 | 454.1 | 0.1 |  | 0.1 | 11.7 |  | 31 - 31 - Magnetic Diagnostics |  | 454.1
36 - 36 - Edge and Divertor Diagnostics |  | 99 |  |  |  | 36 - 36 - Edge and Divertor Diagnostics |  | 99 | 99.3 | 0.3 |  | 0.3 |  |  | 36 - 36 - Edge and Divertor Diagnostics |  | 99.3
38 - 38 - Electron Beam (EB) Mapping |  | 292 |  |  |  | 38 - 38 - Electron Beam (EB) Mapping |  | 292 | 292.1 | 0.1 |  | 0.1 |  |  | 38 - 38 - Electron Beam (EB) Mapping |  | 292.1
39 - 39 - Diagnostics Integration |  | 836 |  |  |  | 39 - 39 - Diagnostics Integration |  | 836 | 847.2 | 11.2 | FY03 actual vs estimate | 11.2 |  |  | 39 - 39 - Diagnostics Integration |  | 847.2
41 - 41 - AC Power | 411 - Auxliary AC Power Systems | 568 | 5318 | 5330.9 | 12.9 | 41 - 41 - AC Power | 411 - Auxliary AC Power Systems | 568 | 569.3 | 1.3 |  |  | 12.9 |  | 41 - 41 - AC Power | 411 | 569.3
41 - 41 - AC Power | 412 - Experimental AC Power Systems | 43 |  |  |  | 41 - 41 - AC Power | 412 - Experimental AC Power Systems | 43 | 42.8 | -0.2 | misc escalation | 12.9 |  |  | 41 - 41 - AC Power | 412 | 42.8
42 - 42 - AC/DC Converters |  | 24 |  |  |  | 42 - 42 - AC/DC Converters |  | 24 | 23.5 | -0.5 |  |  |  |  | 42 - 42 - AC/DC Converters | 422 | 23.5
43 - 43 - DC Systems | 431 - C-Site DC Systems | 333 |  |  |  | 43 - 43 - DC Systems | 431 - C-Site DC Systems | 333 | 326.7 | -6.3 |  |  |  |  | 43 - 43 - DC Systems | 431 | 326.7
43 - 43 - DC Systems | 432 - D-to-C Site DC Systems | 1324 |  |  |  | 43 - 43 - DC Systems | 432 - D-to-C Site DC Systems | 1324 | 1328.7 | 4.7 |  |  |  |  | 43 - 43 - DC Systems | 432 | 1328.7
43 - 43 - DC Systems | 433 - D-Site DC Systems | 491 |  |  |  | 43 - 43 - DC Systems | 433 - D-Site DC Systems | 491 | 487.9 | -3.1 |  |  |  |  | 43 - 43 - DC Systems | 433 | 487.9
44 - 44 - Control and protection Systems | 441 - Electrical Interlocks | 575 |  |  |  | 44 - 44 - Control and protection Systems | 441 - Electrical Interlocks | 575 | 578.6 | 3.6 |  |  |  |  | 44 - 44 - Control and protection Systems | 441 | 578.6
44 - 44 - Control and protection Systems | 442 - Kirk Key Interlocks | 98 |  |  |  | 44 - 44 - Control and protection Systems | 442 - Kirk Key Interlocks | 98 | 98 | 0 |  |  |  |  | 44 - 44 - Control and protection Systems | 442 | 98
44 - 44 - Control and protection Systems | 443 - Real Time Control Systems | 38 |  |  |  | 44 - 44 - Control and protection Systems | 443 - Real Time Control Systems | 38 | 38.4 | 0.4 |  |  |  |  | 44 - 44 - Control and protection Systems | 443 | 38.4
44 - 44 - Control and protection Systems | 444 - Instrument Systems | 433 |  |  |  | 44 - 44 - Control and protection Systems | 444 - Instrument Systems | 433 | 433.2 | 0.2 |  |  |  |  | 44 - 44 - Control and protection Systems | 444 | 433.2
44 - 44 - Control and protection Systems | 445 - Coil protection Systems | 281 |  |  |  | 44 - 44 - Control and protection Systems | 445 - Coil protection Systems | 281 | 283.4 | 2.4 |  |  |  |  | 44 - 44 - Control and protection Systems | 445 | 283.4
44 - 44 - Control and protection Systems | 446 - Ground Fault Monitoring | 167 |  |  |  | 44 - 44 - Control and protection Systems | 446 - Ground Fault Monitoring | 167 | 167 | 0 |  |  |  |  | 44 - 44 - Control and protection Systems | 446 | 167
45 - 45 - Power System Design and Integration | 451 - System Design and Interfaces | 579 |  |  |  | 45 - 45 - Power System Design and Integration | 451 - System Design and Interfaces | 579 | 591.4 | 12.4 |  |  |  |  | 45 - 45 - Power System Design and Integration | 451 | 591.4
45 - 45 - Power System Design and Integration | 452 - Electrical Systems Support | 91 |  |  |  | 45 - 45 - Power System Design and Integration | 452 - Electrical Systems Support | 91 | 91.4 | 0.4 |  |  |  |  | 45 - 45 - Power System Design and Integration | 452 | 91.4
45 - 45 - Power System Design and Integration | 453 - System Testing (PTP's) | 192 |  |  |  | 45 - 45 - Power System Design and Integration | 453 - System Testing (PTP's) | 192 | 192 | 0 |  |  |  |  | 45 - 45 - Power System Design and Integration | 453 | 192
46 - 46 - FCPC Building Modifications |  | 81 |  |  |  | 46 - 46 - FCPC Building Modifications |  | 81 | 78.6 | -2.4 |  |  |  |  | 46 - 46 - FCPC Building Modifications | 460 | 78.6
51 - 51 - TCP/IP Infrastructure Systems |  | 429 | 2580 | 2579.7 | -0.3 | 51 - 51 - TCP/IP Infrastructure Systems |  | 429 | 429 | 0 |  | -0.3 | -0.3 |  | 51 - 51 - TCP/IP Infrastructure Systems |  | 429
52 - 52 - Central Instrumentation & Control |  | 578 |  |  |  | 52 - 52 - Central Instrumentation & Control |  | 578 | 578 | 0 |  |  |  |  | 52 - 52 - Central Instrumentation & Control |  | 578
53 - 53 - Data Acquisition & Facility Computing |  | 408 |  |  |  | 53 - 53 - Data Acquisition & Facility Computing |  | 408 | 407.8 | -0.2 |  |  |  |  | 53 - 53 - Data Acquisition & Facility Computing |  | 407.8
54 - 54 - Facility Timing & Synchronization |  | 352 |  |  |  | 54 - 54 - Facility Timing & Synchronization |  | 352 | 352 | 0 |  |  |  |  | 54 - 54 - Facility Timing & Synchronization |  | 352
55 - 55 - Real Time Plasma & Power Supply Control Sys |  | 293 |  |  |  | 55 - 55 - Real Time Plasma & Power Supply Control Sys |  | 293 | 293.3 | 0.3 |  |  |  |  | 55 - 55 - Real Time Plasma & Power Supply Control Sys |  | 293.3
56 - 56 - Central Safety Interlock Systems |  | 400 |  |  |  | 56 - 56 - Central Safety Interlock Systems |  | 400 | 399.9 | -0.1 |  |  |  |  | 56 - 56 - Central Safety Interlock Systems |  | 399.9
57 - 57 - Control Room Facility |  | 120 |  |  |  | 57 - 57 - Control Room Facility |  | 120 | 119.7 | -0.3 |  |  |  |  | 57 - 57 - Control Room Facility |  | 119.7
61 - 61 - Water Systems | 611 - C-Site Cooling System | 153 | 532 | 531.7 | -0.3 | 61 - 61 - Water Systems | 611 - C-Site Cooling System | 153 | 153.3 | 0.3 |  | -0.3 | -0.3 |  | 61 - 61 - Water Systems | 611 | 153.3
61 - 61 - Water Systems | 612 - NB Water Cooling Systems | 240 |  |  |  | 61 - 61 - Water Systems | 612 - NB Water Cooling Systems | 240 | 239.9 | -0.1 |  |  |  |  | 61 - 61 - Water Systems | 612 | 239.9
61 - 61 - Water Systems | 613 - Vacuum Pumping System | 100 |  |  |  | 61 - 61 - Water Systems | 613 - Vacuum Pumping System | 100 | 100 | 0 |  |  |  |  | 61 - 61 - Water Systems | 613 | 100
61 - 61 - Water Systems | 614 - Bakeout Water System | 39 |  |  |  | 61 - 61 - Water Systems | 614 - Bakeout Water System | 39 | 38.5 | -0.5 |  |  |  |  | 61 - 61 - Water Systems | 614 | 38.5
62 - 62 - Cryogenic Systems | 621 - LN2-LHe Supply System | 253 | 747 | 747.5 | 0.5 | 62 - 62 - Cryogenic Systems | 621 - LN2-LHe Supply System | 253 | 252.9 | -0.1 |  | 0.5 | 0.5 |  | 62 - 62 - Cryogenic Systems | 621 | 252.9
62 - 62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply | 274 |  |  |  | 62 - 62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply | 274 | 274.4 | 0.4 |  |  |  |  | 62 - 62 - Cryogenic Systems | 622 | 274.4
62 - 62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System | 220 |  |  |  | 62 - 62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System | 220 | 220.2 | 0.2 |  |  |  |  | 62 - 62 - Cryogenic Systems | 623 | 220.2
63 - 63 - Utility Systems |  | 121 |  |  |  | 63 - 63 - Utility Systems |  | 121 | 120.9 | -0.1 |  | -0.1 | -0.1 |  | 63 - 63 - Utility Systems |  | 120.9
64 - 64 - PFC/VV Heating & Cooling |  | 629 |  |  |  | 64 - 64 - PFC/VV Heating & Cooling |  | 629 | 628.9 | -0.1 |  | -0.1 | -0.1 |  | 64 - 64 - PFC/VV Heating & Cooling | 640 | 628.9
65 - 65 - Facility Systems Integration |  | 9 |  |  |  | 65 - 65 - Facility Systems Integration |  | 9 | 41.6 | 32.6 | FY04 LOE support due to stretchout | 32.6 | 32.6 |  | 65 - 65 - Facility Systems Integration | 612 | 9.4
71 - 71 - Shield Wall Seismic Modifications |  | 27 | 4253 | 4237.3 | -15.7 | 71 - 71 - Shield Wall Seismic Modifications |  | 27 | 32.2 | 5.2 |  |  | -15.7 |  | 65 - 65 - Facility Systems Integration | 650 | 32.2
72 - 72 - Control Room Refurbishment |  | 48 |  |  |  | 72 - 72 - Control Room Refurbishment |  | 48 | 47.6 | -0.4 | Task re-grouping and bottomsup waf reestimate | -15.7 |  |  | 71 - 71 - Shield Wall Seismic Modifications |  | 32.2
73 - 73 - Platform Design & Fabrication |  | 196 |  |  |  | 73 - 73 - Platform Design & Fabrication |  | 196 | 159.6 | -36.4 |  |  |  |  | 72 - 72 - Control Room Refurbishment |  | 47.6
74 - 74 - Machine Assembly Planning and Oversight |  | 1527 |  |  |  | 74 - 74 - Machine Assembly Planning and Oversight |  | 1527 | 1614.2 | 87.2 |  |  |  |  | 73 - 73 - Platform Design & Fabrication |  | 70 | 159.6
75 - 75 - Test Cell and Basement Assembly Operations |  | 2234 |  |  |  | 75 - 75 - Test Cell and Basement Assembly Operations |  | 2234 | 2160 | -74 |  |  |  |  | 73 - 73 - Platform Design & Fabrication | 730 | 89.6
76 - 76 - Tooling Design & Fabrication |  | 221 |  |  |  | 76 - 76 - Tooling Design & Fabrication |  | 221 | 223.7 | 2.7 |  |  |  |  | 74 - 74 - Machine Assembly Planning and Oversight | 740 | 147.8 | 1614.2
81 - 81 - Project Management and Control |  | 3195 |  |  |  | 81 - 81 - Project Management and Control |  | 3195 | 3354.3 | 159.3 | Project mgt oversight | 81 | 159.3 |  | 74 - 74 - Machine Assembly Planning and Oversight | 741 | 281.6
[11 empty] | FY03 c vs est pppl & ornl | 37 |  |  | 74 - 74 - Machine Assembly Planning and Oversight | 742 | 1184.8
[11 empty] | PDR outside reviewers contracts | 41 |  |  | 75 - 75 - Test Cell and Basement Assembly Operations | 750 | 2160
82 - 82 - Project Engineering |  | 4689 |  |  |  | 82 - 82 - Project Engineering |  | 4689 | 4723.1 | 34.1 | FY03 cost vs estimate | 34 | 34.1 |  | 76 - 76 - Tooling Design & Fabrication |  | 223.7
84 - 84 - Project Physics |  | 501 |  |  |  | 84 - 84 - Project Physics |  | 501 | 507.65 | 6.65 | FY03 cost estimate +16k fy04 revised est -9k | 6.65 | 6.65 |  | 81 - 81 - Project Management and Control | 810 | 3354.3
85 - 85 - Integrated Systems Testing |  | 1225 |  |  |  | 85 - 85 - Integrated Systems Testing |  | 1225 | 1225 | 0 |  |  | 0 |  | 82 - 82 - Project Engineering | 820 | 4723.1
AA - PPPL Allocations |  | 956 |  |  |  | AA - PPPL Allocations |  | 956 | 983.3 | 27.3 | FY03 est= -24k FY04 revised est =+51 | 27.3 | 27.3 |  | 84 - 84 - Project Physics | 840 | 507.7
CC - Contingency |  | 15910 | [5 empty] | 70417.6 | 70982.75 | 562.15 |  | 562.85 | 565.15 |  | 85 - 85 - Integrated Systems Testing |  | 1225
[15 empty] | AA - PPPL Allocations | AAA | 983.3
|  | 86328 |  | X |  |  | CC - Contingency | 15910 | 15347.85 | -562.15 |  |  |  |  | CC - Contingency | CCC | 15344
[7 empty] | TEC= | 86327.6 | 86333.6 | [7 empty] | 70985.2
X
#REF!
X
X
X
|  |  |  | X |  |  | NCSX
|  |  |  | X |  |  | ECP5 Summary
|  |  |  | X |  |  | WBS 12 -Design & Analysis |  |  | 256
|  |  |  | #REF! |  |  | FY03 Misc Actual vs Estimate Cost |  |  | 180
|  |  |  | X |  |  | FY04 Misc Re-Estimates |  |  | 167
|  |  |  | X |  |  | WBS 12 -R&D |  |  | 163.5
|  |  |  | X |  |  | WBS 81-Project management oversight |  |  | 81
[7 empty] | WBS 14 -Winding Materials |  |  | 54
|  |  |  | #REF! |  |  | WBS 81 -PDR Outside reviewers |  |  | 41
|  |  |  | #REF! |  |  | WBS 14 -R&D |  |  | -96
|  |  |  | #REF! |  |  | WBS 14 -Fixtures & Winding HW |  |  | -284
|  |  |  | #REF! | [5 empty] | 562.5
#REF!