| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: February 27, 2004 |
| ECP No: 04-005 | ECP Title: Reconciliation of WAF Baseline |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, Project Control Manager, Engineering Manager, NCSX Project Manager, & NCSX Federal Project Director |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update WAF baseline to reflect this ECP. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: February 27, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Update NCSX Baseline to reflect latest WAF plans and schedules. Impacted WBS Elements: WBS 12, 14, 18, 25, 65, 74, 74, 81, & 84. Allocations and Contingency also impacted. Impacts of Change (Briefly Describe): This ECP reflects: Adjustments to reflect the FY2003 actual costs (+$178.8K) Adjustments to the baseline to reflect the updated WAFs through January 2004 (+$196.7K) Re-estimates of the in-house R&D activities (+$163.5K) Re-estimates of design and analysis tasks (+$215.0K) Revised estimates of prototype contracts (-$96.0K) Updated estimates of other M&S activities (-$66.0K) Updated estimates for additional scope items added at CD-2 (+$19.0K) As a result of the above changes, it is proposed to draw down contingency by approximately $610K from $15,910K to $15300K. Assessment of Other Options: None. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachment 1 – Summary Attachment 2 – Detailed Analyses by WBS Level 2 and 3 Attachment 3 – Updated NCSX Project Baseline Description of Change: This ECP updates the CD-2 baseline to reflect the actual FY2003 costs and updated plans and estimates developed over the 4-month period of October 2003 – January 2004. These plans reflect information learned in both the in-house design and R&D efforts and prototype vendor assessments and discoveries as their work proceeded. As a result of the lessons-learned in the first third of FY2004, it was determined that a significant amount of additional design and analyses and R&D was necessary to mitigate down-stream risks. |